## Blank Task List
Subcommittee | Community Engagement |  | Year |  | 2022
|  |  | Time Period |  | February-July
|  |  | Lead Agency(s) |  | Partner Subcommittees
Task Type | Description | Task Month(s) | CAMPO | GoTriangle | B&F | P&P | CE
Specialized | Receive an update to the Wake Transit project sponsor engagement strategy presentations schedule to include applicable FY2018-2021 projects | Feb |  | x
Specialized | Provide input to finalize the submission process and support the launch of the Wake Transit Activities Calendar | Feb-Mar |  | x
Specialized | Review and provide input on a standardized community demographics collection methodology | Feb-Mar |  | x
Specialized | Review and provide input to finalize the engagement summary report outline | Feb-Apr |  | x
Recurring/Annual | Review, provide input and recommend adoption of an updated Wake Transit Community Engagement Policy | Feb-Apr |  | x
Specialized | Review, provide input and recommend adoption of a Wake Transit Communications Plan | Feb-Jun |  | x
Tracking/Oversight | Receive engagement strategy presentations from Wake Transit project sponsors according to the presentation schedule | Feb-Jul |  | x
Recurring/Annual | Receive Wake Transit community engagement activity updates from project sponsors | Feb-Jul |  | x
Specialized | Review and provide input to support the GoForward/Wake web page update process | Mar-Apr |  | x
Recurring/Annual | Receive FY2023 update to the Wake Transit project sponsor engagement strategy presentations schedule | May-Jun |  | x
Recurring/Annual | Develop the 2022 August-January Work Task List | May-June | x
Recurring/Annual | Receive the annual Work Plan engagement summary report | June |  | x |  | x
Recurring/Annual | Participate in the annual Engagement & Communications after-action review process | June-July |  | x
Voting Record: | CE Subcommittee consideration to adopt: January, 31st, 2022
Motion made by Michelle Peele. Second by Allison Wylie. Voting Members:
TPAC Approval: | TPAC confirmation scheduled on February 9, 2022.

## Drop down options
Year | Time Period
2022 | February-July
2023 | August-January
2024
Task Types | Subcommittee
Recurring/Annual | Planning & Prioritization
Specialized | Community Engagement
Tracking/Oversight | Budget & Finance