## Task List Template
Subcommittee | Public Engagement & Comms |  |  |  | Fiscal Year |  | FY21
[5 empty] | Time Period |  | February-July
[5 empty] | Lead Agency(s) |  | Subcommittee Partnership(s)
Task Type | Description | Task Month(s) | Status | Notes | C | G | Process | B&F | P&P | PE&C
Recurring/Annual | Continuously disseminate information back to agencies and provide calendar information | February-July | On-Going |  |  | x |  |  |  | x
Tracking/Oversight | Receive regular process updates from Lead Agency for current Wake Transit PE&C activities | February-July | On-Going |  |  | x |  |  |  | x
Specialized | Communicate with TDM partners to determine Wake Transit PE&C support needs | February-July | On-Going |  |  | x
Recurring/Annual | Provide feedback and support for the Wake Transit Performance Tracker development process | February-July | On-Going |  | x |  |  |  |  | x
Recurring/Annual | Review list of Work Plan plans, programs and projects that will need individual PE Plans in the next fiscal year from Lead Agency | February-May | Started |  |  | x |  |  |  | x
Recurring/Annual | Receive draft schedule to receive Community Engagement Strategy project sponsor from Lead Agency | February-April | Started |  |  | x |  |  |  | x
Recurring/Annual | Review Community Engagement Policy for update recommendations to Governing Boards at their June meetings | February-April | Started |  | x | x |  |  |  | x
[5 empty] | Lead Agency(s) |  | Subcommittee Partnership(s)
Task Type | Description | Task Month(s) |  |  | CAMPO | GoTriangle | Process | B&F | P&P | PE&C
Recurring/Annual | Provide feedback and support for Annual Work Plan Strategy and FY22 outreach materials | February | Started |  |  | x |  |  |  | x
Recurring/Annual | Distribute Annual Work Plan outreach materials in accordance with adopted Annual Work Plan Strategy | February-June |  |  |  | x |  |  |  | x
Recurring/Annual | Receive and provide feedback on draft Community Engagement Strategies submitted by project sponsors as stated in the Community Engagement Policy and managed by Lead Agency | February-June |  |  |  | x |  |  |  | x
Recurring/Annual | Receive Annual Work Plan "outreach summary" | June |  |  |  | x |  |  |  | x
Recurring/Annual | Participate in after-action review and support needed revisions to Annual Work Plan Community Engagement Strategy | July |  |  |  | x |  |  |  | x
Recurring/Annual | Receive and adopt PE&C Subcommittee August-January Work Task List drafted by Chair & Vice-Chair | July |  |  |  | x |  |  |  | x | Subcommittee Work Task List
Specialized | Determine content needs for Toolkit and Guidebook and complete development in conjunction with Wake Transit Community Engagement Policy | FY22 |  |  |  | x |  |  |  | x
Specialized | Develop the initial Wake Transit Communications Plan and Communications Strategy with Lead Agency | TBD |  |  |  | x |  |  |  | x
Specialized | Receive and provide feedback on draft Comment Response Procedure for Wake Transit related public comments and media coverage from Lead Agency | TBD |  |  |  | x |  |  |  | x