## STIP
Project ID | Div | MPO/RPO | County | Description | Design Rec. Plan Set (25% Plans) Complete | Confident Scope Approved | Funding Program Description | ROW Acquisition Begins | Letting Type | Let Date | STIP Status | ROW Estimate | ROW Estimate Date | UTIL Estimate | UTIL Estimate Date | CON Estimate | CON Estimate Date | OTHER Estimate | OTHER Estimate Date
A-0010AE | 13 | French Broad River MPO | BUNCOMBE | SR 1882 (NEW STOCK ROAD) INTERCHANGE. IMPROVE INTERCHANGE AREA INCLUDING WIDENING I-26 TO NORTH OF SR 1720 (AIKEN ROAD). | Not Yet | 2024-06-04 | HIGHWAY - STI (PRIORITIZATION) | 2027-10-15 | Raleigh Letting (LET) | 2031-08-19 | Delivery | 18600000 | 2026-02-18 | 3100000 | 2026-02-18 | 93900000 | 2024-06-04
AP-0001 | 10 | Charlotte Regional TPO | MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONATIONAL AIRPORT (CLT) CONSTRUCT END AROUND TAXIWAY ON WEST SIDE OF PROPOSED FOURTH PARALLEL RUNWAY. | Yes | 2025-06-17 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2029-06-30 | Delivery |  |  |  |  | 2000000 | 2025-06-17
AV-5701 | 7 | Greensboro Urban Area MPO | GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO), RUNWAY 5R-23L EXTENSION PROGRAM | Yes | 2023-10-02 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2027-03-31 | Delivery |  |  |  |  | 21000000 | 2023-10-02
AV-5707 | 7 | Greensboro Urban Area MPO | GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO), CONSTRUCT TAXIWAY G. | Yes | 2023-10-02 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2027-06-01 | Delivery |  |  |  |  | 16900000 | 2023-10-02
AV-5711 | 7 | Greensboro Urban Area MPO | GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO), SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | Yes | 2025-02-24 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2028-12-31 | Delivery |  |  |  |  | 9000000 | 2025-02-24
AV-5715 | 7 | Greensboro Urban Area MPO | GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO),RUNWAY 5R-23L GROUP VI UPGRADE. | Yes | 2023-10-02 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2029-01-01 | Delivery |  |  |  |  | 11000000 | 2023-10-02
AV-5718 | 7 | Greensboro Urban Area MPO | GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO), HIGH SPEED TAXIWAY TO RUNWAY 5R-23L | Yes | 2023-10-02 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2027-06-01 | Delivery |  |  |  |  | 4000000 | 2023-10-02
AV-5731 | 10 | Cabarrus-Rowan MPO | CABARRUS | CONCORD-PADGETT REGIONAL AIRPORT (JQF),EXPAND COMMERCIAL TERMINAL APRON. PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION). | Yes | 2021-06-14 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2027-03-01 | Delivery |  |  |  |  | 7917000 | 2021-06-14
AV-5734 | 6 | Fayetteville Area MPO | CUMBERLAND | FAYETTEVILLE REGIONAL AIRPORT (FAY), REPLACE PERIMETER FENCING AND ROAD | Yes | 2023-01-20 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2026-09-30 | Delivery |  |  |  |  | 3440000 | 2023-01-20
AV-5737 | 7 | Burlington-Graham MPO | ALAMANCE | BURLINGTON-ALAMANCE REGIONAL AIRPORT (BUY) OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN RUNWAY 24 APPROACH. | Not Yet | Not Yet | AVIATION - STI (PRIORITIZATION) | 2026-07-01 | NON - DOT LET (Aviation) | 2040-01-01 | Delivery | 1200000 | 2022-08-16
AV-5738 | 9 | Winston-Salem Area TPO | FORSYTH | SMITH REYNOLDS AIRPORT (INT), ACQUIRE LAND AND CLEAR TERRAIN OBSTRUCTIONS EAST OF RUNWAY 15-33 TO DRAIN AND GRADE MATERIAL IN PLACE | Not Yet | Not Yet | AVIATION - STI (PRIORITIZATION) | 2017-08-03 | NON - DOT LET (Aviation) | 2030-07-15 | Delivery | 250000 | 2025-03-04 |  |  | 6000000 | 2025-02-26
AV-5741 | 12 | Greater Hickory MPO | CATAWBA | HICKORY REGIONAL AIRPORT (HKY), 600 FEET EXTENSION OF RUNWAY 6 - PHASE I & II | Not Yet | 2026-09-01 | AVIATION - STI (PRIORITIZATION) | 2027-06-30 | NON - DOT LET (Aviation) | 2029-03-31 | Delivery |  |  | 600000 | 2025-07-11 | 3844000 | 2021-08-05
AV-5743 | 2 | Mid-East RPO | BEAUFORT | WARREN FIELD AIRPORT (OCW), ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | Not Yet | Not Yet | AVIATION - STI (PRIORITIZATION) | 2029-07-11 | NON - DOT LET (Aviation) | 2031-07-09 | Delivery | 2200000 | 2024-11-26 |  |  | 7800000 | 2024-11-26
AV-5744A | 3 | Cape Fear RPO | PENDER | HENDERSON FIELD (ACZ) EXTEND RUNWAY 5,500 FEET. | Yes | 2025-02-25 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2026-12-31 | Delivery |  |  |  |  | 4405000 | 2025-02-25
AV-5761 | 8 | Lumber River RPO | RICHMOND | RICHMOND COUNTY AIRPORT (RCZ ), CLEAR OBSTRUCTION IN RUNWAY14 APPROACH | Not Yet | Not Yet | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2026-05-01 | Delivery |  |  |  |  | 570000 | 2023-10-02
AV-5798 | 3 | Wilmington Urban Area MPO | NEW HANOVER | ILM NEW HANOVER COUNTY TAXIWAY IMPROVEMENTS | Yes | 2025-02-25 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2027-08-31 | Delivery |  |  |  |  | 4000000 | 2025-02-25
AV-5800 | 7 | Greensboro Urban Area MPO | GUILFORD | GSO AIRPORT GUILFORD COUNTY TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. | Yes | 2023-10-02 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2027-12-31 | Delivery |  |  |  |  | 7000000 | 2023-10-02
AV-5802 | 7 | Greensboro Urban Area MPO | GUILFORD | GSO AIRPORT GUILFORD COUNTY CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. | Yes | 2023-10-02 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2028-03-01 | Delivery |  |  |  |  | 11000000 | 2023-10-02
AV-5803 | 7 | Greensboro Urban Area MPO | GUILFORD | GSO INTERNATIONAL AIRPORT GUILFORD COUNTY TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | Yes | 2025-02-24 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2028-01-30 | Delivery |  |  |  |  | 28000000 | 2025-02-24
AV-5804 | 3 | Jacksonville Urban Area MPO | ONSLOW | ALBERT J.ELLIS AIRPORT (OAJ).ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. | Yes | 2017-11-17 | AVIATION - STI (PRIORITIZATION) | 2027-06-30 | Construction Not Programmed | 2040-01-01 | Delivery | 300000 | 2017-11-17
AV-5805 | 3 | Jacksonville Urban Area MPO | ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) TO ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION | Yes | 2017-11-17 | AVIATION - STI (PRIORITIZATION) | 2026-06-30 | Construction Not Programmed | 2040-01-01 | Delivery | 698000 | 2017-11-17
AV-5811 | 4 | Eastern Carolina RPO | WAYNE | AV-5811 MOUNT OLIVE MUNICIPAL AIRPORT (W40) EXTEND RUNWAY 5500 FEET. | Not Yet | Not Yet | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2028-07-11 | Delivery |  |  |  |  | 1200000 | 2023-12-15
AV-5815 | 3 | Cape Fear RPO | PENDER | HENDERSON FIELD (ACZ), APRON EXPANSION. | Yes | 2024-10-25 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2026-12-31 | Delivery |  |  |  |  | 8900000.01 | 2024-10-25
AV-5817 | 10 | Rocky River RPO | STANLY | STANLY COUNTY AIRPORT (VUJ),ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | Not Yet | Not Yet | AVIATION - STI (PRIORITIZATION) | 2024-12-06 | NON - DOT LET (Aviation) | 2027-06-30 | Delivery | 3100000 | 2025-02-25 |  |  | 1500000 | 2025-02-25
AV-5818 | 5 | Kerr-Tar RPO | PERSON | PERSON COUNTY EXECUTIVE AIRPORT (TDF), EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | Not Yet | 2022-04-04 | AVIATION - STI (PRIORITIZATION) | 2026-10-16 | NON - DOT LET (Aviation) | 2028-03-01 | Delivery | 2200000 | 2026-05-28 |  |  | 20700000 | 2022-04-04
AV-5819 | 5 | Capital Area MPO | FRANKLIN | LHZ; TRIANGLE NORTH EXECUTIVE AIRPORT EXTEND RUNWAY INCLUDING RELOCATION OF UTILITIES, NAVIGATION AIDS, AND ROADWAYS. | Yes | 2024-09-24 | AVIATION - STI (PRIORITIZATION) | 2026-12-31 | NON - DOT LET (Aviation) | 2031-06-18 | Delivery | 3500000 | 2024-09-23 |  |  | 26000000 | 2024-09-24
AV-5833 | 4 | Peanut Belt RPO | HALIFAX | HALIFAX (IXA), HALIFAX NORTHAMPTON REGIONAL RIRPORT CONSTRUCT NEW ACCESS ROAD, TAXIWAY, AND SMALL APRON. | Yes | 2025-04-03 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2026-06-30 | Delivery |  |  |  |  | 2500000 | 2025-04-03
AV-5851 | 7 | Burlington-Graham MPO | ALAMANCE | BURLINGTON-ALAMANCE REDIONAL AIRPORT (BUY) CONSTRUCT 100 FTPAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. | Not Yet | 2025-02-27 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2029-01-26 | Delivery |  |  |  |  | 6600000 | 2025-02-27
AV-5885 | 3 | Wilmington Urban Area MPO | NEW HANOVER | ILM - WILMINGTON INTERNATIONAL AIRPORT REHABILITATE RUNWAY. | Yes | 2025-02-25 | AVIATION - STI (PRIORITIZATION) |  | NON - DOT LET (Aviation) | 2027-04-30 | Delivery |  |  |  |  | 7500000.01 | 2025-02-25
AV-5894 | 11 | High Country RPO | WILKES | WILKES COUNTY AIRPORT (UKF) LOCATED IN NORTH WILKESBORO. EXTEND RUNWAY TO 7,000 FEET. | Not Yet | 2022-11-08 | AVIATION - STI (PRIORITIZATION) | 2026-06-09 | NON - DOT LET (Aviation) | 2026-10-21 | Delivery | 600000 | 2022-11-08 |  |  | 12300000 | 2022-11-08
EB-5540 | 6 | Fayetteville Area MPO | CUMBERLAND | FILTER PLANT DRIVE; WASHINGTON DRIVE / BLUE STREET, FILTER PLANT DRIVE FROM NC 24/ NC 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD) AND WASHINGTON DRIVE /BLUE STREET FROM NC 210(MURCHISON ROAD) TO LITTLE CROSS CREEK. CONSTRUCT MULTI-USEPATH. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2027-09-30 | Delivery |  |  |  |  | 750000 | 2022-11-18
EB-5600 | 3 | Wilmington Urban Area MPO | NEW HANOVER | SR 1219 (SOUTH 17TH STREET) FROM HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | Yes | 2017-11-17 | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2026-11-20 | Delivery |  |  |  |  | 933000 | 2017-11-17
EB-5701 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | US 29/74 (EAST FRANKLIN BOULEVARD) FROM SR 2200 (COX ROAD) TO THE CITY LIMITS. CONSTRUCT MISSING SIDEWALK ON NORTH SIDE. | Yes | 2026-02-27 | BIKE & PED - STI (PRIORITIZATION) | 2026-10-30 | NON - DOT LET (LAP) | 2027-09-01 | Delivery | 800000 | 2021-08-05 | 75000 | 2022-07-06 | 880000 | 2026-02-27
EB-5703 | 5 | Triangle West TPO | DURHAM | DURHAM - LASALLE STREET FROM KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROODRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDEFROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | Yes | 2025-04-28 | BIKE & PED - STI (PRIORITIZATION) | 2022-03-27 | NON - DOT LET (LAP) | 2027-10-15 | Delivery | 515000 | 2021-01-19 |  |  | 1800000 | 2025-04-28
EB-5704 | 5 | Triangle West TPO | DURHAM | RAYNOR STREET FROM NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | Yes | 2025-04-28 | BIKE & PED - STI (PRIORITIZATION) | 2021-10-06 | NON - DOT LET (LAP) | 2026-10-15 | Delivery | 169000 | 2020-10-29 |  |  | 800000 | 2025-04-28
EB-5708 | 5 | Triangle West TPO | DURHAM | NC 54 FROM NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT INDURHAM CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE | Yes | 2025-04-28 | BIKE & PED - STI (PRIORITIZATION) | 2021-10-06 | NON - DOT LET (LAP) | 2026-10-15 | Delivery | 177000 | 2021-01-12 |  |  | 1100000 | 2025-04-28
EB-5711 | 4 | Rocky Mount Urban Area MPO | NASH | US 64 BUSINESS (SUNSET AVENUE) FROM SR 1836 (MAY DRIVE) TO US 301 BUSINESS NORTHBOUND (CHURCH STREET) INSTALL PEDESTRIAN SIGNALS | Yes | 2023-09-28 | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-03-15 | Delivery |  |  |  |  | 580000 | 2023-09-28
EB-5715 | 5 | Triangle West TPO | DURHAM | US 501 BYPASS (NORTH DUKE STREET) FROM MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | Yes | 2025-04-28 | BIKE & PED - STI (PRIORITIZATION) | 2021-02-05 | NON - DOT LET (LAP) | 2026-10-15 | Delivery | 296000 | 2021-01-25 |  |  | 3400000 | 2025-04-28
EB-5718 | 5 | Capital Area MPO | WAKE | SR 1012 (WESTERN BOULEVARD) CONSTRUCT BICYCLE/PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD)IN RALEIGH. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-10-30 | Division Design Raleigh Let (DDRL) | 2030-03-19 | Delivery | 6200000 | 2024-11-21 | 310000 | 2024-10-17 | 5600000 | 2024-09-05
EB-5720 | 5 | Triangle West TPO | DURHAM | BRYANT BRIDGE NORTH/GOOSE CREEK WEST TRAIL, NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | Yes | 2024-05-21 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-07 | NON - DOT LET (LAP) | 2028-12-14 | Delivery | 890000 | 2026-05-27 | 1100000 | 2024-05-24 | 7300000 | 2026-05-27
EB-5721 | 7 | Triangle West TPO | ORANGE | ORANGE COUNTY BICYCLE ROUTE 1 FROM CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH | Yes | 2024-10-14 | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2026-06-02 | Delivery |  |  |  |  | 2900000 | 2026-04-13
EB-5722 | 9 | Winston-Salem Area TPO | FORSYTH | NC 67 (SILAS CREEK PARKWAY) FROM DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | Yes | 2026-04-21 | BIKE & PED - STI (PRIORITIZATION) | 2022-01-07 | NON - DOT LET (LAP) | 2028-09-29 | Delivery | 840000 | 2026-02-04 | 280000 | 2026-02-13 | 7900000 | 2026-02-26
EB-5723 | 10 | Charlotte Regional TPO | UNION | US 74 MULTI-USE PATH AND SOUTHFORK-CROOKED CREEK GREENWAY. CONSTRUCT MULTI-USE PATH ALONG A SECTION OF US 74 IN INDIAN TRAIL AND ON SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO CROOKED CREEK PARK. | Yes | 2025-09-22 | BIKE & PED - STI (PRIORITIZATION) | 2026-08-06 | NON - DOT LET (LAP) | 2027-09-01 | Delivery | 640000 | 2026-01-30 |  |  | 4000000 | 2026-01-30
EB-5732 | 10 | Cabarrus-Rowan MPO | CABARRUS | SR 2894 (BRUTON SMITH BOULEVARD / CONCORD MILLS BOULEVARD),US 29 TO JOHN Q. HAMMONDS DRIVE IN CONCORD. CONSTRUCT SHARED USE PATH ON NORTH SIDE OF ROAD. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-12-07 | Division Design Raleigh Let (DDRL) | 2029-01-16 | Delivery | 1500000 | 2026-05-18 | 400000 | 2026-05-11 | 10400000 | 2026-02-18
EB-5734 | 8 | Central Pines RPO | CHATHAM | SR 2103 (EAST RALEIGH STREET) FROM SOUTH 6TH AVENUE TO US 64 (E 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTHSIDE. | Yes | 2026-01-29 | BIKE & PED - STI (PRIORITIZATION) | 2024-03-18 | NON - DOT LET (LAP) | 2027-01-08 | Delivery | 205000 | 2023-10-02 | 135000 | 2023-10-02 | 2300000 | 2026-01-29
EB-5742 | 8 | Central Pines RPO | LEE | SANFORD - NC 42 (WICKER STREET) FROM THE WEST LEE MIDDLE SCHOOL ENTRANCE TO KIWANIS FAMILY PARK GREENWAY | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-12-08 | Delivery |  |  |  |  | 387000 | 2021-08-04
EB-5743 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | NC 279 (SOUTH NEW HOPE ROAD) FROM SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (EAST HUDSON BOULEVARD) | Yes | 2026-02-26 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-16 | NON - DOT LET (LAP) | 2027-12-07 | Delivery |  |  |  |  | 800000 | 2026-02-26
EB-5744 | 8 | Piedmont Triad RPO | RANDOLPH | SR 1950 (WEST ACADEMY STREET); SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN, CONSTRUCT SIDEWALK ON NORTH SIDE. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-06-16 | NON - DOT LET (LAP) | 2029-01-12 | Delivery | 130000 | 2026-06-08 | 350000 | 2026-07-16 | 3000000 | 2026-07-16
EB-5745 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROMSR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD).CONSTRUCT SIDEWALK ON ONE SIDE. | Yes | 2026-02-26 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-16 | NON - DOT LET (LAP) | 2027-12-07 | Delivery | 350000 | 2026-02-20 | 600000 | 2023-07-12 | 3400000 | 2026-02-26
EB-5748 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | BEATY ROAD FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | Yes | 2024-11-27 | BIKE & PED - STI (PRIORITIZATION) | 2027-04-05 | NON - DOT LET (LAP) | 2029-03-27 | Delivery | 140000 | 2025-04-30 | 0.01 | 2025-04-30 | 800000 | 2024-11-27
EB-5753 | 13 | Foothills RPO | MCDOWELL | EB-5753 - PE - SR 1703 (BALDWIN AVENUE) FROM PERRY STREET TO US 70 (EAST COURT STREET) IN MARION. CONSTRUCT CURB AND GUTTER, SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | Yes | 2026-02-20 | BIKE & PED - STI (PRIORITIZATION) | 2027-04-30 | NON - DOT LET (LAP) | 2029-07-18 | Delivery | 160000 | 2025-04-21 | 760000 | 2026-02-20 | 4000000 | 2026-02-20
EB-5761A | 4 | Rocky Mount Urban Area MPO | NASH | US 301 BUSINESS (CHURCH STREET) AND US 301 BUSINESS (FRANKLIN STREET), US 301 BUSINESS (CHURCH STREET) FROM NC 97 (RALEIGH BOULEVARD) TO WEST HOLLY STREET AND US 301 BUSINESS (FRANKLIN STREET) FROM NC 97 (RALEIGH BOULEVARD) TO FALLS ROAD.IMPLEMENT ROAD DIET REDUCING THE NUMBER OF TRAVEL LANES FROM | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-09-24 | NON - DOT LET (LAP) | 2028-09-29 | Delivery | 269000 | 2025-09-22 | 181000 | 2025-09-22 | 8500000 | 2025-09-22
EB-5761B | 4 | Rocky Mount Urban Area MPO | NASH | US 301 BUSINESS (CHURCH STREET) HOLLY STREET TO US 64 INTERCHANGE. INSTALL PAVEMENT MARKINGS, INSTALL BIKE LANES, INSTALL PEDESTRIAN SIGNAL HEADS, PROVIDE SIDEWALK AND CURB EXTENSIONS. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2030-09-20 | NON - DOT LET (LAP) | 2031-06-30 | Delivery | 181000 | 2025-09-22 | 619000 | 2025-09-22 | 4000000 | 2025-09-22
EB-5763 | 4 | Rocky Mount Urban Area MPO | NASH | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-04-21 | NON - DOT LET (LAP) | 2029-10-26 | Delivery | 75000 | 2017-11-17 |  |  | 3000000 | 2017-11-17
EB-5768 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | SOUTH MARIETTA STREET/ HILLTOP DRIVE, HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-12-01 | NON - DOT LET (LAP) | 2027-09-30 | Delivery | 1200000 | 2023-07-25 | 800000 | 2023-06-29 | 1000000 | 2023-07-06
EB-5810 | 9 | Winston-Salem Area TPO | FORSYTH | BARBARA JANE AVENUE, FROM OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON SALEM. CONSTRUCT SIDEWALKS. | Yes | 2026-04-21 | BIKE & PED - STI (PRIORITIZATION) | 2025-10-31 | NON - DOT LET (LAP) | 2026-09-30 | Delivery | 5000 | 2025-12-10 |  |  | 410000 | 2025-12-10
EB-5812 | 9 | Winston-Salem Area TPO | FORSYTH | SALEM CREEK GREENWAY, FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON SALEM CONSTRUCT GREENWAY | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-09-29 | NON - DOT LET (LAP) | 2030-09-30 | Delivery | 130000 | 2024-10-31 | 150000 | 2024-10-31 | 10400000 | 2024-10-31
EB-5822 | 13 | French Broad River MPO | BUNCOMBE | WILMA DYKEMAN GREENWAY NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-08-27 | Division POC Let (DPOC) | 2030-03-20 | Delivery | 2100000 | 2026-02-16 | 100000 | 2026-02-16 | 2200000 | 2026-02-16
EB-5834 | 5 | Triangle West TPO | DURHAM | NC 157 / SR 1322 (GUESS RD.) FROM HILLCREST DRIVETO SR 1407(WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTHSIDES. | Not Yet | 2024-08-21 | BIKE & PED - STI (PRIORITIZATION) | 2026-12-14 | NON - DOT LET (LAP) | 2030-09-30 | Delivery | 204000 | 2024-08-21 | 420000 | 2024-08-21 | 9700000 | 2024-08-21
EB-5835 | 5 | Triangle West TPO | DURHAM | NC 55 (ALSTON AVE.) FROM SR 1171 (RIDDLE RD.) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | Not Yet | 2024-08-24 | BIKE & PED - STI (PRIORITIZATION) | 2030-09-30 | NON - DOT LET (LAP) | 2031-09-24 | Delivery | 350000 | 2024-08-24 | 250000 | 2024-08-24 | 10600000 | 2024-08-24
EB-5837 | 5 | Triangle West TPO | DURHAM | THIRD FORK CREEK TRAIL FROM SOUTHERN BOUNDARIES PARK TO THEAMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATHAND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | Yes | 2024-05-21 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-15 | NON - DOT LET (LAP) | 2027-01-29 | Delivery | 300000 | 2026-05-27 |  |  | 6700000 | 2026-05-27
EB-5838 | 5 | Capital Area MPO | WAKE | SR 1637 (CHURCH STREET)FROM SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | Yes | 2026-02-23 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-30 | NON - DOT LET (LAP) | 2027-09-30 | Delivery | 1400000 | 2026-02-23 | 510000 | 2026-04-28 | 2400000 | 2026-02-23
EB-5844 | 10 | Cabarrus-Rowan MPO | CABARRUS | LITTLE TEXAS ROAD SIDEWALK PROJECT - SR 2154 (LITTLE TEXAS ROAD) FROM SR 2180 (LANE STREET) TO NC 3 (DALE EARNHARDT BOULEVARD) IN KANNAPOLIS | Yes | 2024-11-12 | BIKE & PED - STI (PRIORITIZATION) | 2024-06-21 | NON - DOT LET (LAP) | 2027-06-30 | Delivery | 400000 | 2021-06-14 |  |  | 5500000 | 2024-11-12
EB-5845 | 11 | Northwest Piedmont RPO | SURRY | MOUNT AIRY, FROM S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. FROM ROCKFORD STREET, PENN STREET TO US 52. FROM WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-06-29 | NON - DOT LET (LAP) | 2027-06-17 | Delivery | 280000 | 2026-02-23 |  |  | 4300000 | 2026-01-22
EB-5848 | 1 | Albemarle RPO | DARE | US 158 FROM CYPRESS KNEE LANE TO JEJAC DRIVE IN KITTY HAWK CONSTRUCT SIDEWALK ON WEST SIDE. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2027-08-18 | Delivery |  |  | 10000 | 2025-05-01 | 7200000 | 2024-08-13
EB-5861 | 9 | Cabarrus-Rowan MPO | ROWAN | THIRD STREET GREENWAY WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNONLANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-09-29 | Delivery | 10000 | 2025-02-26 | 10000 | 2025-02-26 | 4287000 | 2025-02-26
EB-5863 | 8 | Central Pines RPO | LEE | US 1 BUSINESS (CHATHAGE STREET) FROM NC 42 (WICKER STREET) TO CHATHAM STREET IN SANDFORD REDUCE NUMBER OF LANES AND CONSTRUCT BYCYCLE/PEDESTRIAN ACCOMODATIONS | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-05-08 | NON - DOT LET (LAP) | 2028-11-06 | Delivery | 150000 | 2023-10-02 |  |  | 1469000 | 2023-10-02
EB-5865 | 8 | Lumber River RPO | SCOTLAND | SR 1107 (ATKINSON STREET) FROM US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG CONSTRUCT SIDEWALKS | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-10-16 | Division POC Let (DPOC) | 2028-05-23 | Delivery | 30000 | 2026-02-25 | 180000 | 2026-02-26 | 900000 | 2026-02-17
EB-5867 | 8 | Central Pines RPO | LEE | SR 1107 (FIELDS DRIVE) FROM SR 1237 (CARTHAGE STREET) TO US421 BUSINESS (HORNER BOULEVARD)IN SANFORD | Yes | 2025-12-10 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-18 | NON - DOT LET (LAP) | 2028-05-08 | Delivery | 620000 | 2025-12-10 | 600000 | 2025-12-10 | 4700000 | 2025-12-10
EB-5868 | 8 | Central Pines RPO | LEE | WOODLAND STREET FROM EVERGREEN LANE TO GLOBE STREET IN SANFORD CONSTRUCT SIDEWALK | Yes | 2026-02-23 | BIKE & PED - STI (PRIORITIZATION) | 2026-08-21 | NON - DOT LET (LAP) | 2027-12-31 | Delivery | 270000 | 2026-02-23 | 120000 | 2026-02-23 | 1200000 | 2026-02-23
EB-5869 | 8 | Sandhills MPO | MOORE | SR 1203 (JOHNSON STREET) FROM US 15/501 TO MIKE PLACE IN ABERDEEN CONSTRUCT SIDEWALK | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-05-19 | Delivery | 220000 | 2026-06-16 |  |  | 580000 | 2026-07-29
EB-5872A | 8 | Lumber River RPO | SCOTLAND | SR 1108 (WEST BOULEVARD) FROM EAST OF US 15-401 BYPASS TO SUNSET AVENUYEIN LAURINBURG. SIDEWALK IMPROVEMENTS. | Yes | 2026-02-19 | BIKE & PED - STI (PRIORITIZATION) | 2026-11-20 | Division POC Let (DPOC) | 2028-11-14 | Delivery | 20000 | 2026-02-25 |  |  | 750000 | 2026-02-19
EB-5873 | 7 | High Point Urban Area MPO | GUILFORD | SR 1278 (SOUTH COLLEGE DRIVE) FROM SR 1300 (EAST GREEN DRIVE) TO SR 1113(EAST KIVETT DRIVE)IN HIGH POINT CONSTRUCT SIDEWALK | Yes | 2024-11-22 | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2027-02-01 | Delivery |  |  |  |  | 430000 | 2024-11-22
EB-5874 | 7 | High Point Urban Area MPO | GUILFORD | NC 68 (EASTCHESTER DRIVE)FROM JOHNSON STREET TO SR 1278(NORTH COLLEGE DRIVE IN HIGH POINT CONSTRUCT SIDEWALK | Yes | 2024-11-25 | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2027-02-01 | Delivery |  |  |  |  | 850000 | 2024-11-25
EB-5878 | 7 | Greensboro Urban Area MPO | GUILFORD | WEST MEADOWVIEW ROAD FROM SR 1007 (RANDLEMAN ROAD) TO SOUTHELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | Yes | 2025-03-17 | BIKE & PED - STI (PRIORITIZATION) | 2021-12-02 | NON - DOT LET (LAP) | 2026-06-18 | Delivery | 50000 | 2025-03-17 |  |  | 950000 | 2025-03-17
EB-5879 | 7 | Burlington-Graham MPO | ALAMANCE | US 70 (NORTH CHURCH STREET) FROM SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD)IN BURLINGTON CONSTRUCT SIDEWALK | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2029-09-30 | NON - DOT LET (LAP) | 2031-10-01 | Delivery | 3300000 | 2024-05-13 | 950000 | 2024-06-07 | 930000 | 2024-05-02
EB-5880 | 7 | Triangle West TPO | ORANGE | SR 1005 (JONES FERRY ROAD) FROM DAVIE ROAD TO SR 1010 (WESTMAIN STREET) IN CARRBORO CONSTRUCT SIDEWALK ON NORTH SIDE | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-09-30 | NON - DOT LET (LAP) | 2028-09-13 | Delivery | 530000 | 2025-07-02 |  |  | 1300000 | 2025-10-06
EB-5883 | 7 | Greensboro Urban Area MPO | GUILFORD | US 220 (WENDOVER AVENUE) FROM GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. | Yes | 2025-04-22 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-25 | NON - DOT LET (LAP) | 2028-05-25 | Delivery | 296000 | 2023-10-02 |  |  | 6500000 | 2025-04-22
EB-5885 | 7 | Burlington-Graham MPO | ALAMANCE | US 70 (NORTH CHURCH STREET)FROM BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON CONSTRUCT SIDEWALK | Yes | 2025-08-22 | BIKE & PED - STI (PRIORITIZATION) | 2026-03-15 | NON - DOT LET (LAP) | 2026-10-14 | Delivery | 30000 | 2024-10-11 | 750000 | 2024-10-11 | 710000 | 2025-08-22
EB-5886A | 7 | Triangle West TPO | ORANGE | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2030-05-04 | Division POC Let (DPOC) | 2033-09-01 | Delivery | 900000 | 2025-05-23 | 1100000 | 2025-05-23 | 7000000 | 2025-05-23
EB-5886B | 7 | Triangle West TPO | ORANGE | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHERKING JR BOULEVARD) IN CHAPEL HILL. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-10-13 | Division POC Let (DPOC) | 2030-10-03 | Delivery | 510000 | 2026-02-18 | 2900000 | 2025-09-22 | 9600000 | 2026-02-13
EB-5888 | 7 | Piedmont Triad RPO | ROCKINGHAM | SR 1747 (EAST STADIUM DRIVE) FROM SR 1962 (NORTH PIERCE STREET ) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | Yes | 2026-01-29 | BIKE & PED - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2026-08-06 | Delivery |  |  |  |  | 1900000 | 2026-01-29
EB-5889 | 7 | High Point Urban Area MPO | GUILFORD | SR 1486 (WEST MAIN STREET);SR 1539(PENNY ROAD) FROM EXISTING SIDEWALK ON SR 1486(WEST MAIN STREET) TO PARK ACCESS ON SR1539(PENNY ROAD)IN JAMESTOWN CONSTRUCT SIDEWALK WITH CURB AND GUTTER | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-08-17 | NON - DOT LET (LAP) | 2028-07-27 | Delivery | 2500000 | 2024-07-25 | 1900000 | 2024-09-12 | 4100000 | 2024-07-16
EB-5890 | 7 | Triangle West TPO | ORANGE | BARNES STREET FROM KING STREET TO SR 1005 (JONES FERRY ROAD)IN CARRBRORO CONSTRUCT SIDEWALK | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-09-30 | NON - DOT LET (LAP) | 2028-09-07 | Delivery | 420000 | 2025-03-22 | 230000 | 2025-04-21 | 450000 | 2025-03-14
EB-5891 | 7 | Piedmont Triad RPO | ROCKINGHAM | US 220 BUSINESS FROM EAST JACKSON STREET IN MAYODAN TO MAYORIVER STATE PARK CONSTRUCT MULTIUSE PATH | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2030-03-30 | Division POC Let (DPOC) | 2031-10-02 | Delivery | 510000 | 2025-02-06 | 1300000 | 2025-01-25 | 6600000 | 2024-12-03
EB-5898 | 8 | Piedmont Triad RPO | RANDOLPH | NAOMI STREET SIDEWALK AND PEDESTRIAN IMPROVEMENT PROJECT - SR 1950 (WEST NAOMI STREET) FROM WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-06-16 | NON - DOT LET (LAP) | 2029-01-12 | Delivery | 1900000 | 2023-12-14 | 10000 | 2026-05-28 | 2900000 | 2024-02-12
EB-5900 | 7 | Greensboro Urban Area MPO | GUILFORD | SUMMERFIELD SOUTH GREENWAY FROM US 220 TO CENTERFIELD ROAD IN SUMMERFIELD CONSTRUCT MULTIUSE PATH | Yes | 2025-09-30 | BIKE & PED - STI (PRIORITIZATION) | 2025-08-28 | NON - DOT LET (LAP) | 2026-11-19 | Delivery | 540000 | 2025-09-30 | 180000 | 2025-09-30 | 6800000 | 2025-09-30
EB-5904 | 5 | Triangle West TPO | DURHAM | DUKE BELT LINE TRAIL - PETTIGREW STREET TO AVONDALE STREET IN DURHAM, CONSTRUCT A MULTI-USE TRAIL ON FORMER RAIL CORRIDOR | Yes | 2025-05-27 | BIKE & PED - STI (PRIORITIZATION) | 2018-09-04 | NON - DOT LET (LAP) | 2026-09-30 | Delivery | 7100000 | 2017-11-17 |  |  | 20800000 | 2025-05-27
EB-5905 | 4 | Rocky Mount Urban Area MPO | NASH | US 64 BUSINESS (THOMAS STREET) FROM SR 1005 (EAST RALEIGH BOULEVARD) TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-08-24 | Delivery |  |  |  |  | 1400000 | 2024-08-30
EB-5907 | 6 | Fayetteville Area MPO | CUMBERLAND | CROSS CREEK TRAIL, ALONG CROSS CREEK FROM NORTH OF HAY STREET TO SOUTH OF BLUE STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-09-29 | NON - DOT LET (LAP) | 2030-06-28 | Delivery | 630000 | 2023-10-17 | 220000 | 2025-03-20 | 1400000 | 2025-04-11
EB-5912 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | SIDEWALKS ALONG SR 2044 (TUCKASEEGE ROAD) IN MOUNT HOLLY | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-06-30 | NON - DOT LET (LAP) | 2031-06-26 | Delivery | 2500000 | 2024-06-27 | 430000 | 2024-03-07 | 4500000 | 2024-07-03
EB-5913 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | SR 2014 (LAKEWOOD ROAD) EAGLE ROAD; END OF EXISTING SIDEWALK ON SR 2014 (LAKEWOOD ROAD) TO SR 2565 (EAGLE ROAD); SR 2014 (LAKEWOOD ROAD) TO ROCKY BRANCH PARK TRAILHEAD IN CRAMERTON. CONSTRUCT SIDEWALK AND PEDESTRIAN ACCOMODATIONS. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2029-01-30 | Delivery |  |  | 10000 | 2026-05-27 | 354000 | 2022-08-17
EB-5916 | 13 | Foothills RPO | MCDOWELL | FONTA FLORA TRAIL, SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | Yes | 2026-03-30 | BIKE & PED - STI (PRIORITIZATION) | 2026-08-28 | NON - DOT LET (LAP) | 2027-05-28 | Delivery | 60000 | 2025-10-31 |  |  | 5900000 | 2026-03-30
EB-5920 | 9 | Winston-Salem Area TPO | FORSYTH | SR 1122 (JONESTOWN RD) FROM EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD (0.4 MI). | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-09-30 | NON - DOT LET (LAP) | 2028-09-29 | Delivery | 200000 | 2024-03-22 | 800000 | 2024-03-22 | 900000 | 2024-03-22
EB-5921 | 9 | Cabarrus-Rowan MPO | ROWAN | SR 2739 (NORTH MAIN STREET) FROM 12TH STREET TO 22ND STREETIN KANNAPOLIS. CONSTRUCT SIDEWALK. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2030-09-29 | NON - DOT LET (LAP) | 2033-09-30 | Delivery | 700000 | 2025-02-28 | 1100000 | 2025-02-28 | 2600000 | 2024-03-22
EB-5922 | 7 | High Point Urban Area MPO | GUILFORD | EASTCHESTER DRIVE SIDEWALK CONSTRUCT A FIVE FOOT CONCRETE SIDEWALK. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-01-29 | NON - DOT LET (LAP) | 2027-09-30 | Delivery | 130000 | 2024-10-09 | 460000 | 2024-10-09 | 540000 | 2024-10-09
EB-5961 | 11 | Northwest Piedmont RPO | SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) FROM NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-06-11 | NON - DOT LET (LAP) | 2027-06-17 | Delivery | 100000 | 2026-02-23 |  |  | 1300000 | 2026-01-22
EB-5963 | 14 | French Broad River MPO | HENDERSON | ASHEVILLE FROM BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY) | Yes | 2025-03-24 | BIKE & PED - STI (PRIORITIZATION) | 2027-05-24 | Division POC Let (DPOC) | 2031-07-08 | Delivery | 220000 | 2025-03-12 | 240000 | 2025-03-24 | 3600000 | 2025-03-24
EB-5964 | 14 | Southwestern RPO | MACON | US 441 BUSINESS (EAST MAIN STREET) FROM NC 28 (HIGHLANDS ROAD) TO SR 1510 (OLD CAT CREEK ROAD); SR 1510 (OLD CAT CREEK ROAD) FROMUS 441 BUSINESS TO 1ST STREET; AND 1ST STREET TO NEAR GRACE PRESBYTERIAN CHURCH IN FRANKLIN. CONSTRUCT SIDEWALK. | Yes | 2025-03-07 | BIKE & PED - STI (PRIORITIZATION) | 2026-07-06 | Division POC Let (DPOC) | 2026-11-10 | Delivery | 30000 | 2025-05-14 | 40000 | 2025-10-29 | 1600000 | 2025-03-07
EB-5965 | 13 | French Broad River MPO | BUNCOMBE | DEAVERVIEW ROAD FROM US 19 / US 23 / US 74 ALTERNATE (PATTON AVENUE) TO PISGAH VIEW ROAD IN ASHEVILLE. CONSTRUCT MULTI-USE PATH. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-08-18 | Division POC Let (DPOC) | 2031-08-06 | Delivery | 6100000 | 2025-01-05 | 1100000 | 2024-11-27 | 7000000 | 2024-12-02
EB-5969 | 10 | Charlotte Regional TPO | MECKLENBURG | NC 51 FROM TRADE STREET TO INDEPENDENCE POINTE PARKWAY ON SOUTH SIDE OF NC 51 | Yes | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-06-29 | Division POC Let (DPOC) | 2028-04-19 | Delivery | 960000 | 2024-09-20 | 0.01 | 2025-02-28 | 1300000 | 2024-09-20
EB-5970 | 10 | Charlotte Regional TPO | MECKLENBURG | IRWIN CREEK GREENWAY EASTERN EXTENSION FROM EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2032-07-01 | NON - DOT LET (LAP) | 2032-09-01 | Delivery |  |  |  |  | 6700000 | 2026-04-07
EB-5972 | 10 | Rocky River RPO | STANLY | NORTH SECOND AVENUE FROM PARK RIDGE TO SALISBURY AVENUE | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2029-09-07 | NON - DOT LET (LAP) | 2031-10-17 | Delivery | 430000 | 2024-07-01 |  |  | 1200000 | 2024-05-02
EB-5975 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | NC 279 (NEW HOPE ROAD) FROM US 29 / US 74 (FRANKLIN BOULEVARD) TO HUNT AVENUE IN GASTONIA | YES | 2026-04-10 | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2027-10-28 | Delivery |  |  |  |  | 2065000 | 2026-02-20
EB-5976 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | SR 2200 (COX ROAD) FROM I-85 TO COURT DRIVE IN GASTONIA | YES | 2026-08-06 | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-01-27 | Delivery |  |  |  |  | 2000000 | 2026-02-26
EB-5978 | 13 | Greater Hickory MPO | BURKE | COLLEGE STREET MULTIMODAL CONNECTOR TRAIL FROM NORTH GREEN STREET TO US 70 IN MORGANTON | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-09-18 | NON - DOT LET (LAP) | 2027-09-30 | Delivery | 190000 | 2025-10-01 |  |  | 7300000 | 2025-02-05
EB-5979 | 1 | Mid-East RPO | MARTIN | US 17 BUSINESS (EAST MAIN STREET) FROM SKEWARKEE TRAIL TO US 17 IN WILLIAMSTON. CONSTRUCT A MULTI-USE PATH. | Yes | 2026-08-28 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-18 | Division POC Let (DPOC) | 2027-01-29 | Delivery | 20000 | 2025-11-07 | 20000 | 2025-11-07 | 280000 | 2025-11-07
EB-5982 | 3 | Cape Fear RPO | BRUNSWICK | NC 211 (NORTH HOWE STREET) FROM EAST OWEN STREET TO DOSHER HOSPITAL. CONSTRUCT 5-FOOT WIDE SIDEWALK IN THE TOWN OF SOUTHPORT. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2027-09-30 | Delivery |  |  |  |  | 175000 | 2019-03-06
EB-5983 | 11 | High Country RPO | WATAUGA | US 221 / US 421 FROM GROVE STREET TO SR 1401 (BROOKSHIRE ROAD) IN BOONE. CONSTRUCT MULTI-USE PATH. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-02-12 | Division POC Let (DPOC) | 2028-08-17 | Delivery | 2400000 | 2024-09-26 | 360000 | 2024-11-22 | 5300000 | 2024-09-20
EB-5984 | 4 | Rocky Mount Urban Area MPO | EDGECOMBE | EAST RALEIGH BOULEVARD FROM US 64 TO ARLINGTON STREET | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2029-09-28 | NON - DOT LET (LAP) | 2031-01-28 | Delivery | 500000 | 2024-08-26 | 200000 | 2024-08-26 | 3700000 | 2024-06-21
EB-5985 | 7 | Greensboro Urban Area MPO | GUILFORD | CONE BOULEVARD FROM US 29(O'HENRY BOULEVARD) TO SAINT REGISROAD IN GREENSBORO | Yes | 2024-12-17 | BIKE & PED - STI (PRIORITIZATION) | 2026-12-18 | NON - DOT LET (LAP) | 2028-07-13 | Delivery | 5300000 | 2025-01-27 | 1100000 | 2024-08-20 | 6900000 | 2024-12-17
EB-5986 | 7 | Greensboro Urban Area MPO | GUILFORD | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE INGREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-10-16 | NON - DOT LET (LAP) | 2027-12-16 | Delivery | 1700000 | 2024-08-08 | 720000 | 2024-09-09 | 5200000 | 2024-07-15
EB-5987 | 7 | Greensboro Urban Area MPO | GUILFORD | OLD BATTLEGROUND ROAD FROM LAKE BRANDT ROAD TO BICENTENNIALGREENWAY IN GREENSBORO | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-08-16 | NON - DOT LET (LAP) | 2029-02-22 | Delivery | 870000 | 2024-08-05 | 1100000 | 2024-08-20 | 4300000 | 2024-08-01
EB-5988 | 7 | Burlington-Graham MPO | ALAMANCE | LEE AVE/WEST LEBANON AVE LEE AVENUE FROM WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2029-12-11 | NON - DOT LET (LAP) | 2031-12-04 | Delivery | 40000 | 2024-10-09 | 280000 | 2024-10-09 | 310000 | 2024-10-09
EB-5989 | 7 | High Point Urban Area MPO | GUILFORD | CEDROW DRIVE FROM WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2029-01-12 | NON - DOT LET (LAP) | 2031-03-06 | Delivery | 160000 | 2024-11-11 | 80000 | 2024-10-21 | 3800000 | 2024-10-21
EB-5995 | 7 | Greensboro Urban Area MPO | GUILFORD | LAWNDALE DRIVE FROM PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-12-01 | NON - DOT LET (LAP) | 2031-04-17 | Delivery | 2300000 | 2025-03-14 | 60000 | 2025-09-29 | 1800000 | 2025-06-25
EB-5996 | 7 | Greensboro Urban Area MPO | GUILFORD | SR 1001(NORTH CHURCH STREET) FROM HENRY STREET /ELECTRA DRIVE TO LEE'S CHAPEL ROAD IN GREENSBORO | Yes | 2024-10-31 | BIKE & PED - STI (PRIORITIZATION) | 2026-09-30 | NON - DOT LET (LAP) | 2028-07-27 | Delivery | 1100000 | 2025-03-30 | 520000 | 2024-12-13 | 4500000 | 2024-10-31
EB-5997 | 7 | Greensboro Urban Area MPO | GUILFORD | GREEN VALLEY ROAD FROM MARKET STREET TO BATTLEGROUND AVENUEIN GREENSBORO. CONSTRUCT SIDEWALKS. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-05-15 | NON - DOT LET (LAP) | 2030-12-19 | Delivery | 2500000 | 2024-11-01 | 1400000 | 2026-01-20 | 1900000 | 2025-12-17
EB-5998 | 7 | Triangle West TPO | ORANGE | US 15 / US 501 FROM WILLOW DRIVE TO SR 1741/SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2027-12-29 | NON - DOT LET (LAP) | 2030-12-05 | Delivery | 18100000 | 2025-07-15 | 4300000 | 2025-05-15 | 5800000 | 2025-04-07
EB-6001 | 8 | Sandhills MPO | MOORE | SR 2055 (NORTH POPLAR ST) SR 2055 (NORTH POPLAR STREET)FROMJOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-07-21 | Delivery | 310000 | 2026-07-04 |  |  | 400000 | 2026-06-11
EB-6002 | 8 | Central Pines RPO | LEE | SR 1002 (CHARLOTTE AVENUE) FROM CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2028-04-28 | Delivery | 1500000 | 2026-08-21 |  |  | 8300000 | 2026-06-15
EB-6006 | 8 | Central Pines RPO | CHATHAM | SR 1107 (WEST 3RD STREET), FROM NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | Yes | 2026-02-10 | BIKE & PED - STI (PRIORITIZATION) | 2027-02-19 | NON - DOT LET (LAP) | 2027-12-14 | Delivery | 220000 | 2026-02-10 | 160000 | 2026-02-10 | 2500000 | 2026-02-10
EB-6008 | 9 | Winston-Salem Area TPO | FORSYTH | US 158 / US 421 (SALEM PARKWAYT) FROM LOCKLAND AVENUE TO NC150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM | Yes | 2022-11-08 | BIKE & PED - STI (PRIORITIZATION) | 2027-09-30 | NON - DOT LET (LAP) | 2028-09-29 | Delivery | 110000 | 2022-11-08 |  |  | 2255000 | 2022-11-08
EB-6013 | 6 | Lumber River RPO | ROBESON | NC 711 (THIRD STREET) FROM SR 1555 (S JONES ST) TO CARTER MORGEN ROAD (NON-SYSTEM)/WAL-MART SHOPPING CENTER IN PEMBROKE. CONSTRUCT SIDEWALKS. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2028-01-28 | NON - DOT LET (LAP) | 2029-01-26 | Delivery | 400000 | 2025-04-28 | 140000 | 2024-12-19 | 2500000 | 2024-09-27
EB-6015A | 8 | Lumber River RPO | SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) FROM SR 1674 (LAUCHWOODDRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS. | Yes | 2026-02-06 | BIKE & PED - STI (PRIORITIZATION) | 2026-03-20 | Division POC Let (DPOC) | 2028-04-11 | Delivery | 10000 | 2026-01-26 |  |  | 1700000 | 2026-02-06
EB-6015B | 8 | Lumber River RPO | SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) FROM PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG | Yes | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2026-11-20 | Division POC Let (DPOC) | 2028-10-24 | Delivery | 30000 | 2024-11-27 | 290000 | 2024-11-27 | 1300000 | 2024-11-27
EB-6016 | 4 | Capital Area MPO | JOHNSTON | EAST CLAYTON CONNECTOR GREENWAY | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2029-01-22 | NON - DOT LET (LAP) | 2031-01-28 | Delivery | 720000 | 2025-03-07 | 1200000 | 2025-02-05 | 3800000 | 2025-02-05
EB-6017 | 4 | Capital Area MPO | JOHNSTON | MOUNTAINS TO SEA TRAIL FROM FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | Not Yet | Not Yet | BIKE & PED - STI (PRIORITIZATION) | 2029-01-31 | NON - DOT LET (LAP) | 2031-01-29 | Delivery | 1500000 | 2025-05-08 |  |  | 2100000 | 2025-06-19
F-5704 | 1 | Albemarle RPO, Down East RPO | HYDE | SILVER LAKE REPLACEMENT VESSEL. NC 12 CEDAR ISLAND-OCRACOKEFERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY. | Yes | 2025-01-13 | FERRY - STI (PRIORITIZATION) |  | CMGC PRECON AWARD | 2027-03-09 | Delivery |  |  |  |  | 25600000 | 2025-01-13
HB-0039 | 3 | Wilmington MPO | NEW HANOVER | US 17/US 76/US 421. REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-06-15 | Design Build Let (DBL) | 2027-06-15 | Delivery | 24500000 | 2025-08-07 | 3000000 | 2025-09-15 | 1002300000 | 2025-10-03
HP-0008 | 5 | Capital Area MPO | WAKE | HOLLY SPRINGS CITYWIDE SIGNAL SYSTEM. INSTALL FIBER TO CONNECT EXISTING TOWN FIBER TO INTERSECTIONS, UPGRADE EXISTING INFRASTRUCTURE INCLUDING CABINETS, CONTROLLERS, AND SOFTWARE. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2028-03-21 | Delivery |  |  |  |  | 3085000 | 2025-06-17
I-0305B | 7 | Triangle West TPO | ORANGE | I-85, SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-02-25 | Raleigh Letting (LET) | 2033-10-18 | Delivery | 67100000 | 2024-07-30 | 1200000 | 2025-01-17 | 96200000 | 2024-07-30
I-2513AC | 13 | French Broad River MPO | BUNCOMBE | I-26 / I-240 FROM NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | Yes | 2025-07-01 | HIGHWAY - STI (PRIORITIZATION) | 2023-05-26 | Raleigh Letting (LET) | 2026-11-17 | Delivery | 43400000 | 2023-08-07 | 2000000 | 2023-09-21 | 284200000 | 2025-07-01
I-3306AC | 7 | Triangle West TPO | ORANGE | I-40 AT NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTION FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | Yes | 2025-12-17 | HIGHWAY - STI (PRIORITIZATION) | 2025-09-04 | Raleigh Letting (LET) | 2028-03-21 | Delivery | 1300000 | 2025-07-09 | 680000 | 2025-06-23 | 7300000 | 2025-12-17
I-4409A | 13 | French Broad River MPO | BUNCOMBE | REPLACE BRIDGE 100041 OVER SWANNANOA RIVER ON SR 2500 (BLUERIDGE ROAD) IN BLACK MOUNTAIN. | Yes | 2025-08-14 | HIGHWAY - STI (PRIORITIZATION) | 2026-07-15 | Division Design Raleigh Let (DDRL) | 2026-12-15 | Delivery | 1000000 | 2025-08-14 | 900000 | 2025-08-14 | 7000000 | 2025-08-14
I-4409B | 13 | French Broad River MPO | BUNCOMBE | BLUE RIDGE ROAD IMPROVEMENT PROJECT. SR 2500 (BLUE RIDGE ROAD) AT I-40, AND SR 2500 FROM US 70 TO SR 2713 (SOUTH BLUE RIDGE ROAD)IN BLACK MOUNTAIN. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE AND WIDEN TO THREE LANES. | Yes | 2025-08-14 | HIGHWAY - STI (PRIORITIZATION) | 2026-08-19 | Division Design Raleigh Let (DDRL) | 2027-12-21 | Delivery | 7700000 | 2025-08-14 | 1000000 | 2025-08-14 | 23700000 | 2025-08-14
I-4729B | 14 | Foothills RPO | POLK | I-26 AT NC 108 (WEST MILLS STREET / EXIT 67) NEAR COLUMBUS.CONSTRUCT IMPROVEMENTS. | Yes | 2024-07-01 | HIGHWAY - STI (PRIORITIZATION) | 2026-04-28 | Division Design Raleigh Let (DDRL) | 2033-01-18 | Delivery | 3200000 | 2026-03-13 | 2000000 | 2024-08-28 | 33600000 | 2024-07-01
I-4759 | 13 | French Broad River MPO | BUNCOMBE | I-40 AT SR 1228 (Liberty Road).,,UPGRADE GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (Monte Vista Road) AND A FOUR LANE ROADWAY SOUTH OF I-40 TO US 19 / US 23 / NC 151 WITH PARTS ON NEW LOCATION. | Yes | 2024-03-04 | HIGHWAY - STI (PRIORITIZATION) | 2019-05-31 | Raleigh Letting (LET) | 2030-06-18 | Delivery | 15300000 | 2020-12-17 | 2500000 | 2026-02-13 | 94800000 | 2026-04-14
I-4759A | 13 | French Broad River MPO | BUNCOMBE | I-40 SR 1228 (LIBERTY ROAD), CLEARING ONLY. | Yes | 2024-05-16 | HIGHWAY - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2026-10-07 | Delivery |  |  |  |  | 500000 | 2024-05-16
I-5701 | 5 | Capital Area MPO | WAKE | I-40/US 64; FROM I-440/US 1/US 64 TO SR 1009 (LAKE WHEELER ROAD) IN RALEIGH WIDEN FROM SIX TO EIGHT LANES. (COMB W/I-5703). | Yes | 2026-02-11 | HIGHWAY - STI (PRIORITIZATION) | 2027-03-16 | Design Build Let (DBL) | 2027-03-16 | Delivery |  |  | 2300000 | 2025-10-28 | 163100000 | 2026-02-11
I-5703 | 5 | Capital Area MPO | WAKE | I-40 AND I-440/US 1/US 64 INTERSECTION RECONSTRUCT INTERCHANGE. (COMB W/I-5701). | Yes | 2026-02-11 | HIGHWAY - STI (PRIORITIZATION) | 2027-03-16 | Design Build Let (DBL) | 2027-03-16 | Delivery | 40800000 | 2025-10-21 | 2800000 | 2025-10-28 | 330900000 | 2026-02-11
I-5707 | 5 | Triangle West TPO | DURHAM | I-40 FROM NC 55 (ALSTON AVENUE) TO I-885 (DURHAM FREEWAY/TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | Yes | 2026-04-28 | HIGHWAY - STI (PRIORITIZATION) | 2024-10-21 | Raleigh Letting (LET) | 2027-06-15 | Delivery | 800000 | 2024-02-12 | 190000 | 2024-03-12 | 11700000 | 2026-04-28
I-5708 | 5 | Capital Area MPO | WAKE | I-440/US 1 AT SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2019-05-30 | Raleigh Letting (LET) | 2029-05-15 | Delivery | 15455000 | 2020-10-14 | 2000000 | 2023-09-12 | 23000000 | 2024-06-28
I-5712 | 7 | Greensboro Urban Area MPO | GUILFORD | I-40 / US 421 AT SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | Yes | 2026-06-17 | HIGHWAY - STI (PRIORITIZATION) | 2027-10-18 | Raleigh Letting (LET) | 2030-12-17 | Delivery | 14500000 | 2026-06-03 | 1300000 | 2026-05-22 | 27100000 | 2026-06-17
I-5715 | 10 | Charlotte Regional TPO | MECKLENBURG | I-77 AT NC 73. UPGRADE INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | Yes | 2026-06-15 | HIGHWAY - STI (PRIORITIZATION) | 2023-08-30 | Raleigh Letting (LET) | 2026-10-20 | Delivery | 19000000 | 2023-04-04 | 3000000 | 2023-04-04 | 83700000 | 2026-06-15
I-5718 | 10 | Charlotte Regional TPO | MECKLENBURG | I-77 FROM THE SOUTH CAROLINA STATE LINE TO I-277 / NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT THE I-277 INTERCHANGES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-06-15 | Design Build Let (DBL) | 2027-06-15 |  | 1508000 | 2025-07-10
I-5719A | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | I-85, FROM US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET).WIDEN TO EIGHT LANES.(COMB W/U-6044). | Yes | 2024-09-18 | HIGHWAY - STI (PRIORITIZATION) | 2028-11-21 | Design Build Let (DBL) | 2028-11-21 | Delivery | 47200000 | 2024-12-13 | 12300000 | 2024-09-09 | 498200000 | 2024-09-18
I-5719C | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | I-85 FROM NC 274 (BESSEMER CITY ROAD) TO NC 273 (PARK STREET / BEATTY DRIVE) IN GASTONIA. RECONSTRUCTION OF FOUR BRIDGES: PIEDMONT NORTHERN RAILROAD BRIDGE R350129, NORFOLK SOUTHERN RAILROAD BRIDGES R350132 (BESIDE OZARK AVENUE) AND R350138 (BESIDE GROVES STREET), AND BRIDGE 350142 OVER SR 2213 (GRO | Yes | 2024-09-18 | HIGHWAY - STI (PRIORITIZATION) | 2026-08-08 | CMGC CON AWARD | 2027-06-15 | Delivery | 5000000 | 2024-10-30 | 2600000 | 2024-09-09 | 232400000 | 2024-09-18
I-5962 | 12 | Charlotte Regional TPO | IREDELL | I-77 AT SR 1302(CORNELIUS ROAD) IN MOORESVILLE. CONVERT GRADE SEPARATION TO INTERCHANGE. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-09-18 | Division Design Raleigh Let (DDRL) | 2031-09-16 | Delivery | 7000000 | 2025-04-17 | 630000 | 2025-04-18 | 68100000 | 2026-04-16
I-5966 | 5 | Capital Area MPO | WAKE | I-40 FROM SR 1002 (AVIATION PARKWAY) TO SR 1652(HARRISON AVENUE)IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | Yes | 2026-04-21 | HIGHWAY - STI (PRIORITIZATION) | 2028-10-15 | Division Design Raleigh Let (DDRL) | 2031-11-18 | Delivery | 3800000 | 2026-04-24 | 450000 | 2026-04-24 | 91100000 | 2026-04-21
I-5968 | 5 | Capital Area MPO | WAKE | I-540 FROM US 70 TO SR 1829(LEESVILLE ROAD)IN RALEIGH CONSTRUCT EASTBOUND AUXILIARY LANE | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-10-15 | Division Design Raleigh Let (DDRL) | 2030-10-15 | Delivery | 4700000 | 2024-07-15 | 20000 | 2024-05-17 | 35700000 | 2024-10-02
I-5974 | 4 | Upper Coastal Plain RPO | JOHNSTON | I-95 AT US 701 / NC 96. CONSTRUCT INTERCHANGE. | Yes | 2025-05-13 | HIGHWAY - STI (PRIORITIZATION) | 2025-10-21 | Division Design Raleigh Let (DDRL) | 2028-10-17 | Delivery | 5300000 | 2025-09-03 | 1700000 | 2025-05-05 | 76000000 | 2025-05-13
I-5987AA | 6 | Lumber River RPO | ROBESON | I-95 CONSTRUCT WEIGH IN MOTION STATION. | Yes | 2025-05-06 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2028-02-15 | Delivery |  |  |  |  | 4500000 | 2025-05-06
I-5990 | 13 | Greater Hickory MPO | BURKE | I-40 AT EXIT 118 - SR 1761 (OLD NC 10). (COMB W/BR-0151). CONSTRUCT INTERCHANGE IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-09-15 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 6400000 | 2025-05-16 | 900000 | 2025-06-05 | 19800000 | 2025-07-01
I-6004 | 7 | Greensboro Urban Area MPO | GUILFORD | I-40/I-85 AT SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE NEAR SEDALIA. UPGRADE INTERCHANGE. | Yes | 2025-11-25 | HIGHWAY - STI (PRIORITIZATION) | 2026-03-01 | Raleigh Letting (LET) | 2030-10-15 | Delivery | 5700000 | 2025-11-17 | 1100000 | 2025-08-06 | 23100000 | 2025-11-25
P-5700 | 7 | Greensboro Urban Area MPO | GUILFORD | NORFOLK SOUTHERN MAINLINE, NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) |  | NON - DOT LET (Rail) | 2026-06-30 | Delivery |  |  |  |  | 1700000 | 2021-01-21
P-5701B | 7 | Triangle West TPO | ORANGE | NORFOLK SOUTHERN H LINE NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT STATION PLATFORM AND REALIGN CURVE AT MILEPOST 41.4. | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) |  | NON - DOT LET (Rail) | 2027-06-30 | Delivery |  |  |  |  | 1000000 | 2022-08-16
P-5706A | 5 | Triangle West TPO | DURHAM | NORFOLK SOUTHERN H LINE,CROSSING AT GLOVER ROAD (734735L). CONSTRUCT GRADE SEPARATION. | Yes | 2026-04-23 | RAIL - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2027-04-20 | Delivery |  |  |  |  | 30000000
P-5706B | 5 | Triangle West TPO | DURHAM | NORFOLK SOUTHERN H LINE, EAST DURHAM BETWEEN CP NELSON AND CP EAST DURHAM. CONSTRUCT EAST DURHAM RAILROAD SAFETY IMPROVEMENTS. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A GRADE SEPARATION AT ELLIS ROAD SOUTH END (734737A) AND CLOSURE OF WRE | Yes | 2026-04-23 | RAIL - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2030-01-15 | Delivery |  |  |  |  | 70000000
P-5707 | 5 | Capital Area MPO | WAKE | CSX S-LINE AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING 633905Y IN WAKE FOREST. CONSTRUCT GRADE SEPARATION. | Yes | 2025-01-17 | RAIL - STI (PRIORITIZATION) | 2018-06-05 | Raleigh Letting (LET) | 2026-10-20 | Delivery | 1890000 | 2017-11-17 |  |  | 39800000 | 2025-01-17
P-5709 | 7 | Greensboro Urban Area MPO | GUILFORD | GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A), AND CLOSE O'FERRELL STREET CROSSING (722961B) AT NCRR/NSR-NCLINE IN GREENSBORO. | Yes | 2025-06-16 | RAIL - STI (PRIORITIZATION) | 2022-06-15 | Raleigh Letting (LET) | 2027-05-18 | Delivery | 3483885 | 2021-09-02 | 1566300 | 2021-06-16 | 27300000 | 2025-06-16
P-5713 | 7 | Greensboro Urban Area MPO | GUILFORD | NORTH CAROLINA RAILROAD (NCRR)/NORFOLKSOUTHERNRAILROAD, SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSINGTO GRADE SEPARATION. | Yes | 2025-04-07 | RAIL - STI (PRIORITIZATION) | 2026-09-25 | Raleigh Letting (LET) | 2029-06-19 | Delivery | 9100000 | 2025-03-10 | 1600000 | 2025-03-31 | 20200000 | 2025-04-07
P-5714 | 7 | Greensboro Urban Area MPO | GUILFORD | NCRR NORFOLK SOUTHERN, POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) |  | NON - DOT LET (Rail) | 2027-06-20 | Delivery |  |  | 0.01 |  | 6600000 | 2025-04-30
P-5717 | 5 | Triangle West TPO | DURHAM | NORFOLK SOUTHERN H LINE CROSSING NO. 734 742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | Yes | 2025-09-03 | RAIL - STI (PRIORITIZATION) | 2021-09-22 | Raleigh Letting (LET) | 2027-02-16 | Delivery | 4378000 | 2020-12-16 | 1878000 | 2021-11-02 | 41500000 | 2025-09-03
P-5718 | 5 | Capital Area MPO | WAKE | CSX CROSSING 643351A AT SR 1415 (NORTHEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | Yes | Not Yet | RAIL - STI (PRIORITIZATION) | 2027-08-01 | Raleigh Letting (LET) | 2030-08-20 | Delivery | 37300000 | 2023-09-25 | 4500000 | 2024-10-08 | 42000000 | 2024-10-08
P-5719C | 7 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Greensboro Urban Area MPO, Triangle West TPO | ALAMANCE | NCRR PURCHASE AND REFURBISHMENT OF 8 PASSENGER RAIL CARS. | Yes | 2023-10-03 | RAIL - STI (PRIORITIZATION) |  | NON - DOT LET (Rail) | 2027-12-31 | Delivery |  |  |  |  | 212528000 | 2023-10-03
P-5721 | 7 | High Point Urban Area MPO | GUILFORD | NORFOLK SOUTHERN RAILROAD, JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) |  | NON - DOT LET (Rail) | 2028-06-23 | Delivery |  |  |  |  | 4070000 | 2023-10-02
P-5722 | 9 | High Point Urban Area MPO | DAVIDSON | NORFOLK SOUTHERN RAILROAD, KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) |  | NON - DOT LET (Rail) | 2028-12-15 | Delivery |  |  |  |  | 2038000 | 2023-01-24
P-5725 | 10 | Cabarrus-Rowan MPO | CABARRUS | KANNAPOLIS TRAIN STATION IMPROVEMENTS. CONSTRUCT VARIOUS TRACK AND SAFETY IMPROVEMENTS. | Yes | 2024-05-08 | RAIL - STI (PRIORITIZATION) | 2019-03-21 | Raleigh Letting (LET) | 2028-03-21 | Delivery | 1250000 | 2019-03-12 |  |  | 13900000 | 2026-03-12
P-5726 | 9 | Cabarrus-Rowan MPO | ROWAN | RAILROAD NORFOLK SOUTHERN NORFOLK SOUTHERN MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS,SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | Yes | 2023-12-13 | RAIL - STI (PRIORITIZATION) | 2019-02-28 | Raleigh Letting (LET) | 2029-01-16 | Delivery | 1638000 | 2019-03-28 |  |  | 13600000 | 2023-12-13
P-5726A | 9 | Cabarrus-Rowan MPO | ROWAN | NORFOLK SOUTHERN SALISBURY TRAIN STATION SECOND PLATFORM AND PEDESTRIAN UNDERPASS. | Yes | 2023-02-01 | RAIL - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2028-01-26 | Delivery |  |  |  |  | 2500000 | 2023-02-01
P-5726B | 9 | Cabarrus-Rowan MPO | ROWAN | SNORFOLK SOUTHERN SALISBURY NORFOLK SOUTHERN CROSSOVER RELOCATION. | Yes | 2023-10-03 | RAIL - STI (PRIORITIZATION) |  | NON - DOT LET (Rail) | 2027-12-29 | Delivery |  |  |  |  | 4000000 | 2023-10-03
P-5730 | 10 | Charlotte Regional TPO | MECKLENBURG | CLANTON ROAD EXT. NORFOLK SOUTHERN RAILROAD EXTEND CLANTON ROAD TO WILKINSON BLVE (US 29 & US 74) WITH GRADE SEPARATIONOF THE NORFOLK SOUTHERN RAILROAD; CLOSE THE DONALD ROSS ROAD CROSSING AT THE NORFOLK SOUTHER RAILROAD (CROSSING 716178E). | Yes | 2025-04-01 | RAIL - STI (PRIORITIZATION) | 2029-08-15 | Raleigh Letting (LET) | 2034-02-21 | Delivery | 13600000 | 2023-10-03 | 1200000 |  | 62800000 | 2025-04-01
P-5731 | 9 | High Point Urban Area MPO | DAVIDSON | NORFOLK SOUTHERN, CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREETAND CLOSE CROSSING 722306Y. | Yes | 2025-09-17 | RAIL - STI (PRIORITIZATION) | 2025-03-06 | Raleigh Letting (LET) | 2028-04-18 | Delivery | 8900000 | 2025-02-13 | 10000 | 2025-04-03 | 72000000 | 2025-09-17
P-5733 | 9 | Cabarrus-Rowan MPO | ROWAN | NORFOLK SOUTHERN; CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | Yes | 2025-10-01 | RAIL - STI (PRIORITIZATION) | 2025-10-01 | NON - DOT LET (Rail) | 2027-06-25 | Delivery | 5300000 | 2024-11-14 |  |  | 9143000 | 2023-10-03
P-5734 | 5 | Capital Area MPO | WAKE | NS MAIN LINE WAKE COUNTY AT SR 1655 (TRINITY ROAD) IN CARY.CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | Yes | 2024-03-07 | RAIL - STI (PRIORITIZATION) | 2027-07-30 | Raleigh Letting (LET) | 2030-08-20 | Delivery | 23400000 | 2023-10-27 | 960000 | 2025-02-12 | 29600000 | 2024-03-07
P-5736 | 5 | Capital Area MPO | WAKE | NCR/NS H LINE/CSX S LINE WAKE COUNTY AT BERYL ROAD CROSSINGIN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | Not Yet | 2025-04-02 | RAIL - STI (PRIORITIZATION) | 2029-07-30 | Raleigh Letting (LET) | 2032-07-20 | Delivery | 3700000 | 2025-04-21 | 1700000 |  | 5400000 | 2025-04-02
P-5737 | 5 | Capital Area MPO | WAKE | CSX S LINE AT SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | Yes | 2025-12-11 | RAIL - STI (PRIORITIZATION) | 2021-08-09 | Raleigh Letting (LET) | 2027-07-20 | Delivery | 6111000 | 2021-05-03 | 1228000 | 2021-10-14 | 29800000 | 2026-06-05
P-5740B | 3 | Wilmington Urban Area MPO | NEW HANOVER | CSX SE LINE IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. | Yes | 2025-04-29 | RAIL - STI (PRIORITIZATION) | 2023-04-28 | Division POC Let (DPOC) | 2027-02-04 | Delivery | 600000 | 2023-02-01 | 270000 |  | 4200000 | 2025-04-29
P-5744 | 10 | Charlotte Regional TPO | UNION | CSX SF LINE UNION COUNTY AT 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. | Yes | 2024-04-19 | RAIL - STI (PRIORITIZATION) | 2027-03-26 | Raleigh Letting (LET) | 2029-06-19 | Delivery | 14850000 | 2025-05-02 | 6226000 | 2025-03-25 | 23100000 | 2024-04-19
P-5747 | 7 | Greensboro Urban Area MPO | GUILFORD | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN (NS) H-LINE AT SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) | 2027-05-14 | Raleigh Letting (LET) | 2029-09-18 | Delivery | 8800000 | 2025-03-15 | 720000 |  | 24900000 | 2024-04-29
P-5748B | 10 | Charlotte Regional TPO | UNION | CSX SG RAILWAY LINE AT SR 1300 (HELMS ROAD) CONSTRUCT GRADESEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TROY PATH). | Yes | 2024-05-17 | RAIL - STI (PRIORITIZATION) | 2022-10-07 | Raleigh Letting (LET) | 2029-06-19 | Delivery | 5000000 | 2022-08-18 | 378000 | 2022-08-18 | 25000000 | 2026-05-04
P-5750B | 10 | Rocky River RPO | ANSON | CSX SF LINE SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. | Yes | 2025-03-12 | RAIL - STI (PRIORITIZATION) | 2029-02-03 | Raleigh Letting (LET) | 2032-10-19 | Delivery | 2000000 | 2025-02-25 | 480000 | 2025-03-25 | 26400000 | 2025-03-12
P-5753AH | 5 | Capital Area MPO | WAKE | CSX S-LINE AT SR 2013 (GRESHAM LAKE ROAD)/SR 2044 (LIGON MILL ROAD) AND SR 2046 (SEAWELL DRIVE) AT FRIENDSHIP CHAPEL ROAD IN WAKE FOREST. CONSTRUCT GRADE SEPARATIONS AND ROADWAY IMPROVEMENTS. | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) | 2027-06-30 | Raleigh Letting (LET) | 2030-06-18 | Delivery
P-5753CF | 5 | Triangle West TPO | VANCE | CSX S-LINE. CONSTRUCT ALEXANDER AVENUE GRADE SEPARATION ANDROADWAY IMPROVEMENTS ON SR 1267 (DABNEY DRIVE). | Not Yet | Not Yet | RAIL - STI (PRIORITIZATION) | 2030-06-21 | Raleigh Letting (LET) | 2033-06-21 | Delivery | 9000000 |  | 800000 |  | 20000000
R-0204EA | 13 | Foothills RPO | MCDOWELL | US 221 AT THE I-40 INTERCHANGE NEAR MARION. CONSTRUCT INTERCHANGE IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-11-19 | Raleigh Letting (LET) | 2029-09-18 | Delivery | 20100000 | 2025-09-18 | 1600000 | 2025-09-18 | 42700000 | 2025-09-18
R-0204EB | 13 | Foothills RPO | MCDOWELL | US 221 FROM NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD). WIDEN TO MULTI-LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-09-20 | Raleigh Letting (LET) | 2033-08-16 | Delivery | 4000000 | 2025-09-18 | 2200000 | 2025-09-18 | 33400000 | 2025-09-18
R-2233BA | 13 | Foothills RPO | RUTHERFORD | US 221 FROM NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS. | Yes | 2024-05-30 | HIGHWAY - STI (PRIORITIZATION) | 2024-10-15 | Raleigh Letting (LET) | 2028-04-18 | Delivery | 18100000 | 2024-04-15 | 3000000 | 2024-05-30 | 145200000 | 2024-05-30
R-2247D | 9 | Winston-Salem Area TPO | FORSYTH | WINSTON-SALEM NORTHERN BELTWAY FROM SR 1348 (ROBINHOOD ROAD- MEADOWLARK DRIVE)TO NC 67. | Yes | 2025-05-27 | HIGHWAY - STI (PRIORITIZATION) | 2028-05-19 | Raleigh Letting (LET) | 2032-06-15 | Delivery | 2100000 | 2025-04-28 | 6500000 | 2024-06-11 | 159100000 | 2024-06-24
R-2247EA | 9 | Winston-Salem Area TPO | FORSYTH | WINSTON-SALEM NORTHERN BELTWAY FROM NC 67 TO SOUTH OF US 52. | Yes | 2026-07-15 | HIGHWAY - STI (PRIORITIZATION) | 2028-04-17 | Raleigh Letting (LET) | 2029-10-16 | Delivery | 18600000.01 | 2025-04-28 | 3600000 | 2026-06-29 | 232900000 | 2026-04-16
R-2513A | 2 | Down East RPO | CRAVEN | US 17 FROM NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | Yes | 2025-02-24 | HIGHWAY - STI (PRIORITIZATION) | 2029-07-02 | Division Design Raleigh Let (DDRL) | 2033-06-21 | Delivery | 4100000 | 2024-12-04 | 2400000 | 2024-12-09 | 26500000 | 2025-02-24
R-2527 | 8 | Piedmont Triad RPO | MONTGOMERY | NC 24-27 FROM NC 73 TO THE TROY BYPASS. | Yes | 2026-07-15 | HIGHWAY - STI (PRIORITIZATION) | 2019-02-27 | Raleigh Letting (LET) | 2027-09-21 | Delivery | 626000 | 2023-01-24 | 1600000 | 2021-06-29 | 157200000 | 2026-07-15
R-2555B | 10 | Charlotte Regional TPO | MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) FROM NC 73 (SAM FURR ROAD) TOEAST OF SR 2151 (JETTON ROAD) IN CORNELIUS. WIDEN TO FOUR-LANES DIVIDED. | Yes | 2026-05-19 | HIGHWAY - STI (PRIORITIZATION) | 2018-03-18 | Division Design Raleigh Let (DDRL) | 2027-12-21 | Delivery | 21500000 | 2017-11-17 | 4000000 | 2024-08-27 | 40900000 | 2026-05-19
R-2566B | 11 | High Country RPO | WATAUGA | NC 105 FROM SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. WIDEN TO MULTI-LANES. | Yes | 2024-12-11 | HIGHWAY - STI (PRIORITIZATION) | 2022-11-15 | Raleigh Letting (LET) | 2030-11-19 | Delivery | 13200000 | 2022-12-16 | 13700000 | 2023-02-02 | 117200000 | 2024-12-11
R-2576 | 1 | Albemarle RPO | CURRITUCK | MID-CURRITUCK BRIDGE, FROM COINJOCK TO COROLLA NCTA PROJECT | Yes | 2025-09-29 | HIGHWAY - STI (PRIORITIZATION) | 2028-06-20 | Design Build Let (DBL) | 2028-06-20 | Delivery | 42500000 | 2025-07-29 | 13000000 | 2025-09-08 | 1062200000 | 2025-09-29
R-2588B | 14 | French Broad River MPO | HENDERSON | NC 191 FROM SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | Yes | 2024-07-09 | HIGHWAY - STI (PRIORITIZATION) | 2021-04-12 | Division Design Raleigh Let (DDRL) | 2028-08-15 | Delivery | 4500000 | 2022-12-01 | 7750000 | 2022-12-01 | 153900000 | 2026-08-12
R-2632AB | 10 | Charlotte Regional TPO | MECKLENBURG | NC 73 (SAM FURR ROAD) FROM NC 115 (OLD STATESVILLE ROAD) TOSR 2693 (DAVIDSON-CONCORD ROAD) IN HUNTERSVILLE. WIDEN TO FOUR LANES. | Yes | 2025-04-22 | HIGHWAY - STI (PRIORITIZATION) | 2023-06-16 | Raleigh Letting (LET) | 2028-10-17 | Delivery | 8300000 | 2023-04-04 | 5100000 | 2023-04-04 | 68100000 | 2025-04-22
R-2822BA | 14 | Southwestern RPO | GRAHAM | NC 143 BUSINESS FROM WEST BUFFALO CREEK TO NC 143 BUSINESS.UPGRADE CORRIDOR. | Yes | 2025-06-26 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2031-08-19 | Delivery |  |  |  |  | 40000000 | 2025-06-26
R-2822BB | 14 | Southwestern RPO | GRAHAM | NC 143 FROM WEST BUFFALO CREEK OVER NC 143 BUSINESS. REPLACE BRIDGE 370013. | Yes | 2025-06-26 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2029-08-21 | Delivery |  |  |  |  | 33500000 | 2025-06-26
R-3403B | 2 | Down East RPO, New Bern Area MPO | CRAVEN | US 17 FROM SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | Yes | 2024-11-06 | HIGHWAY - STI (PRIORITIZATION) | 2029-07-02 | Division Design Raleigh Let (DDRL) | 2033-06-21 | Delivery | 8900000 | 2024-12-13 | 4100000 | 2024-11-06 | 129100000 | 2024-11-06
R-3410 | 4 | Capital Area MPO | JOHNSTON | NC 42 FROM NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-01-15 | Division Design Raleigh Let (DDRL) | 2031-01-21 | Delivery | 55900000 | 2024-06-27 | 10500000 | 2024-03-05 | 156900000 | 2024-03-05
R-3430CA | 11 | Greater Hickory MPO | CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD), CAJAH MOUNTAIN ROAD TO SR 1933 (SOUTH-WEST BOULEVARD) IN CAJAH'S MOUNTAIN. MODERNIZE ROADWAY TO INCLUDE BICYCLE PEDESTRIAN ACCOMMODATIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-10-20 | Raleigh Letting (LET) | 2032-10-19 | Delivery | 18942000 | 2025-06-26 | 2265000 | 2025-06-26 | 52300000 | 2025-06-26
R-3430CB | 11 | Greater Hickory MPO | CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD) CATAWBA RIVER TO CAJAH MOUNTAIN ROAD IN CAJAH'S MOUNTAIN. MODERNIZE ROADWAY TO INCLUDE BICYCLE PEDESTRIAN ACCOMMODATIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-19 | Raleigh Letting (LET) | 2033-10-18 | Delivery | 17857000 | 2025-06-26 | 2135000 | 2025-06-26 | 49300000 | 2025-06-26
R-3603A | 12 | Greater Hickory MPO | CATAWBA | NC 127 FROM SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. CONSTRUCT RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD). | Yes | 2024-11-20 | HIGHWAY - STI (PRIORITIZATION) | 2030-03-21 | Raleigh Letting (LET) | 2034-03-21 | Delivery | 19600000 | 2025-01-29 | 7300000 | 2024-11-15 | 115700000 | 2024-11-20
R-3608 | 5 | Kerr-Tar RPO | FRANKLIN | US 401/ NC 39 FROM NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-05-17 | Division Design Raleigh Let (DDRL) | 2033-06-21 | Delivery | 4900000 | 2025-05-21 | 2200000 | 2025-05-09 | 38900000 | 2025-05-12
R-5020A | 6 | Cape Fear RPO | COLUMBUS | US 701 BYPASS FROM SOUTH OF SR 1166 (PLEASANT PLAINS ROAD) TO SR 1437 (VIRGIL AVENUE) IN WHITEVILLE. WIDEN TO MULTI-LANES. | Yes | 2025-06-26 | HIGHWAY - STI (PRIORITIZATION) | 2018-02-28 | Division Design Raleigh Let (DDRL) | 2030-07-16 | Delivery | 5250000 | 2017-11-17 |  |  | 63600000 | 2025-06-26
R-5020AA | 6 | Cape Fear RPO | COLUMBUS | US 701 BUSINESS SOUTH OF SR 1920 (MILL POND ROAD). REPLACE CULVERT. | Yes | 2025-09-24 | HIGHWAY - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2027-04-07 | Delivery |  |  |  |  | 2000000 | 2025-09-24
R-5100A | 12 | Charlotte Regional TPO | IREDELL | SR 1109 (WILLIAMSON ROAD) FROM I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD) IN MOORESVILLE. WIDEN TO FOUR LANES. | Yes | 2025-08-14 | HIGHWAY - STI (PRIORITIZATION) | 2021-04-19 | Raleigh Letting (LET) | 2027-09-21 | Delivery | 7800000 | 2022-01-03 | 5300000 | 2022-01-03 | 74300000 | 2025-08-14
R-5100B | 12 | Charlotte Regional TPO | IREDELL | SR 1109 (WILLIAMSON ROAD) FROM SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | Yes | 2025-08-13 | HIGHWAY - STI (PRIORITIZATION) | 2019-06-06 | Division Design Raleigh Let (DDRL) | 2027-02-16 | Delivery | 8900000 | 2019-06-06 | 1300000 | 2024-05-09 | 13600000 | 2026-07-29
R-5701 | 3 | Cape Fear RPO | PENDER | NC 53 AT US 117 BUSINESS (WALKER STREET/WILMINGTON STREET) IN BURGAW. CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | 2024-10-03 | HIGHWAY - STI (PRIORITIZATION) | 2025-06-09 | Division POC Let (DPOC) | 2027-06-03 | Delivery | 210000 | 2024-06-27 | 180000 | 2024-09-03 | 2800000 | 2024-10-03
R-5706A | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | MECKLENBURG | NC 73 (DAVIDSON HIGHWAY) FROM EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD) IN DAVIDSON. WIDEN TO MULTI-LANES. | Yes | 2024-04-08 | HIGHWAY - STI (PRIORITIZATION) | 2026-08-31 | Raleigh Letting (LET) | 2030-10-15 | Delivery | 12000000 | 2024-01-01 | 6200000 | 2024-04-05 | 53100000 | 2024-04-08
R-5709B | 8 | Lumber River RPO, Central Pines RPO, Fayetteville Area MPO | HOKE | NC 211, FROM US 15 / US 501 IN ABERDEEN TO 0.40 MILES NORTH OF SR 1225 (ASHEMONT ROAD). WIDEN TO MULTI-LANES. | Yes | 2026-06-29 | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2029-06-19 | Delivery |  |  |  |  | 121500000 | 2026-06-29
R-5711 | 12 | Charlotte Regional TPO | IREDELL | US 21 - AT INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | Yes | 2025-04-30 | HIGHWAY - STI (PRIORITIZATION) | 2019-01-14 | Division Design Raleigh Let (DDRL) | 2026-12-15 | Delivery | 500000 | 2017-11-17 |  |  | 5200000 | 2025-04-30
R-5714 | 11 | Northwest Piedmont RPO | SURRY | US 601 FROM US 52 TO SR 1365 (FORREST DRIVE) UPGRADE ROADWAY | Yes | 2024-09-11 | HIGHWAY - STI (PRIORITIZATION) | 2019-02-28 | Division Design Raleigh Let (DDRL) | 2030-10-15 | Delivery | 1615000 | 2021-06-14 | 1200000 | 2025-01-17 | 29800000 | 2024-09-11
R-5717 | 1 | Albemarle RPO | CAMDEN | SR 1224/SR 1223 (OLD SWAMP ROAD) FROM NC 343 TO THE CAMDEN-CURRITUCK COUNTY LINE, AND SR 1218 / SR 1227 (SOUTH MILLS ROAD) FROM THE COUNTY LINE TO US 168 IN MOYOCK. (COMB W/R-5717B). WIDEN AND INTERSECTION IMPROVEMENTS. | Yes | 2025-08-01 | HIGHWAY - STI (PRIORITIZATION) | 2018-08-07 | Division Design Raleigh Let (DDRL) | 2027-02-16 | Delivery | 2957010 | 2021-06-04 | 5423000 | 2023-02-23 | 38100000 | 2025-08-01
R-5717B | 1 | Albemarle RPO | CAMDEN | REPLACE BRIDGE 140013 OVER JOYCE CREEK. (COMB W/R-5717). | Yes | 2024-08-05 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2027-02-16 | Delivery |  |  |  |  | 2200000 | 2024-08-05
R-5718 | 4 | Upper Coastal Plain RPO | JOHNSTON | SR 1003 (BUFFALO ROAD) FROM US 70 TO SR 1934 (OLD BEULAH ROAD) IN SELMA. WIDEN TO THREE LANES | Yes | 2026-02-03 | HIGHWAY - STI (PRIORITIZATION) | 2022-04-29 | Division Design Raleigh Let (DDRL) | 2027-02-16 | Delivery | 6936988 | 2021-06-25 | 1190000 | 2021-06-25 | 25700000 | 2026-02-03
R-5721B | 10 | Charlotte Regional TPO | MECKLENBURG | NC 73 FROM VANCE ROAD EXTENSION / SR 2128/SR 2196 (BEATTIESFORD ROAD) TO SR 5544(WEST CATAWBA AVENUE). WIDEN TO MULTILANES. | Yes | 2025-06-09 | HIGHWAY - STI (PRIORITIZATION) | 2023-07-31 | Raleigh Letting (LET) | 2028-10-17 | Delivery | 15436000 | 2023-10-03 | 3000000 | 2023-10-03 | 76400000 | 2025-06-09
R-5724B | 8 | Central Pines RPO | CHATHAM | US 15/US 501 FROM NORTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | Yes | 2026-04-08 | HIGHWAY - STI (PRIORITIZATION) | 2022-08-19 | Division Design Raleigh Let (DDRL) | 2027-04-20 | Delivery | 3900000 | 2023-01-24 | 1300000 | 2023-01-24 | 24200000 | 2026-04-08
R-5736 | 9 | Northwest Piedmont RPO | DAVIE | US 601 FROM SR 1301 (MADISON ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | Yes | 2024-08-07 | HIGHWAY - STI (PRIORITIZATION) | 2030-04-17 | Division Design Raleigh Let (DDRL) | 2033-04-19 | Delivery | 6400000 | 2024-09-26 | 800000 | 2024-07-31 | 32100000 | 2024-08-07
R-5757A | 1 | Peanut Belt RPO | NORTHAMPTON | NC 305 FROM HERTFORD COUNTY LINE TO NORTH OF SR 1503 (LASKER ROAD). UPGRADE ROADWAY. | Yes | 2024-01-25 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2028-08-15 | Delivery |  |  |  |  | 25600000 | 2024-01-25
R-5757B | 1 | Peanut Belt RPO | NORTHAMPTON | NC 305 FROM NORTH OF SR 1503 (LASKER ROAD) TO SEABOARD TOWNLIMITS. UPGRADE ROADWAY. | Yes | 2024-01-25 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2028-08-15 | Delivery |  |  |  |  | 29100000 | 2024-01-25
R-5759 | 11 | High Country RPO | WILKES | NC 115 / US 421 BUSINESS (STATESVILLE ROAD) FROM US 421 TO NC 18 (2ND STREET) IN NORTH WILKESBORO. WIDEN TO TWO LANES WITH MEDIAN AND PEDESTRIAN ACCOMMODATIONS. | Yes | 2025-10-09 | HIGHWAY - STI (PRIORITIZATION) | 2022-02-22 | Division Design Raleigh Let (DDRL) | 2026-11-17 | Delivery | 12600000 | 2021-08-17 | 900000 | 2021-08-05 | 69100000 | 2025-10-09
R-5763 | 14 | Land-of-Sky RPO | TRANSYLVANIA | SR 1540 (WILSON ROAD)FROM SR 1504 (OLD US 64) TO US 276.UPGRADE ROADWAY | Yes | 2024-06-14 | HIGHWAY - STI (PRIORITIZATION) | 2022-03-21 | Division Design Raleigh Let (DDRL) | 2028-09-19 | Delivery | 16400000 | 2023-02-01 | 1200000 | 2023-02-01 | 62000000 | 2026-05-27
R-5766 | 7 | Piedmont Triad RPO | ROCKINGHAM | NC 65/NC 87 FROM WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158/US 29 BUSINESS(FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. | Yes | 2025-01-16 | HIGHWAY - STI (PRIORITIZATION) | 2029-12-06 | Division Design Raleigh Let (DDRL) | 2033-10-18 | Delivery | 18600000 | 2025-01-16 | 4800000 | 2025-01-16 | 36800000 | 2025-01-16
R-5772 | 11 | High Country RPO | WILKES | SR 1001 (OAKWOODS ROAD) FROM US 421 TO FOREST HILL DRIVE. UPGRADE EXISTING ROADWAY. | Yes | 2025-08-18 | HIGHWAY - STI (PRIORITIZATION) | 2025-10-10 | Division Design Raleigh Let (DDRL) | 2028-07-18 | Delivery | 4100000 | 2025-08-15 | 1700000 | 2025-08-22 | 16800000 | 2025-08-18
R-5795 | 4 | Upper Coastal Plain RPO | JOHNSTON | US 70 (FUTURE I-42) FROM US 301 TO I-95 IN SELMA. CONSTRUCTACCESS MANAGEMENT IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-15 | Division Design Raleigh Let (DDRL) | 2032-09-21 | Delivery | 7700000 | 2026-03-16 | 3600000 | 2026-03-16 | 10800000 | 2026-04-01
R-5796 | 1 | Peanut Belt RPO | HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) FROM PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | Yes | 2025-03-14 | HIGHWAY - STI (PRIORITIZATION) | 2023-07-19 | Division Design Raleigh Let (DDRL) | 2027-06-15 | Delivery | 2574000 | 2021-06-28 | 2000000 | 2024-01-09 | 20300000 | 2025-03-14
R-5798 | 10 | Rocky River RPO | ANSON | US 74 FROM GRAHAM STREET TO SR 1749 (ALLEN POND ROAD) IN WADESBORO. CONSTRUCT MEDIAN. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-07-03 | Division Design Raleigh Let (DDRL) | 2032-09-21 | Delivery | 18500000 | 2025-05-01 | 5500000 | 2025-05-07 | 65100000 | 2024-04-22
R-5800 | 14 | Land-of-Sky RPO | TRANSYLVANIA | US 64 / US 276 (ASHEVILLE HIGHWAY) FROM FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET) IN BREVARD. CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | Yes | 2024-08-26 | HIGHWAY - STI (PRIORITIZATION) | 2023-03-01 | Division Design Raleigh Let (DDRL) | 2029-10-16 | Delivery | 14700000 | 2023-03-15 | 4400000 | 2024-08-28 | 34700000 | 2026-08-17
R-5807 | 1 | Albemarle RPO | CAMDEN | NC 343 FROM US 158 TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH, MODERNIZE ROADWAY | Yes | 2024-05-20 | HIGHWAY - STI (PRIORITIZATION) | 2024-12-06 | Division Design Raleigh Let (DDRL) | 2027-12-21 | Delivery | 2000000 | 2024-05-17 | 9600000 | 2024-07-16 | 27600000 | 2024-05-20
R-5809B | 1 | Peanut Belt RPO | BERTIE | NC 45 FROM US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. MODERNIZE ROADWAY. | Yes | 2024-08-14 | HIGHWAY - STI (PRIORITIZATION) | 2025-01-09 | Division Design Raleigh Let (DDRL) | 2028-08-15 | Delivery | 6100000 | 2025-01-17 | 13000000 | 2024-08-14 | 33000000 | 2024-08-14
R-5810 | 1 | Mid-East RPO | MARTIN | US 17 FROM SR 1119 (RALPH TAYLOR ROAD) TO SR 1521 (MILL INNROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | Yes | 2025-09-05 | HIGHWAY - STI (PRIORITIZATION) | 2024-08-13 | Division Design Raleigh Let (DDRL) | 2026-10-20 | Delivery | 250000 | 2024-06-03 | 80000 | 2024-07-09 | 13100000 | 2025-09-05
R-5822 | 7 | Piedmont Triad RPO | CASWELL | NC 86 FROM US 158 TO SR 1500 (OLD NC HIGHWAY 86) 1.2 MILES SOUTH OF THE VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCTTURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | Yes | 2024-09-25 | HIGHWAY - STI (PRIORITIZATION) | 2027-01-21 | Division Design Raleigh Let (DDRL) | 2029-02-20 | Delivery | 440000 | 2024-09-04 | 1300000 | 2024-09-11 | 26600000 | 2024-09-25
R-5823 | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | GUILFORD | NC 65 / NC 68 FROM US 158 IN STOKESDALE IN GUILFORD COUNTY TO I-73 / US 220 IN ROCKINGHAM COUNTY. MULTIPLE INTERSECTIONIMPROVEMENTS ALONG CORRIDOR. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-09-15 | Division Design Raleigh Let (DDRL) | 2033-11-15 | Delivery | 10500000 | 2022-12-01 | 3300000 | 2025-05-13 | 29200000 | 2024-10-14
R-5824 | 8 | Fayetteville Area MPO, Central Pines RPO | MOORE | NC 690 (LOBELIA ROAD)FROM US 1 IN VASS TO CUMBERLAND COUNTYLINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | Yes | 2026-02-16 | HIGHWAY - STI (PRIORITIZATION) | 2024-10-07 | Division Design Raleigh Let (DDRL) | 2028-05-16 | Delivery | 2200000 | 2026-03-20 | 1500000 | 2026-02-06 | 14300000 | 2026-02-16
R-5826B | 8 | Piedmont Triad RPO | MONTGOMERY | NC 109 FROM SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). UPGRADE ROADWAY. | Yes | 2025-05-09 | HIGHWAY - STI (PRIORITIZATION) | 2022-09-14 | Division Design Raleigh Let (DDRL) | 2027-03-16 | Delivery | 438300 | 2021-06-22 | 240000 | 2022-11-22 | 13600000 | 2025-05-09
R-5830 | 11 | High Country RPO | WATAUGA | SR 1522 (DEERFIELD ROAD), FROM STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD) IN BOONE. UPGRADE ROADWAY. | Yes | 2025-07-02 | HIGHWAY - STI (PRIORITIZATION) | 2025-10-17 | Division Design Raleigh Let (DDRL) | 2028-06-20 | Delivery | 6200000 | 2025-07-24 | 500000 | 2025-07-02 | 16000000 | 2025-07-02
R-5832 | 11 | High Country RPO | ASHE | NC 88, FROM NC 88 TO NC 194. UPGRADE ROADWAY. | Yes | 2024-11-01 | HIGHWAY - STI (PRIORITIZATION) | 2025-08-25 | Division Design Raleigh Let (DDRL) | 2028-08-15 | Delivery | 16300000 | 2024-12-11 | 1700000 | 2025-03-03 | 68000000 | 2024-11-01
R-5836 | 11 | Northwest Piedmont RPO | SURRY | US 601 (ROCKFORD STREET) FROM I-74 TO SR 1104 (CODY TRAIL) SOUTH OF DOBSON. WIDEN TO FOUR LANES. | Yes | 2025-11-24 | HIGHWAY - STI (PRIORITIZATION) | 2027-04-14 | Division Design Raleigh Let (DDRL) | 2029-04-17 | Delivery | 980000 | 2025-01-13 | 2200000 | 2025-01-13 | 143800000 | 2025-11-24
R-5840 | 14 | Foothills RPO | POLK | NC 9 FROM US 74 TO NC 108. CONSTRUCT PAVED SHOULDERS. | Yes | 2024-07-15 | HIGHWAY - STI (PRIORITIZATION) | 2022-05-25 | Division Design Raleigh Let (DDRL) | 2029-08-21 | Delivery | 2200000 | 2021-06-13 | 1300000 | 2023-10-06 | 19400000 | 2026-08-17
R-5853 | 4 | Goldsboro Urban Area MPO | WAYNE | US 13 FROM SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | Yes | 2026-07-01 | HIGHWAY - STI (PRIORITIZATION) | 2025-06-09 | Division Design Raleigh Let (DDRL) | 2028-06-20 | Delivery | 3500000 | 2024-08-14 | 1900000 | 2024-05-07 | 10100000 | 2026-07-01
R-5879 | 1 | Mid-East RPO | MARTIN | MARTIN COUNTY AT US 13/US 17 AT MAIN STREET IN WILLIAMSTON.IMPROVE INTERSECTION. | Yes | 2024-05-31 | HIGHWAY - STI (PRIORITIZATION) | 2027-10-29 | Raleigh Letting (LET) | 2030-10-15 | Delivery | 30000 | 2026-06-24 | 220000 | 2026-06-24 | 5900000 | 2026-06-24
R-5887 | 8 | Capital Area MPO | CHATHAM | US 64 CHATHAM & WAKE COUNTIES AT NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-11-20 | Division Design Raleigh Let (DDRL) | 2032-05-18 | Delivery | 27500000 | 2026-02-24 | 2600000 | 2026-02-06 | 142500000 | 2026-03-10
R-5889A | 7 | Greensboro Urban Area MPO | GUILFORD | US 29 FROM NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-08-18 | Division Design Raleigh Let (DDRL) | 2032-08-17 | Delivery | 37400000 | 2025-09-05 | 4500000 | 2025-06-16 | 136700000 | 2025-07-08
R-5899 | 3 | Cape Fear RPO | PENDER | NC 210 AT SR 1560 (WATTS LANDING ROAD) INTERSECTION IN SURFCITY. IMPROVE INTERSECTION. | Yes | 2026-02-10 | HIGHWAY - STI (PRIORITIZATION) | 2025-09-08 | Division Design Raleigh Let (DDRL) | 2027-04-20 | Delivery | 820000 | 2025-03-12 | 210000 | 2024-09-24 | 7500000 | 2026-02-10
R-5900 | 3 | Cape Fear RPO | PENDER | NC 50/ NC 210 AT SR 1534 (BELT ROAD). IMPROVE INTERSECTION. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-11-22 | Division Design Raleigh Let (DDRL) | 2030-05-21 | Delivery | 4600000 | 2024-07-10 | 310000 | 2024-09-13 | 19500000 | 2024-09-16
R-5905 | 11 | Northwest Piedmont RPO | SURRY | NC 89 (WEST PINE STREET) FROM SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-09-21 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 25000000 | 2026-02-23 | 5900000 | 2026-02-05 | 53400000 | 2024-11-19
R-5909 | 11 | Northwest Piedmont RPO | YADKIN | SR 1314 (EAST MAIN STREET) FROM US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-08-20 | Division Design Raleigh Let (DDRL) | 2030-06-18 | Delivery | 10000000 | 2024-12-05 | 2300000 | 2024-09-30 | 11000000 | 2024-10-03
R-5913 | 11 | Northwest Piedmont RPO | YADKIN | US 21 BUSINESS WIDENING AND PEDESTRIAN IMPROVEMENT PROJECT IN JONESVILLE AND ELKIN. REHABILIATE BRIDGE 850021 OVER THE YADKIN RIVER AND WIDEN US 21 BUSINESS FROM COMMERCE STREET IN ELKIN TO SR 1402 / US 21 BUSINESS (NORTH BRIDGE STREET) INJONESVILLE. CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET / ELM | Yes | 2025-07-03 | HIGHWAY - STI (PRIORITIZATION) | 2025-12-05 | Division Design Raleigh Let (DDRL) | 2028-07-18 | Delivery | 2200000 | 2025-07-16 | 400000 | 2025-06-26 | 10500000 | 2025-07-03
R-5914 | 11 | Northwest Piedmont RPO | YADKIN | NC 67 FROM US 601 IN BOONEVILLE TO SR 1545 (WEST MAIN STREET) IN EAST BEND. MODERNIZE ROADWAY AND CONSTRUCT INTERSECTION IMPROVEMENTS AT NC 67 AND SR 1570 (NEBO ROAD) / SR 1003 (SMITHTOWN ROAD). | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-03-13 | Division Design Raleigh Let (DDRL) | 2033-03-15 | Delivery | 29000000 | 2025-04-02 | 14800000 | 2024-11-19 | 92100000 | 2024-11-15
R-5927 | 8 | Sandhills MPO, Central Pines RPO | MOORE | US 15/US 501 FROM NC 2/NC 211/MIDLAND DRIVE TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-08-20 | Division Design Raleigh Let (DDRL) | 2031-05-20 | Delivery | 1100000 | 2026-02-13 | 4600000 | 2026-02-18 | 61800000 | 2026-02-24
R-5929 | 8 | Central Pines RPO | MOORE | NC 24 / NC 27 AT SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15/ US 501. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-08-20 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 500000 | 2025-03-14 | 300000 | 2025-03-10 | 4900000 | 2025-03-10
R-5936 | 1 | Albemarle RPO | WASHINGTON | SR 1126 (NEWLAND ROAD) FROM SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE) MODERNIZE ROADWAY. | Yes | 2024-03-19 | HIGHWAY - STI (PRIORITIZATION) | 2027-08-02 | Division Design Raleigh Let (DDRL) | 2029-10-16 | Delivery | 820000 | 2024-04-02 | 120000 | 2024-03-14 | 38000000 | 2024-03-19
R-5937 | 1 | Albemarle RPO | WASHINGTON | SR 1106 (MORATTOCK ROAD) WASHINGTON COUNTY FROM SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-01-21 | Division Design Raleigh Let (DDRL) | 2032-01-20 | Delivery | 1400000 | 2024-05-15 | 340000 | 2024-06-13 | 21600000 | 2024-05-14
R-5939 | 1 | Albemarle RPO | PERQUIMANS | SR 1300 (NEW HOPE ROAD) FROM WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | Yes | 2026-07-01 | HIGHWAY - STI (PRIORITIZATION) | 2027-12-17 | Division Design Raleigh Let (DDRL) | 2030-01-15 | Delivery | 2600000 | 2026-07-01 | 2600000 | 2026-06-26 | 31700000 | 2026-07-09
R-5940 | 1 | Albemarle RPO | TYRRELL | US 64 FROM COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-10-15 | Division Design Raleigh Let (DDRL) | 2032-01-20 | Delivery | 1400000 | 2024-10-14 | 6000000 | 2024-08-30 | 64900000 | 2024-09-26
R-5943 | 2 | Eastern Carolina RPO | GREENE | US 13 AT SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-07-15 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 3700000 | 2026-01-29 | 600000 | 2026-02-16 | 10600000 | 2026-01-28
R-5949 | 4 | Upper Coastal Plain RPO | EDGECOMBE | US 258 FROM SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | Yes | 2025-04-29 | HIGHWAY - STI (PRIORITIZATION) | 2029-11-20 | Raleigh Letting (LET) | 2032-11-16 | Delivery | 8500000 | 2025-04-23 | 2600000 | 2024-10-21 | 54000000 | 2025-04-29
R-5950 | 4 | Upper Coastal Plain RPO | JOHNSTON | SR 1501 (SWIFT CREEK ROAD) FROM AIRPORT INDUSTRIAL DRVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | Yes | 2026-05-18 | HIGHWAY - STI (PRIORITIZATION) | 2028-10-16 | Division Design Raleigh Let (DDRL) | 2030-09-17 | Delivery | 720000 | 2026-05-13 | 530000 | 2026-05-18 | 12900000 | 2026-05-04
R-5958 | 8 | Piedmont Triad RPO | RANDOLPH | NC 159 (ZOO PARKWAY) AT RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | Yes | 2024-10-31 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-19 | Division POC Let (DPOC) | 2029-06-26 | Delivery | 800000 | 2025-04-22 | 410000 | 2025-04-22 | 1900000 | 2024-10-31
R-5959 | 8 | Central Pines RPO | LEE | SR 1521 (KELLY DRIVE) FROM SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | Yes | 2026-03-03 | HIGHWAY - STI (PRIORITIZATION) | 2025-07-22 | Division Design Raleigh Let (DDRL) | 2027-10-19 | Delivery | 1900000 | 2023-10-02 | 660000 | 2023-10-02 | 7900000 | 2026-03-03
TD-5307 | 5 | Capital Area MPO | WAKE | VARIOUS, TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER ANDPARK-AND-RIDE FACILITY. | Not Yet | Not Yet | TRANSIT - STI (PRIORITIZATION) | 2027-06-18 | NON - DOT LET (LAP) | 2028-06-20 | Delivery | 1500000 | 2025-06-20 |  |  | 6658000 | 2025-06-20
U-2307B | 12 | Greater Hickory MPO | CATAWBA | EAST SIDE THOROUGHFARE FROM SR 1453 (SPRINGS ROAD) TO NC 127 | Yes | 2023-11-14 | HIGHWAY - STI (PRIORITIZATION) | 2026-12-14 | Raleigh Letting (LET) | 2029-06-19 | Delivery | 53800000 | 2024-02-12 | 15700000 | 2023-11-14 | 64700000 | 2023-11-14
U-2509AA | 10 | Charlotte Regional TPO | MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) AT SHARON FOREST DRIVE AND HARRIS BOULEVARD / VILLAGE LAKE DRIVE. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | Yes | 2024-01-02 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-30 | Raleigh Letting (LET) | 2031-03-18 | Delivery | 85100000 | 2023-10-09 | 6500000 | 2023-12-28 | 78500000 | 2024-01-02
U-2509AB | 10 | Charlotte Regional TPO | MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) AT SR 3356 (SARDIS ROAD) ANDSR 3473 (SAM NEWELL ROAD) IN CHARLOTTE. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SR 3473 (SAM NEWELL ROAD). CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FRO | Yes | 2024-02-12 | HIGHWAY - STI (PRIORITIZATION) | 2027-04-30 | Raleigh Letting (LET) | 2031-04-15 | Delivery | 40700000 | 2024-03-06 | 5700000 | 2024-02-07 | 76000000 | 2024-02-12
U-2509AC | 10 | Charlotte Regional TPO | MECKLENBURG | US 74 (INDEPENDENCE POINTE PARKWAY) FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY) IN CHARLOTTE.CONSTRUCT ROADWAY ON NEW LOCATION. | Yes | 2024-02-22 | HIGHWAY - STI (PRIORITIZATION) | 2030-04-30 | Raleigh Letting (LET) | 2032-10-19 | Delivery | 5800000 | 2024-01-31 | 3500000 | 2024-02-22 | 20400000 | 2024-02-22
U-2509AD | 10 | Charlotte Regional TPO | MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) AT SR 3143 (MATTHEWS-MINT HILL ROAD) IN CHARLOTTE. CONSTRUCT INTERCHANGE AT SR 3143 (MATTHEWS-MINT HILL ROAD) AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | Yes | 2024-01-25 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-30 | Raleigh Letting (LET) | 2030-07-16 | Delivery | 46800000 | 2024-01-31 | 2600000 | 2024-02-22 | 35700000 | 2024-01-25
U-2509B | 10 | Charlotte Regional TPO | MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) FROM SARDIS ROAD NORTH TO IDLEWILD ROAD. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-31 | Raleigh Letting (LET) | 2033-04-19 | Delivery | 8500000 | 2024-06-19 | 2100000 | 2024-05-01 | 75100000 | 2024-05-15
U-2509EB | 10 | Charlotte Regional TPO | MECKLENBURG | INDEPENDENCE POINTE PARKWAY FROM SR 3356 (SARDIS ROAD) TO SR 3474 (SAM NEWELL ROAD) IN CHARLOTTE. CONSTRUCT ROADWAY ON NEW LOCATION. | Yes | 2024-01-31 | HIGHWAY - STI (PRIORITIZATION) | 2027-07-31 | Raleigh Letting (LET) | 2030-07-16 | Delivery | 1200000 | 2023-11-03 | 190000 | 2024-02-22 | 12000000 | 2024-01-31
U-2530A | 12 | Greater Hickory MPO | CATAWBA | NC 127 FROM SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). WIDEN TO MULTI-LANES. | Yes | 2025-12-30 | HIGHWAY - STI (PRIORITIZATION) | 2025-06-27 | Division Design Raleigh Let (DDRL) | 2029-03-20 | Delivery | 25000000 | 2025-05-01 | 3900000 | 2024-11-20 | 59700000 | 2025-12-30
U-2561C | 4 | Upper Coastal Plain RPO | NASH | NC 43 FROM SR 1613 (WOODRUFF AVENUE)TO I-95 WIDEN TO MULTI-LANES | Yes | 2026-07-13 | HIGHWAY - STI (PRIORITIZATION) | 2026-06-01 | Division Design Raleigh Let (DDRL) | 2028-03-21 | Delivery | 4400000 | 2024-09-12 | 3100000 | 2024-10-29 | 16400000 | 2026-07-13
U-2817 | 2 | Greenville Urban Area MPO | PITT | SR 1700 (EVANS STREET / OLD TAR ROAD) FROM SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | Yes | 2024-11-05 | HIGHWAY - STI (PRIORITIZATION) | 2019-06-27 | Division Design Raleigh Let (DDRL) | 2028-02-15 | Delivery | 53700000 | 2021-08-03 | 8700000 | 2023-07-20 | 117700000 | 2026-05-12
U-2901B | 5 | Capital Area MPO | WAKE | NC 55 (WILLIAMS STREET) FROM US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-05-03 | Division Design Raleigh Let (DDRL) | 2031-06-17 | Delivery | 12900000 | 2024-04-30 | 1700000 | 2024-04-09 | 40300000 | 2024-08-01
U-2901BA | 5 | Capital Area MPO | WAKE | NC 55 (WILLIAMS STREET), CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. | Yes | 2024-08-01 | HIGHWAY - STI (PRIORITIZATION) | 2027-11-19 | Division Design Raleigh Let (DDRL) | 2029-10-16 | Delivery | 830000 | 2024-04-11 | 140000 | 2024-04-03 | 30600000 | 2024-08-01
U-3338C | 3 | Wilmington Urban Area MPO | NEW HANOVER | SR 1175 (KERR AVENUE) AT US 74 (MARTIN LUTHER KING JR PARKWAY) IN WILMINGTON. CONSTRUCT INTERCHANGE IMPROVEMENTS. | Yes | 2024-08-22 | HIGHWAY - STI (PRIORITIZATION) | 2018-05-08 | Division Design Raleigh Let (DDRL) | 2030-06-18 | Delivery | 8000000 | 2021-08-02 | 2300000 | 2022-02-14 | 38800000 | 2026-07-09
U-3400 | 8 | High Point Urban Area MPO | RANDOLPH | SR 1577/SR 1004 (ARCHDALE ROAD) FROM US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | Yes | 2024-10-16 | HIGHWAY - STI (PRIORITIZATION) | 2023-09-15 | Division Design Raleigh Let (DDRL) | 2030-06-18 | Delivery | 7901000 | 2023-01-24 | 6300000 | 2024-08-21 | 43600000 | 2024-10-16
U-3415A | 10 | Cabarrus-Rowan MPO | CABARRUS | SR 1394 (POPLAR TENT ROAD) FROM GABLE OAKS LANE / WOODHAVENPLACE TO SEASONS PLACE IN CONCORD. WIDEN TO MULTI-LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-01-15 | Division Design Raleigh Let (DDRL) | 2033-06-21 | Delivery | 12900000 | 2023-01-25 | 900000 | 2023-01-25 | 49400000 | 2024-10-28
U-3422B | 6 | Fayetteville Area MPO | CUMBERLAND | SR 1003 (CAMDEN ROAD) FROM JUST WEST OF SR 1112 (ROCKFISH ROAD) TO SR 1596 (HOPE MILLS ROAD). | Yes | 2025-09-25 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2026-12-15 | Delivery |  |  |  |  | 54000000 | 2025-09-25
U-3431 | 2 | Down East RPO | CRAVEN | NC 101/SR 1763 (FONTANA BOULEVARD/MILLER BOULEVARD) FROM SR1756 (LAKE ROAD) TO OUTER BANKS DRIVE IN HAVELOCK; AND SR 1756 (LAKE ROAD) FROM SR 1763 (MILLER BOULEVARD) TO THE HAVELOCK BYPASS. WIDEN TO MULTI-LANES AND CONSTRUCT ROAD IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-11-16 | Division Design Raleigh Let (DDRL) | 2030-07-16 | Delivery | 26000000 | 2025-08-29 | 3500000 | 2025-05-01 | 96600000 | 2025-08-12
U-3467 | 10 | Charlotte Regional TPO | UNION | NC 84 (WEDDINGTON ROAD) FROM NC 16 (PROVIDENCE ROAD) TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | Yes | 2024-04-29 | HIGHWAY - STI (PRIORITIZATION) | 2024-06-28 | Raleigh Letting (LET) | 2027-07-20 | Delivery | 41000000 | 2024-04-22 | 5700000 | 2024-04-22 | 103300000 | 2024-04-29
U-3618 | 2 | Eastern Carolina RPO | LENOIR | KINSTON - SR 1571 (CAREY ROAD EXTENSION) FROM SR 1572 (ROUSE ROAD) TO US 258 AT SR 1001 (PAULS PATH ROAD) | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-06-26 | Division Design Raleigh Let (DDRL) | 2031-05-20 | Delivery | 3200000 | 2025-04-16 | 2900000 | 2025-04-22 | 50300000 | 2024-09-27
U-4007E | 3 | Jacksonville Urban Area MPO | ONSLOW | NC 53 FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE) IN JACKSONVILLE. ADD LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-07-14 | Division Design Raleigh Let (DDRL) | 2031-01-21 | Delivery | 8900000 | 2024-07-01 | 420000 | 2026-02-27 | 16500000 | 2026-05-29
U-4403C | 6 | Fayetteville Area MPO | CUMBERLAND | US 401 (RAMSEY STREET)FROM US 401 BYPASS TO NORTH OF SLOCOMB ROAD | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-01-30 | Division Design Raleigh Let (DDRL) | 2033-01-18 | Delivery | 23400000 | 2024-02-12 | 20900000 | 2024-10-09 | 55300000 | 2024-01-11
U-4404 | 6 | Fayetteville Area MPO | CUMBERLAND | SR 1400 (CLIFFDALE ROAD) FROM MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-05-31 | Division Design Raleigh Let (DDRL) | 2032-05-18 | Delivery | 5800000 | 2025-04-11 | 5400000 | 2025-04-24 | 10800000 | 2025-04-03
U-4405C | 6 | Fayetteville Area MPO | CUMBERLAND | US 401 (RAEFORD ROAD) FROM EAST OF SR 1596 (GLENSFORD DRIVE) TO EAST OF ROBESON STREET. | Yes | 2024-11-20 | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2029-01-16 | Delivery |  |  |  |  | 63400000 | 2024-11-20
U-4407 | 4 | Goldsboro Urban Area MPO | WAYNE | US 70 BUSINESS (EAST ASH STREET) FROM SR 1711 (SOUTH OAK FOREST ROAD) TO US 70. WIDEN TO FOUR LANES. | Yes | 2026-05-22 | HIGHWAY - STI (PRIORITIZATION) | 2026-07-31 | Division Design Raleigh Let (DDRL) | 2028-10-17 | Delivery | 9500000 | 2026-05-13 | 2200000 | 2026-04-16 | 29500000 | 2026-05-21
U-4700A | 12 | Greater Hickory MPO | CATAWBA | US 321 FROM US 70 IN HICKORY TO US 321A (COMBINED WITH B-4450: TO REPLACE BRIDGE 367 OVER CATAWBA RIVER ON US 321) | Yes | 2026-02-23 | HIGHWAY - STI (PRIORITIZATION) | 2019-11-26 | Division Design Raleigh Let (DDRL) | 2027-08-17 |  | 64000000 | 2020-10-26 |  |  | 287400000 | 2026-07-01
U-4700CA | 11 | Greater Hickory MPO | CALDWELL | US 321 AT SR 1160 (MOUNT HERMAN ROAD) IN HUDSON. UPGRADE TOREDUCED CONFLICT INTERSECTION. | Yes | 2025-06-18 | HIGHWAY - STI (PRIORITIZATION) | 2019-01-18 | Division Design Raleigh Let (DDRL) | 2026-09-15 | Delivery | 420000 | 2020-10-19 |  |  | 8200000 | 2025-06-18
U-4700CB | 11 | Greater Hickory MPO | CALDWELL | US 321 AT SR 1809 / SR 1952 (PINE MOUNTAIN ROAD) IN HUDSON.INSTALL REDUCED CONFLICT INTERSECTION. | Yes | 2025-06-18 | HIGHWAY - STI (PRIORITIZATION) | 2019-01-18 | Division Design Raleigh Let (DDRL) | 2026-09-15 | Delivery | 500000 | 2020-10-19 | 100000 | 2025-01-17 | 16400000 | 2025-06-18
U-4714AC | 10 | Charlotte Regional TPO | UNION | SR 1010 (JOHN STREET) / SR 1009 (OLD MONROE ROAD) FROM EASTOF I-485 TO WEST OF MORNINGSIDE MEADOW LANE IN MATTHEWS. WIDEN TO MULTI-LANES. | Yes | 2025-01-09 | HIGHWAY - STI (PRIORITIZATION) | 2019-07-25 | Raleigh Letting (LET) | 2027-01-19 | Delivery | 2152894 | 2021-09-01 | 2200000 | 2025-01-17 | 40700000 | 2025-01-09
U-4714BA | 10 | Charlotte Regional TPO | UNION | SR 1009 (OLD MONROE ROAD) FROM WEST OF MORNINGSIDE MEADOW LANE TO INDIAN TRAIL ROAD IN MATTHEWS. WIDEN TO MULTI-LANES. | Yes | 2025-10-01 | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2027-01-19 | Delivery |  |  |  |  | 22555000 | 2025-10-01
U-4714BB | 10 | Charlotte Regional TPO | UNION | SR 1009 (JOHNSTREET / OLD MONROE ROAD) INDIAN TRAIL ROAD TOEAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | Yes | 2025-10-01 | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2028-02-15 | Delivery |  |  |  |  | 77765000 | 2025-10-01
U-4739 | 13 | French Broad River MPO | BUNCOMBE | SR 3556 (AMBOY ROAD / MEADOW ROAD) FROM I-240 TO NC 81/SR 3214 (BILTMORE AVENUE) IN ASHEVILLE. UPGRADE ROADWAY INCLUDING A NEW BRIDGE OVER THE FRENCH BROAD RIVER. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-09-20 | Raleigh Letting (LET) | 2033-03-15 | Delivery | 24100000 | 2024-08-14 | 5400000 | 2024-08-20 | 58300000 | 2024-08-21
U-4900 | 6 | Fayetteville Area MPO | CUMBERLAND | NC 210 (MURCHISON ROAD) FROM I-295 TO SOUTH OF US 401 BYPASS | Yes | 2026-04-07 | HIGHWAY - STI (PRIORITIZATION) | 2023-04-28 | Division Design Raleigh Let (DDRL) | 2027-12-21 | Delivery | 10600000 | 2022-08-25 | 15000000 | 2022-08-25 | 35000000 | 2026-04-07
U-4902C | 3 | Wilmington Urban Area MPO | NEW HANOVER | US 17 BUSINESS (MARKET STREET) FROM NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. CONSTRUCT ACCESS MANAGEMENTIMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-07-02 | Division Design Raleigh Let (DDRL) | 2032-08-17 | Delivery | 56300000 | 2024-10-29
U-5019A | 13 | French Broad River MPO | BUNCOMBE | CONSTRUCT CLINGMAN FOREST AND NASTY BRANCH GREENWAYS | Yes | 2026-03-30 | HIGHWAY - STI (PRIORITIZATION) |  | NON - DOT LET (LAP) | 2026-09-30 | Delivery |  |  |  |  | 5300000 | 2026-03-30
U-5019E | 13 | French Broad River MPO | BUNCOMBE | BRIDGE IMPROVEMENTS ON BRIDGE 100743 OVER THE FRENCH BROAD RIVER ON SR 3408 (CRAVEN STREET), IN ASHEVILLE. CONSTRUCT BRIDGE IMPROVEMENTS. THIS PROJECT IS PART OF THE RIVERWAY MULTI-MODAL NETWORK. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-04-16 | Division POC Let (DPOC) | 2028-04-05 | Delivery | 2000000 | 2026-01-26 | 3800000 | 2024-03-05 | 5300000 | 2024-05-06
U-5301 | 5 | Capital Area MPO | WAKE | APEX/CARY - US 64 FROM WEST OF SR 1306 (LAURA DUNCAN ROAD) TO US 1 | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-05-18 | Raleigh Letting (LET) | 2031-04-15 | Delivery | 93000000 | 2025-11-05 | 4400000 | 2024-10-29 | 207100000 | 2024-10-29
U-5301A | 5 | Capital Area MPO | WAKE | APEX/CARY - US 64 AT SR 1306 (LAURA DUNCAN ROAD) | Yes | 2024-10-29 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-15 | Raleigh Letting (LET) | 2028-10-17 | Delivery | 5600000 | 2024-10-29 | 110000 | 2024-10-29 | 32300000 | 2024-10-29
U-5304F | 7 | Triangle West TPO | ORANGE | US 15/US 501 FROM SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-09-01 | Raleigh Letting (LET) | 2033-10-18 | Delivery | 4400000 | 2025-02-05 | 1700000 | 2025-01-09 | 77500000 | 2024-12-04
U-5307A | 5 | Capital Area MPO | WAKE | US 1 FROM I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | Not Yet | 2024-04-22 | HIGHWAY - STI (PRIORITIZATION) | 2026-04-09 | Raleigh Letting (LET) | 2031-06-17 | Delivery | 128500000 | 2024-02-28 | 13400000 | 2024-01-12 | 295600000 | 2024-04-22
U-5307B | 5 | Capital Area MPO | WAKE | US 1 FROM NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. UPGRADEROADWAY TO CONTROLLED ACCESS FACILITY. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-04-09 | Raleigh Letting (LET) | 2031-06-17 | Delivery | 119500000 | 2024-02-28 | 8200000 | 2024-02-07 | 177400000 | 2025-09-01
U-5307C | 5 | Capital Area MPO | WAKE | US 1 FROM NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTHOF NC 98 BUSINESS IN WAKE FOREST. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-11-16 | Raleigh Letting (LET) | 2033-06-21 | Delivery | 37700000 | 2024-02-28 | 6400000 | 2024-02-07 | 152900000 | 2025-09-01
U-5307D | 5 | Capital Area MPO | WAKE | US 1 FROM SOUTH OF NC 98 BUSINESS TO SR 1909 (PURNELL ROAD)/ SR 1931 (HARRIS ROAD) IN WAKE FOREST. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-11-16 | Raleigh Letting (LET) | 2033-06-21 | Delivery | 72000000 | 2024-02-28 | 10100000 | 2024-02-07 | 160500000 | 2024-05-15
U-5308 | 8 | High Point Urban Area MPO | RANDOLPH | SR 1547 (FINCH FARM ROAD) FROM SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | Yes | 2024-10-24 | HIGHWAY - STI (PRIORITIZATION) | 2019-09-30 | Division Design Raleigh Let (DDRL) | 2028-09-19 | Delivery | 7396000 | 2021-05-18 | 3900000 | 2025-02-28 | 50100000 | 2024-10-24
U-5508 | 3 | Jacksonville Urban Area MPO | ONSLOW | NC 24 (LEJEUNE BLVD) AT NC 53 (WESTERN BLVD)IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE, (COMB W/U-5736, U-4007E) | Yes | 2026-06-04 | HIGHWAY - STI (PRIORITIZATION) | 2027-07-14 | Division Design Raleigh Let (DDRL) | 2030-01-15 | Delivery | 1100000 | 2025-07-11 | 450000 | 2026-02-09 | 3600000 | 2026-05-29
U-5518 | 5 | Capital Area MPO, Triangle West TPO | WAKE | US 70 (GLENWOOD AVENUE) FROM WEST OF SR 3067 (T. W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY AND INTERCHANGES TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-04-16 | Design Build Let (DBL) | 2030-04-16 | Delivery | 148600000 | 2026-02-20 | 21000000 | 2026-02-13 | 302400000 | 2026-02-20
U-5702A | 3 | Wilmington Urban Area MPO | NEW HANOVER | NC 132 (COLLEGE ROAD) FROM SR 1272 (NEW CENTRE DRIVE) TO US117 (SHIPYARD BOULEVARD) IN WILMINGTON | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-19 | Division Design Raleigh Let (DDRL) | 2033-02-15 | Delivery | 29800000 | 2025-03-12 | 12500000 | 2025-02-18 | 38900000 | 2025-02-26
U-5706 | 8 | Lumber River RPO | RICHMOND | NEW ROUTE FROM US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-11-11 | Division Design Raleigh Let (DDRL) | 2031-11-18 | Delivery | 18200000 | 2024-11-15 | 2500000 | 2024-10-24 | 64300000 | 2024-10-24
U-5709 | 8 | Central Pines RPO | LEE | SR 1237 (CARTHAGE STREET) FROM SR 1152 (FIRE TOWER ROAD) TONC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO-LANE DIVIDED FACILITY WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | Yes | 2026-07-30 | HIGHWAY - STI (PRIORITIZATION) | 2021-11-19 | Division Design Raleigh Let (DDRL) | 2028-03-21 | Delivery | 2674000 | 2021-05-04 | 698000 | 2021-05-04 | 23200000 | 2026-07-30
U-5710 | 3 | Wilmington Urban Area MPO | NEW HANOVER | US 74 (EASTWOOD ROAD) SR 1409 (MILITARY CUTOFF ROAD)IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE | Yes | 2024-04-24 | HIGHWAY - STI (PRIORITIZATION) | 2023-06-16 | Division Design Raleigh Let (DDRL) | 2027-09-21 | Delivery | 16900000 | 2022-11-30 | 4000000 | 2024-11-15 | 60200000 | 2026-06-02
U-5711 | 8 | Piedmont Triad RPO | RANDOLPH | SR 1712 (PINEVIEW STREET) FROM WEST OF SYLVAN DRIVE TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | Yes | 2026-03-06 | HIGHWAY - STI (PRIORITIZATION) | 2018-08-31 | Division Design Raleigh Let (DDRL) | 2026-09-15 | Delivery | 1233000 | 2017-11-17 | 130000 | 2022-08-15 | 9700000 | 2026-03-06
U-5716 | 3 | Jacksonville Urban Area MPO | ONSLOW | NC 24 AT US 258 (RICHLANDS HIGHWAY) INTERSECTION - CONVERT AT-GRADE INTERSECTION TO INTERCHANGE | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-07-19 | Division Design Raleigh Let (DDRL) | 2031-03-18 | Delivery | 33600000 | 2025-01-27 | 3900000 | 2024-12-02 | 66400000 | 2024-12-02
U-5717 | 5 | Triangle West TPO | DURHAM | US 15/US 501 AT SR 1116 (GARRETT ROAD) IN DURHAM. UPGRADE AT-GRADE INTERSECTION TO AN INTERCHANGE. | Yes | 2025-12-22 | HIGHWAY - STI (PRIORITIZATION) | 2019-04-23 | Division Design Raleigh Let (DDRL) | 2029-10-16 | Delivery | 20413786 | 2021-06-22 |  |  | 62200000 | 2025-12-22
U-5723 | 10 | Charlotte Regional TPO | UNION | US 74 AT US 601 IN MONROE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | Yes | 2026-04-02 | HIGHWAY - STI (PRIORITIZATION) | 2019-01-28 | Division Design Raleigh Let (DDRL) | 2030-01-15 | Delivery | 2160000 | 2021-09-10 | 500000 | 2024-09-24 | 25400000 | 2026-04-02
U-5726 | 4 | Upper Coastal Plain RPO | JOHNSTON | US 301/NC 39/NC 96 FROM SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-11-27 | Division Design Raleigh Let (DDRL) | 2029-03-20 | Delivery | 13900000 | 2024-06-13 | 4300000 | 2024-07-17 | 29100000 | 2024-05-10
U-5727 | 8 | Central Pines RPO | LEE | US 1/US 15/US 501 FROM SOUTH OF SR 1198 (BRYAN DRIVE) TO SR1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. (COMB W/U-5727). | Yes | 2026-08-03 | HIGHWAY - STI (PRIORITIZATION) | 2023-03-16 | Division Design Raleigh Let (DDRL) | 2028-01-18 | Delivery | 9325000 | 2023-10-03 | 1500000 | 2024-08-27 | 30500000 | 2026-08-03
U-5727A | 8 | Central Pines RPO | LEE | US 1 / US15 / US 501 SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. CLEARING, GRUBBING, AND EROSION CONTROL. | Yes | 2025-09-19 | HIGHWAY - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2026-08-11 | Delivery |  |  |  |  | 2500000 | 2025-09-19
U-5728 | 3 | Jacksonville Urban Area MPO | ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) AT SR 1308 (BELL FORK ROAD/GUM BRANCH ROAD)IN JACKSONVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | 2026-03-06 | HIGHWAY - STI (PRIORITIZATION) | 2018-03-12 | Division Design Raleigh Let (DDRL) | 2026-09-15 | Delivery | 1700000 | 2022-03-30 | 590000 | 2024-02-07 | 6800000 | 2026-03-06
U-5731 | 3 | Wilmington Urban Area MPO | NEW HANOVER | US 74 AT US 17/US 421, CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-10-15 | Division Design Raleigh Let (DDRL) | 2030-06-18 | Delivery | 6100000 | 2024-11-13 | 590000 | 2024-11-26 | 48700000 | 2024-12-03
U-5732 | 3 | Wilmington Urban Area MPO | PENDER | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONSTRUCT REDUCED CONFLICT INTERSECTION. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-05-31 | Division Design Raleigh Let (DDRL) | 2032-01-20 | Delivery | 25200000 | 2025-03-28 | 5100000 | 2024-12-30 | 60000000 | 2024-12-31
U-5734 | 3 | Wilmington Urban Area MPO | NEW HANOVER | US 421 (SOUTH FRONT STREET) FROM US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD).WIDEN TO MULTI-LANES. | Yes | 2024-10-31 | HIGHWAY - STI (PRIORITIZATION) | 2025-11-24 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 35800000 | 2024-11-12 | 3200000 | 2024-10-24 | 37500000 | 2024-10-31
U-5735 | 3 | Jacksonville Urban Area MPO | ONSLOW | US 17 (WILMINGTON HIGHWAY) AT SR 1130 (OLD MAPLEHURST ROAD)IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO THE NEW RIVER MARINE CORPS AIR STATION MAIN GATE AT MCCUTCHEON FIELD. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-12-17 | Division Design Raleigh Let (DDRL) | 2032-06-15 | Delivery | 25000000 | 2026-04-01 | 5100000 | 2025-12-29 | 109400000 | 2026-01-07
U-5736 | 3 | Jacksonville Urban Area MPO | ONSLOW | NC 53 (WESTERN BOULEVARD) FROM US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-07-14 | Division Design Raleigh Let (DDRL) | 2031-01-21 | Delivery | 16100000 | 2024-08-12 | 2300000 | 2026-02-27 | 55800000 | 2026-05-29
U-5737 | 8 | Central Pines RPO | CHATHAM | US 64 (EAST 11TH STREET) FROM NORTH GLENN AVENUE TO US 421 (FUTURE I-685) IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL AND INSTALL PEDESTRIAN FACILITIES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-06-30 | Division Design Raleigh Let (DDRL) | 2030-09-17 | Delivery | 8000000 | 2026-03-20 | 3400000 | 2026-01-08 | 43600000 | 2026-03-06
U-5739 | 3 | Jacksonville Urban Area MPO | ONSLOW | US 258 / NC 24 (RICHLANDS HIGHWAY) FROM SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | Yes | 2024-10-07 | HIGHWAY - STI (PRIORITIZATION) | 2027-07-14 | Division Design Raleigh Let (DDRL) | 2031-01-21 | Delivery | 2600000 | 2024-10-14 | 3200000 | 2024-11-14 | 31600000 | 2024-10-07
U-5747A | 5 | Capital Area MPO | WAKE | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. (COMB W/U-5747B & U-5750). | Yes | 2024-11-26 | HIGHWAY - STI (PRIORITIZATION) | 2021-02-08 | Division Design Raleigh Let (DDRL) | 2028-05-16 | Delivery | 6256000 | 2021-04-13 | 550000 | 2022-07-26 | 28500000 | 2026-06-17
U-5747B | 5 | Capital Area MPO | WAKE | SR 1635 AT NC 54 - CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. (COMB W/U-5747A & U-5750). | Yes | 2024-11-26 | HIGHWAY - STI (PRIORITIZATION) | 2019-08-14 | Division Design Raleigh Let (DDRL) | 2028-05-16 | Delivery | 10070000 | 2021-03-18 | 620000 | 2022-07-26 | 44500000 | 2026-06-17
U-5750 | 5 | Capital Area MPO | WAKE | NC 54 FROM NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. CONSTRUCT ADDITIONAL LANES. (COMB W/U-5747A & U-5747B). | Yes | 2025-01-10 | HIGHWAY - STI (PRIORITIZATION) | 2021-01-22 | Division Design Raleigh Let (DDRL) | 2028-05-16 | Delivery | 6967000 | 2021-06-16 | 1700000 | 2022-04-01 | 28300000 | 2026-06-17
U-5751 | 5 | Capital Area MPO | WAKE | NC 55/NC 42 IN FUQUAY-VARINA, IMPROVE US 401 INTERSECTION WITH NC 55/NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO JUDD PARKWAY. | Yes | 2024-05-17 | HIGHWAY - STI (PRIORITIZATION) | 2027-07-21 | Raleigh Letting (LET) | 2031-01-21 | Delivery | 59900000 | 2024-03-22 | 3300000 | 2025-04-07 | 113300000 | 2024-05-17
U-5753 | 8 | Fayetteville Area MPO | HOKE | SR 1305, US 401 TO PLANK ROAD; AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD) WIDEN TO MULTILANES. | Yes | 2026-01-13 | HIGHWAY - STI (PRIORITIZATION) | 2022-06-17 | Raleigh Letting (LET) | 2027-06-15 | Delivery | 42050000 | 2024-08-23 | 385000 | 2024-08-22 | 62100000 | 2026-01-13
U-5761 | 10 | Cabarrus-Rowan MPO | CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) AT US 29 / US 601 (CANNON BOULEVARD) IN KANNAPOLIS. CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | 2026-02-05 | HIGHWAY - STI (PRIORITIZATION) | 2019-03-13 | Division Design Raleigh Let (DDRL) | 2027-09-21 | Delivery | 180000 | 2017-11-17 | 1800000 | 2024-09-09 | 20600000 | 2026-02-05
U-5763 | 10 | Charlotte Regional TPO | MECKLENBURG | NC 51 (MATTHEWS TOWNSHIP PARKWAY) FROM SR 3356 (SARDIS ROAD) TO SR 1009 / SR 1010 (WEST JOHN STREET) IN MATTHEWS. WIDEN TO SIX LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-09-12 | Division Design Raleigh Let (DDRL) | 2034-05-16 | Delivery | 40100000 | 2024-09-30 | 5800000 | 2024-09-20 | 43000000 | 2024-06-28
U-5764 | 10 | Charlotte Regional TPO | UNION | US 74 FROM NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-09-27 | Division Design Raleigh Let (DDRL) | 2030-06-18 | Delivery | 59248000 | 2024-11-13 | 7400000 | 2024-06-06 | 74700000 | 2024-05-01
U-5765 | 10 | Charlotte Regional TPO | MECKLENBURG | NC 73 (SAM FURR ROAD) FROM SR 5544 (WEST CATAWBA AVENUE) TOSR 2316 / SR 2141 (NORTHCROSS DRIVE) IN HUNTERSVILLE. WIDENTO SIX LANES. | Yes | 2026-07-07 | HIGHWAY - STI (PRIORITIZATION) | 2022-10-12 | Raleigh Letting (LET) | 2026-10-20 | Delivery | 27000000 | 2020-10-26 | 7369000 | 2021-08-23 | 61900000 | 2026-07-07
U-5766A | 10 | Charlotte Regional TPO | MECKLENBURG | NC 160 (STEEL CREEK ROAD) FROM THE SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD / YORK ROAD) IN CHARLOTTE. WIDEN TO MULTI-LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-05-17 | Division Design Raleigh Let (DDRL) | 2030-11-19 | Delivery | 26600000 | 2024-09-13 | 10700000 | 2024-11-07 | 35600000 | 2024-01-30
U-5766B | 10 | Charlotte Regional TPO | MECKLENBURG | NC 160, FROM NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-08-17 | Division Design Raleigh Let (DDRL) | 2030-04-16 | Delivery | 58200000 | 2024-11-07 | 42200000 | 2024-11-07 | 137400000 | 2024-11-27
U-5767 | 10 | Charlotte Regional TPO | MECKLENBURG | US 21 (STATESVILLE ROAD) FROM NORTHCROSS CENTER COURT TO SR2147 (WESTMORELAND ROAD). WIDEN TO MULTILANES. | Yes | 2024-04-29 | HIGHWAY - STI (PRIORITIZATION) | 2029-07-18 | Raleigh Letting (LET) | 2033-07-19 | Delivery | 88500000 | 2024-12-17 | 2700000 | 2024-04-26 | 44300000 | 2024-04-29
U-5768 | 10 | Charlotte Regional TPO | MECKLENBURG | NC 49 FROM JOHN KIRK DRIVE TO I-485 IN HARRISBURG. WIDEN TOSIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO NC 49 AND MALLARD CREEK CHURCH ROAD. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | Yes | 2024-02-22 | HIGHWAY - STI (PRIORITIZATION) | 2029-07-17 | Raleigh Letting (LET) | 2033-07-19 | Delivery | 37900000 | 2025-01-17 | 7500000 | 2023-11-13 | 80400000 | 2024-02-22
U-5769A | 10 | Charlotte Regional TPO | UNION | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCHRD). WIDEN TO MULTI-LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-02-02 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 29800000 | 2024-11-11 | 10000 | 2025-01-17 | 71000000 | 2024-06-20
U-5769AA | 10 | Charlotte Regional TPO | UNION | NC 16 (PROVIDENCE ROAD SOUTH) AT SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | Yes | 2025-09-05 | HIGHWAY - STI (PRIORITIZATION) | 2024-07-10 | Division POC Let (DPOC) | 2026-08-20 | Delivery | 4000000 | 2023-10-03 | 90000 | 2025-01-09 | 980000 | 2025-09-05
U-5769B | 10 | Charlotte Regional TPO | UNION | NC 16 (PROVIDENCE ROAD SOUTH) FROM SR 1321 (CUTHBERTSON ROAD) IN WEDDINGTON TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW WIDENTO MULTILANES | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-02-02 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 18200000 | 2024-11-11 | 10000 | 2025-01-17 | 80900000 | 2024-06-20
U-5770B | 8 | High Point Urban Area MPO | RANDOLPH | SR 1009 (SOUTH MAIN STREET) FROM WEST OF COLUMBUS AVENUE TOSR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCIIMPROVEMENTS. | Yes | 2024-08-23 | HIGHWAY - STI (PRIORITIZATION) |  | Division Design Raleigh Let (DDRL) | 2029-01-16 | Delivery |  |  | 2400000 | 2025-02-27 | 25600000 | 2024-08-23
U-5771 | 10 | Charlotte Regional TPO | MECKLENBURG | US 21 FROM SR 2136 (GILEAD ROAD) TO SR 6028 (HOLLY POINT DRIVE) IN HUNTERSVILLE. WIDEN TO FOUR LANES. | Yes | 2025-06-20 | HIGHWAY - STI (PRIORITIZATION) | 2021-12-30 | Raleigh Letting (LET) | 2027-03-16 | Delivery | 53460000 | 2021-07-19 | 1640000 | 2021-07-19 | 44700000 | 2025-06-20
U-5774F | 5 | Triangle West TPO | DURHAM | NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. UPGRADE ROADWAY CORRIDOR AND CONSTRUCT INTERCHANGE IMPROVEMENTS AT I-40. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-20 | Raleigh Letting (LET) | 2033-01-18 | Delivery | 117800000 | 2024-03-08 | 5500000 | 2024-09-11 | 156100000 | 2024-04-11
U-5785 | 2 | Greenville Urban Area MPO | PITT | SR 1708 (FIRETOWER ROAD) FROM WEST OF SR 1725 (COUNTY HOME ROAD)/EAST ARLINGTON BOULEVARD TO SR 1726 (PORTERTOWN ROAD);AND SR 1726 (PORTERTOWN ROAD) FROM FIRETOWER ROAD TO NC 33 IN GREENVILLE. WIDEN TO FOUR LANES. | Yes | 2024-11-06 | HIGHWAY - STI (PRIORITIZATION) | 2024-09-30 | Raleigh Letting (LET) | 2029-07-17 | Delivery | 48000000 | 2024-10-17 | 9300000 | 2024-05-24 | 109400000 | 2024-11-06
U-5786 | 9 | Winston-Salem Area TPO | DAVIDSON | SR 1508 (HICKORY TREE ROAD) FROM US 52/NC 8/FUTURE I-285 TONC 150 WIDEN TO MULTI-LANES | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-12-18 | Division Design Raleigh Let (DDRL) | 2033-10-18 | Delivery | 12700000 | 2025-02-25 | 5200000 | 2024-08-21 | 45700000 | 2024-07-23
U-5790 | 3 | Wilmington Urban Area MPO | NEW HANOVER | US 421 (CAROLINA BEACH ROAD)FROM NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONTRUCT FLYOVERS AT US 421 AND NC 132. INCLUDES U-5859 | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-12-10 | Division Design Raleigh Let (DDRL) | 2029-03-20 | Delivery | 12000000 | 2025-01-23 | 3200000 | 2024-12-02 | 39300000 | 2024-12-02
U-5791A | 3 | Jacksonville Urban Area MPO | ONSLOW | SR 2714 (JACKSONVILLE PARKWAY EXTENSION) FROM NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). WIDEN TO MULTILANES, | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-06-16 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery
U-5792 | 3 | Wilmington Urban Area MPO | NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) FROM US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-06-30 | Division Design Raleigh Let (DDRL) | 2029-06-19 | Delivery | 37900000 | 2025-10-20 | 2700000 | 2025-10-28 | 241900000 | 2025-10-29
U-5799 | 12 | Charlotte Regional TPO | IREDELL | US 21 FROM SR 1933 (PUMP STATION ROAD) TO SR 1930 (FORT DOBBS ROAD) IN STATESVILLE. WIDEN TO FOUR LANES AND REALIGN OFFSET INTERSECTIONS AT SR1922 (SHUMAKER DRIVE) AND SR 2171 (JANE SOWERS ROAD). | Yes | 2024-08-16 | HIGHWAY - STI (PRIORITIZATION) | 2019-12-02 | Raleigh Letting (LET) | 2031-01-14 | Delivery | 22300000 | 2020-12-17 | 3700000 | 2024-12-19 | 29400000 | 2024-08-16
U-5803 | 10 | Charlotte Regional TPO | MECKLENBURG | SR 2940 (EASTWAY DRIVE) - AT INTERSECTION OF SR 2940 (EASTWAY DRIVE) AND (SHAMROCK DRIVE). REALIGN SR 2940 AND RECONFIGURE 5-LEG SKEWED INTERSECTION TO THREE 2-LEG INTERSECTIONS. | Yes | 2026-06-11 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-01 | NON - DOT LET (LAP) | 2027-09-30 | Delivery |  |  |  |  | 40700000 | 2026-02-19
U-5805 | 10 | Charlotte Regional TPO | MECKLENBURG | INTERSECTION OF SR 1009 (MONROE ROAD) AT INTERSECTION OF SR1009 (MONROE ROAD) AND (RAMA ROAD/IDLEWILD ROAD). CONSTRUCTINTERSECTION IMPROVEMENTS. | Yes | 2023-10-03 | HIGHWAY - STI (PRIORITIZATION) | 2019-10-07 | NON - DOT LET (LAP) | 2026-09-01 | Delivery | 750000 | 2020-10-19 |  |  | 20300000 | 2026-02-20
U-5811 | 5 | Capital Area MPO | WAKE | SR 1002 (AVIATION PARKWAY) FROM NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTI-LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2026-11-20 | Raleigh Letting (LET) | 2029-07-17 | Delivery | 13000000 | 2024-03-04 | 2100000 | 2024-03-13 | 42200000 | 2024-03-13
U-5815A | 8 | Sandhills MPO | MOORE | US 1 (SANDHILLS BOULEVARD), SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-06-20 | Division POC Let (DPOC) | 2032-01-27 | Delivery | 4700000 | 2024-02-29 | 3200000 | 2023-11-20 | 12700000 | 2023-11-07
U-5816 | 12 | Charlotte Regional TPO | IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) FROM US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | Yes | 2026-04-22 | HIGHWAY - STI (PRIORITIZATION) | 2026-11-30 | Division Design Raleigh Let (DDRL) | 2029-05-15 | Delivery | 25700000 | 2025-07-28 | 3200000 | 2024-04-24 | 50200000 | 2026-04-22
U-5817 | 12 | Charlotte Regional TPO | IREDELL | SR 1246 (FAIRVIEW ROAD) EXTENSION OVER I-77 TO CONNECT WITHSR 1206 (ALCOVE ROAD). CONSTRUCT ROADWAY EXTENSION AND PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | Yes | 2024-02-27 | HIGHWAY - STI (PRIORITIZATION) | 2019-06-21 | Raleigh Letting (LET) | 2027-09-21 | Delivery | 5761137 | 2021-07-26 | 1300000 | 2024-03-19 | 25200000 | 2024-02-27
U-5821 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | NC 279 (NEW HOPE ROAD) FROM SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD) IN GASTONIA. WIDEN TO FOUR LANES. | Yes | 2024-07-23 | HIGHWAY - STI (PRIORITIZATION) | 2023-07-31 | Division Design Raleigh Let (DDRL) | 2028-03-21 | Delivery | 51200000 | 2021-08-19 | 17000000 | 2024-10-30 | 109800000 | 2024-07-23
U-5823 | 5 | Triangle West TPO | DURHAM | WOODCROFT PARKWAY EXTENSION. FROM SR 1116 (GARRETT ROAD) TONC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | Yes | 2024-07-31 | HIGHWAY - STI (PRIORITIZATION) | 2026-09-30 | NON - DOT LET (LAP) | 2027-10-13 | Delivery | 1500000 | 2026-07-10 | 400000 | 2026-07-10 | 11000000 | 2026-07-10
U-5825B | 5 | Capital Area MPO | WAKE | US 1 AT SR 1010 (TEN TEN ROAD) INTERCHANGE. RECONSTRUCT INTERCHANGE. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-07-05 | Division Design Raleigh Let (DDRL) | 2031-03-18 | Delivery | 30300000 | 2024-12-05 | 2300000 | 2024-11-19 | 66900000 | 2025-03-05
U-5834 | 13 | French Broad River MPO | BUNCOMBE | SR 3116 (MILLS GAP ROAD) FROM US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | Yes | 2025-05-05 | HIGHWAY - STI (PRIORITIZATION) | 2018-09-19 | Division Design Raleigh Let (DDRL) | 2028-01-18 | Delivery | 13000000 | 2025-01-29 | 4800000 | 2025-01-29 | 37600000 | 2025-05-05
U-5835 | 13 | Foothills RPO | MCDOWELL | US 221 BUSINESS FROM US 221/NC 226 TO GEORGIA AVENUE. WIDENEXISTING ROADWAY. | Yes | 2024-11-20 | HIGHWAY - STI (PRIORITIZATION) | 2024-02-08 | Division Design Raleigh Let (DDRL) | 2030-11-19 | Delivery | 7400000 | 2024-12-12 | 100000 | 2025-01-17 | 26300000 | 2024-11-20
U-5836 | 13 | Greater Hickory MPO | BURKE | NC 181 FROM SR 1414 (ST. MARY'S CHURCH ROAD) TO MORGANTON ETJ WIDEN EXISTING ROADWAY | Yes | 2025-01-15 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-12 | Division Design Raleigh Let (DDRL) | 2030-06-18 | Delivery | 3000000 | 2024-12-01 | 2000000 | 2025-01-15 | 13200000 | 2025-01-15
U-5841 | 7 | Greensboro Urban Area MPO | GUILFORD | FRIENDLY AVENUE FROM WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDEN ROADWAY AND CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | 2026-02-25 | HIGHWAY - STI (PRIORITIZATION) | 2019-06-11 | Division POC Let (DPOC) | 2026-11-19 | Delivery | 350000 | 2021-04-08 |  |  | 3100000 | 2026-06-18
U-5842 | 7 | Greensboro Urban Area MPO | GUILFORD | PISGAH CHURCH ROAD AT NORTH ELM STREET IN GREENSBORO INTERSECTION IMPROVEMENTS | Yes | 2026-09-18 | HIGHWAY - STI (PRIORITIZATION) | 2028-06-15 | NON - DOT LET (LAP) | 2031-09-18 | Delivery | 1800000 | 2023-08-07 | 1300000 | 2023-08-22 | 6400000 | 2023-08-23
U-5844 | 7 | Burlington-Graham MPO | ALAMANCE | NC 62 FROM SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON, WIDEN TO A THREE-LANE FACILITY. | Yes | 2026-02-02 | HIGHWAY - STI (PRIORITIZATION) | 2023-11-16 | Division Design Raleigh Let (DDRL) | 2027-03-16 | Delivery | 13300000 | 2022-06-08 | 1900000 | 2026-02-02 | 18500000 | 2026-02-02
U-5845 | 7 | Triangle West TPO | ORANGE | SR 1009 (SOUTH CHURTON STREET) FROM I-40 TO THE ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-07-16 | Raleigh Letting (LET) | 2033-07-19 | Delivery | 19700000 | 2024-09-06 | 7200000 | 2024-06-18 | 50500000 | 2024-07-12
U-5857A | 8 | Fayetteville Area MPO | HOKE | SR 1406; SR 1003 (ROCKFISH ROAD); SR 1413 (PITTMAN GROVE ROAD) TO NORTH OF WESTFIELD DRIVE. WIDEN TO MULTI-LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-03-19 | Raleigh Letting (LET) | 2033-09-20 | Delivery | 19100000 | 2026-05-28 | 2300000 | 2026-05-28 | 39000000 | 2026-05-28
U-5857B | 8 | Fayetteville Area MPO | HOKE | NEW ROUTE (GILLIS HILL ROAD) NORTH OF WESTFIELD DRIVE TO SR1788 (STEEPLE RUN DRIVE). CONSTRUCT MULTILANE ROADWAY ON NEW LOCATION. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-04-19 | Raleigh Letting (LET) | 2030-04-16 | Delivery | 19100000 | 2026-05-28 | 2300000 | 2026-05-28 | 51400000 | 2026-05-28
U-5860 | 2 | Mid-East RPO | BEAUFORT | SR 1306 (15TH STREET) FROM US 17 BUSINESS (CAROLINA AVENUE)TO BROWN STREET IN WASHINGTON. WIDEN TO MULTI-LANES | Yes | 2024-11-05 | HIGHWAY - STI (PRIORITIZATION) | 2026-06-26 | Division Design Raleigh Let (DDRL) | 2028-06-20 | Delivery | 18100000 | 2024-12-13 | 4200000 | 2024-11-19 | 37300000 | 2026-03-26
U-5862 | 3 | Grand Strand Area Transportation Study | BRUNSWICK | US 17 (FUTURE I-74; SHALLOTTE BYPASS) AT SR 1357 (SMITH AVENUE) INTERSECTION IN SHALLOTTE. UPGRADE INTERSECTION TO INTERCHANGE. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-09-20 | Division Design Raleigh Let (DDRL) | 2031-05-20 | Delivery | 8800000 | 2026-02-04 | 2000000 | 2026-03-20 | 45200000 | 2026-03-20
U-5864 | 8 | High Point Urban Area MPO | RANDOLPH | SR 1595/SR 4053 (SURRETT DRIVE) FROM I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | Not Yet | 2024-10-22 | HIGHWAY - STI (PRIORITIZATION) | 2029-02-19 | Division Design Raleigh Let (DDRL) | 2033-05-17 | Delivery | 28300000 | 2024-08-26 | 6700000 | 2024-10-21 | 44500000 | 2024-10-22
U-5886 | 14 | French Broad River MPO | HENDERSON | SR 1170 (WHITE STREET) FROM SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). (COMB W/U-6049). REALIGN AND EXTEND ROADWAY. | Yes | 2024-06-25 | HIGHWAY - STI (PRIORITIZATION) | 2022-12-16 | Division Design Raleigh Let (DDRL) | 2028-10-17 | Delivery | 21100000 | 2022-12-07 | 2900000 | 2023-01-25 | 18200000 | 2024-06-25
U-5889 | 5 | Capital Area MPO | WAKE | SR 1115 (AVENT FERRY ROAD) FROM SR 1116 (CASS HOLT ROAD) TONC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | Yes | 2024-05-20 | HIGHWAY - STI (PRIORITIZATION) | 2026-07-01 | NON - DOT LET (LAP) | 2028-07-03 | Delivery | 1400000 | 2024-04-30 | 490000 | 2024-05-20 | 15500000 | 2024-05-20
U-5890 | 5 | Kerr-Tar RPO | VANCE | SR 1162 (DABNEY DRIVE) FROM COOPER DRIVE TO US 158 BUSINESSIN HENDERSON. UPGRADE CORRIDOR. | Yes | 2024-09-30 | HIGHWAY - STI (PRIORITIZATION) | 2027-11-01 | Division Design Raleigh Let (DDRL) | 2031-11-18 | Delivery | 36000000 | 2024-05-05 | 5000000 | 2024-04-23 | 38900000 | 2024-09-30
U-5891 | 5 | Capital Area MPO | WAKE | NC 50 (CREEDMOOR ROAD) FROM I-540 TO NORTH OF NC 98. WIDEN TO MULTILANE DIVIDED ROADWAY | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-12-19 | Raleigh Letting (LET) | 2034-06-20 | Delivery | 143200000 | 2024-08-01 | 6300000 | 2026-03-17 | 143100000 | 2026-03-25
U-5892 | 7 | Greensboro Urban Area MPO | GUILFORD | US 220 (BATTLEGROUND AVENUE) FROM WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO ADD LANES | Yes | 2026-01-27 | HIGHWAY - STI (PRIORITIZATION) | 2027-08-11 | Division Design Raleigh Let (DDRL) | 2030-09-17 | Delivery | 15500000 | 2026-02-16 | 6300000 | 2026-02-06 | 28300000 | 2026-01-27
U-5901 | 9 | Cabarrus-Rowan MPO | ROWAN | NEW ROUTE (AIRPORT PARKWAY) FROM US 70/US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2538 (PEELER ROAD) AT US 29 IN SALISBURY. CONSTRUCT TWO-LANE ROADWAY. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-07-31 | Division Design Raleigh Let (DDRL) | 2034-01-17 | Delivery | 19600000 | 2024-08-15 | 7900000 | 2024-08-21 | 52100000 | 2024-07-08
U-5903 | 3 | Jacksonville Urban Area MPO | ONSLOW | SR 1336 (HENDERSON DRIVE) FROM SR 1308 (GUM BRANCH ROAD) TONC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE TO REDUCED CONFLICT INTERSECTION. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-07-19 | Division Design Raleigh Let (DDRL) | 2033-01-18 | Delivery | 5900000 | 2024-11-21 | 4200000 | 2024-11-14 | 38500000 | 2024-11-26
U-5911 | 4 | Rocky Mount Urban Area MPO | NASH | NC 48 AT NC 4 IN ROCKY MOUNT. CONSTRUCT ROUNDABOUT. | Yes | 2024-02-26 | HIGHWAY - STI (PRIORITIZATION) | 2025-10-28 | Division Design Raleigh Let (DDRL) | 2027-04-20 | Delivery | 30000 | 2024-03-14 | 360000 | 2024-04-12 | 8500000 | 2026-03-10
U-5917 | 2 | Greenville Urban Area MPO | PITT | SR 1704 (FOURTEENTH STREET) FROM RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO MULTI-LANES | Yes | 2024-10-29 | HIGHWAY - STI (PRIORITIZATION) | 2019-06-21 | Division Design Raleigh Let (DDRL) | 2028-03-21 | Delivery | 4322000 | 2021-05-17 | 1800000 | 2024-10-28 | 24700000 | 2024-10-29
U-5931 | 10 | Charlotte Regional TPO | UNION | US 74 AT SR 1501 (SECREST SHORTCUT ROAD) IN MONROE. CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-06-30 | Division Design Raleigh Let (DDRL) | 2030-06-18 | Delivery | 4531000 | 2024-10-25 | 520000 | 2024-05-01 | 8800000 | 2024-05-01
U-5934 | 5 | Triangle West TPO | DURHAM | I-885 FROM I-40 TO NC 147 IN DURHAM. ADD LANES, REHABILITATE PAVEMENT, AND INSTALL TRANSIT ACCOMMODATIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-09-13 | Raleigh Letting (LET) | 2031-04-15 | Delivery | 0.01 | 2025-04-02 | 3300000 | 2026-03-12 | 226900000 | 2026-02-24
U-5939 | 1 | Albemarle RPO | PASQUOTANK | US 17 BUSINESS TO SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | Yes | 2024-06-27 | HIGHWAY - STI (PRIORITIZATION) | 2025-05-12 | Division Design Raleigh Let (DDRL) | 2028-03-21 | Delivery | 5400000 | 2024-09-23 | 530000 | 2024-07-30 | 19200000 | 2025-02-25
U-5940 | 1 | Albemarle RPO | PASQUOTANK | US 17 (HUGHES BOULEVARD) FROM SR 1308 (CHURCH STREET) TO US17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-03-08 | Division Design Raleigh Let (DDRL) | 2031-03-18 | Delivery | 18500000 | 2026-03-26 | 8400000 | 2026-03-06 | 23800000 | 2026-02-05
U-5941 | 4 | Upper Coastal Plain RPO | WILSON | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) FROM SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETYIMPROVEMENTS. | Yes | 2026-05-06 | HIGHWAY - STI (PRIORITIZATION) | 2027-12-01 | Division Design Raleigh Let (DDRL) | 2031-05-20 | Delivery | 5600000 | 2026-01-02 | 4800000 | 2026-05-06 | 16700000 | 2025-11-24
U-5945 | 4 | Upper Coastal Plain RPO | WILSON | WILSON CITY -SIGNAL SYSTEM | Yes | 2025-05-21 | HIGHWAY - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2026-08-25 | Delivery |  |  | 2600000 | 2025-12-03 | 3600000 | 2025-05-21
U-5949 | 3 | Jacksonville Urban Area MPO | ONSLOW | NC 210 FROM US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD).WIDEN TO MULTI-LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-07-26 | Division Design Raleigh Let (DDRL) | 2034-06-20 | Delivery | 33200000 | 2024-12-23 | 15400000 | 2024-10-08 | 115400000 | 2024-10-08
U-5951 | 3 | Jacksonville Urban Area MPO | ONSLOW | US 17 AT US 17 BUSINESS (MARINE BOULEVARD) IN JACKSONVILLE.UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | Yes | 2026-03-04 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-12 | Division Design Raleigh Let (DDRL) | 2029-03-20 | Delivery | 2400000 | 2026-03-06 | 280000 | 2026-01-23 | 27200000 | 2026-03-04
U-5952 | 2 | Greenville Urban Area MPO | PITT | GREENVILLE - SIGNAL SYSTEM | Yes | 2024-06-21 | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2027-11-16 | Delivery |  |  | 750000 | 2024-06-21 | 13100000 | 2024-06-21
U-5955B | 10 | Charlotte Regional TPO | MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) AT IDAHO DRIVE IN CHARLOTTE. CONVERT INTERSECTION TO AN INTERCHANGE. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-03-18 | Division Design Raleigh Let (DDRL) | 2033-03-15 | Delivery | 2300000 | 2026-02-23 | 1100000 | 2023-03-02 | 23500000 | 2026-02-23
U-5957 | 10 | Charlotte Regional TPO | MECKLENBURG | NC 27 (FREEDOM DRIVE) FROM SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD) IN CHARLOTTE. WIDEN TO FOUR LANES. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-06-28 | Division Design Raleigh Let (DDRL) | 2033-10-18 | Delivery | 15900000 | 2024-11-19 | 2200000 | 2025-05-01 | 28800000 | 2024-08-21
U-5961 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | NC 274 (UNION ROAD) FROM OSCEOLA STREET TO NIBLICK DRIVE UPGRADE ROADWAY | Yes | 2024-08-21 | HIGHWAY - STI (PRIORITIZATION) | 2028-06-30 | Division Design Raleigh Let (DDRL) | 2030-11-19 | Delivery | 25500000 | 2025-01-24 | 4100000 | 2024-11-01 | 24000000 | 2024-08-21
U-5965 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | US 29 (FRANKLIN BOULEVARD) AT NC 274 (BESSEMER CITY ROAD) /SR 2466 (WEST GARRISON BOULEVARD) IN GASTONIA. CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | 2026-03-30 | HIGHWAY - STI (PRIORITIZATION) | 2022-12-28 | Division Design Raleigh Let (DDRL) | 2027-04-20 | Delivery | 690000 | 2022-08-18 | 240000 | 2024-04-30 | 5300000 | 2026-03-30
U-5967 | 5 | Capital Area MPO | WAKE | TOWN OF MORRISVILLE CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM | Not Yet | 2025-04-22 | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2028-03-21 | Delivery |  |  |  |  | 560000 | 2025-04-22
U-5969B | 5 | Kerr-Tar RPO | PERSON | US 501, FROM 157 TO SR 1596 (WEST MOREHEAD STREET) CONVERT TO 4-LANE MEDIAN DIVIDED FACILITY, IMPROVE VARIOUS INTERSECTIONS WITH SOME CONSOLIDATION OF INTERSECTIONS, AND FILL IN SIDEWALK GAPS. | Yes | 2025-05-28 | HIGHWAY - STI (PRIORITIZATION) | 2029-05-18 | Division Design Raleigh Let (DDRL) | 2031-06-17 | Delivery | 7900000 | 2024-11-09 | 200000 | 2024-11-22 | 15100000 | 2025-05-28
U-5974A | 7 | High Point Urban Area MPO | GUILFORD | NC 68, SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLARD DAIRY ROAD) IN HIGH POINT. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-05-05 | Division Design Raleigh Let (DDRL) | 2031-03-18 | Delivery | 16300000 | 2026-03-31 | 4700000 | 2026-03-31 | 56605000 | 2026-03-31
U-5974B | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | GUILFORD | NC 68, SR 1823 ( WILLARD DAIRY ROAD) TO AMERICHASE DRIVE INHIGH POINT. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2031-05-06 | Division Design Raleigh Let (DDRL) | 2034-03-21 | Delivery
U-5975 | 8 | Central Pines RPO | LEE | US 1 / US 15 / US 501 INTERSECTIONS FROM US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE) SOUTH OF SANFORD. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | Yes | 2025-11-13 | HIGHWAY - STI (PRIORITIZATION) | 2022-12-05 | Division Design Raleigh Let (DDRL) | 2028-01-18 | Delivery | 4071000 | 2021-07-19 | 3300000 | 2023-02-27 | 40900000 | 2025-11-13
U-5975A | 8 | Central Pines RPO | LEE | US 1 / US 15 / US 501, US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). CLEARING, GRUBBING, AND EROSION CONTROL. | Yes | 2025-09-19 | HIGHWAY - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2026-08-11 | Delivery |  |  |  |  | 2500000 | 2025-09-19
U-5976 | 8 | Sandhills MPO | MOORE | US 15 / 501, AT NC 2 (MIDLAND ROAD), NC 211 (YADKIN ROAD), SR 1895 (MIDLAND ROAD) INTERSECTION IN PINEHURST, (PINEHURSTTRAFFIC CIRCLE). UPGRADE TRAFFIC CIRCLE AND APPROACHES. | Not Yet | 2024-09-19 | HIGHWAY - STI (PRIORITIZATION) | 2027-08-20 | Division Design Raleigh Let (DDRL) | 2031-05-20 | Delivery | 28900000 | 2024-11-20 | 970000 | 2024-09-18 | 51100000 | 2024-09-19
U-5993 | 2 | New Bern Area MPO | CRAVEN | NC 55 (NEUSE BOULEVARD)AT US 17 BUSINESS (MLK). CONSTRUCT ROUNDABOUT. | Yes | 2024-09-17 | HIGHWAY - STI (PRIORITIZATION) | 2027-06-01 | Division POC Let (DPOC) | 2029-06-13 | Delivery | 3100000 | 2026-02-16 | 1300000 | 2024-10-29 | 5700000 | 2024-09-17
U-5998 | 4 | Capital Area MPO, Upper Coastal Plain RPO | JOHNSTON | NC 42, FROM SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | Yes | 2026-06-29 | HIGHWAY - STI (PRIORITIZATION) | 2025-08-11 | Division Design Raleigh Let (DDRL) | 2027-08-17 | Delivery | 3300000 | 2024-08-27 | 2100000 | 2024-05-16 | 30100000 | 2026-06-29
U-6004 | 9 | Winston-Salem Area TPO | FORSYTH | SR 1103 (LEWISVILLE-CLEMMONS ROAD) FROM US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS | Yes | 2024-02-06 | HIGHWAY - STI (PRIORITIZATION) | 2024-09-20 | Division Design Raleigh Let (DDRL) | 2029-10-16 | Delivery | 33600000 | 2024-02-14 | 3000000 | 2024-01-29 | 32700000.01 | 2024-02-06
U-6006 | 8 | Piedmont Triad RPO | RANDOLPH | US 220 BUSINESS, FROM SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | Yes | 2026-07-15 | HIGHWAY - STI (PRIORITIZATION) | 2023-07-21 | Division Design Raleigh Let (DDRL) | 2028-06-20 | Delivery | 1000000 | 2023-01-24 | 2748000 | 2023-01-24 | 18100000 | 2026-07-15
U-6009 | 7 | Burlington-Graham MPO | ALAMANCE | US 70 (SOUTH CHURCH STREET), FROM TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-03-17 | Division Design Raleigh Let (DDRL) | 2030-01-15 | Delivery | 2500000 | 2025-09-04 | 2100000 | 2025-05-01 | 20300000 | 2024-06-20
U-6013 | 7 | Burlington-Graham MPO | ALAMANCE | NC 119 FROM SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126(OLD HILLSBOROUGH ROAD) TO LOWES BOULEVARD IN MEBANE. WIDENTO MULTILANES. | Yes | 2026-01-29 | HIGHWAY - STI (PRIORITIZATION) | 2022-07-13 | Division Design Raleigh Let (DDRL) | 2027-08-17 | Delivery | 5500000 | 2022-06-23 | 900000 | 2021-07-01 | 10600000 | 2026-07-14
U-6014 | 7 | Burlington-Graham MPO | ALAMANCE | SR 1716 (GRAHAM-HOPEDALE ROAD) FROM SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BICYCLE/PEDESTRIAN ACCOMMODATIONS. | Yes | 2025-12-04 | HIGHWAY - STI (PRIORITIZATION) | 2023-02-13 | Division Design Raleigh Let (DDRL) | 2027-02-16 | Delivery | 1500000 | 2023-10-02 | 1200000 | 2023-10-02 | 19200000 | 2025-12-04
U-6027 | 8 | Lumber River RPO | RICHMOND | WIDEN AND ENHANCE SR 1516 (GREENE STREET) FROM US 220 TO US1 AND RE-ROUTE US 1 ONTO GREEN STREET TO REDUCE HEAVY TRUCKTRAFFIC IN DOWNTOWN ROCKINGHAM. | Yes | 2024-11-15 | HIGHWAY - STI (PRIORITIZATION) | 2025-03-27 | Division Design Raleigh Let (DDRL) | 2028-06-20 | Delivery | 2200000 | 2024-09-26 | 1300000 | 2024-09-16 | 8100000 | 2024-11-15
U-6032 | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | CABARRUS | SR 2467 (MALLARD CREEK ROAD) FROM I-485 TO THE CABARRUS COUNTY LINE AND SR 1445 (DERITA ROAD) FROM THE COUNTY LINE TO SR 2894 (CONCORD MILLS BOULEVARD) IN CHARLOTTE. WIDEN TO SIX LANES. | Yes | 2026-05-06 | HIGHWAY - STI (PRIORITIZATION) | 2021-06-25 | Division Design Raleigh Let (DDRL) | 2029-03-20 | Delivery | 14358000 | 2021-06-25 | 2514000 | 2021-06-25 | 38200000 | 2026-05-06
U-6034 | 11 | Greater Hickory MPO | CALDWELL | US 321 ALTERNATE FROM SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET) IN GRANITE FALLS. UPGRADE ROADWAY. | Yes | 2024-11-07 | HIGHWAY - STI (PRIORITIZATION) | 2025-07-24 | Division Design Raleigh Let (DDRL) | 2028-11-21 | Delivery | 16000000 | 2025-04-24 | 3000000 | 2025-04-21 | 29400000 | 2026-08-27
U-6043 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | US 29 / US 74 (FRANKLIN BOULEVARD) FROM SR 2200 (COX ROAD) TO EAST OF LINEBERGER ROAD IN GASTONIA. CONSTRUCT ADDITIONALEASTBOUND LANE. | Yes | 2025-03-04 | HIGHWAY - STI (PRIORITIZATION) | 2023-01-31 | Division Design Raleigh Let (DDRL) | 2027-01-19 | Delivery | 1300000 | 2022-10-25 | 860000 | 2025-03-04 | 7900000 | 2025-03-04
U-6044 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | SR 2200 (COX ROAD)FROM I-85 TO US 29/74 SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS (COMB W/I-5719 AND U-5800). | Yes | 2024-09-18 | HIGHWAY - STI (PRIORITIZATION) | 2028-11-21 | Design Build Let (DBL) | 2028-11-21 | Delivery | 49500000 | 2024-11-01 | 1500000 | 2023-08-23 | 14300000 | 2024-09-18
U-6048 | 14 | French Broad River MPO | HAYWOOD | US 19/23 FROM SR 1836(CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD. UPGRADE ROADWAY | Yes | 2024-07-31 | HIGHWAY - STI (PRIORITIZATION) | 2029-07-19 | Division Design Raleigh Let (DDRL) | 2033-01-18 | Delivery | 1000000.01 | 2025-04-30 | 700000 | 2024-08-29 | 41600000 | 2024-07-31
U-6049 | 14 | French Broad River MPO | HENDERSON | BRIDGE 440143 OVER MUD CREEK ON US 25 BUSINESS (SOUTH MAIN STREET) AND US 25 BUSINESS FROM SOUTH MAIN STREET / SOUTH KING STREET TO US 276 IN HENDERSONVILLE. WIDEN BRIDGE TO FIVE LANES. | Yes | 2024-06-25 | HIGHWAY - STI (PRIORITIZATION) | 2022-12-16 | Division Design Raleigh Let (DDRL) | 2028-10-17 | Delivery | 2600000 | 2022-12-07 | 360000 | 2023-01-25 | 8800000 | 2024-06-25
U-6073 | 6 | Fayetteville Area MPO | CUMBERLAND | SR 1107 (FISHER ROAD) CUMBERLAND COUNTY FROM STRICKLAND BRIDGE ROAD TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | Yes | 2023-10-02 | HIGHWAY - STI (PRIORITIZATION) | 2029-10-01 | Division Design Raleigh Let (DDRL) | 2032-10-19 | Delivery | 33400000 | 2025-02-28 | 6500000 | 2024-12-20 | 42700000 | 2026-02-17
U-6078 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | NC 275 AT NC 274 (BESSEMER CITY ROAD); NC 275 AT SR 1327 (FAIRVIEW ROAD) AND SR 1456 (WHITE JENKINS ROAD) IN GASTONIA.CONSTRUCT INTERSECTION IMPROVEMENTS AND CLOSE INTERSECTION AT NC 275 AND SR 1456 (WHITE JENKINS ROAD). | Yes | 2025-09-03 | HIGHWAY - STI (PRIORITIZATION) | 2025-02-28 | Division Design Raleigh Let (DDRL) | 2027-07-20 | Delivery | 1400000 | 2024-11-14 | 780000 | 2024-10-14 | 7400000 | 2026-06-24
U-6082 | 3 | Jacksonville Urban Area MPO | ONSLOW | SR 1308 (BELL FORK ROAD) TO SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-04-11 | Division Design Raleigh Let (DDRL) | 2031-08-19 | Delivery | 2800000 | 2025-02-13 | 1100000 | 2025-01-21 | 12900000 | 2025-01-31
U-6103 | 10 | Charlotte Regional TPO | MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANE. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-31 | Raleigh Letting (LET) | 2033-04-19 | Delivery | 12000000 | 2024-04-30 | 8100000 | 2024-05-01 | 248500000 | 2024-05-15
U-6109 | 10 | Charlotte Regional TPO | MECKLENBURG | US 521 (LANCASTER HWY/JOHNSTON ROAD)FROM SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2030-03-19 | Division Design Raleigh Let (DDRL) | 2034-08-15 | Delivery | 11900000 | 2024-05-24 | 2100000 | 2024-05-24 | 52900000 | 2024-05-31
U-6110 | 4 | Goldsboro Urban Area MPO | WAYNE | US 70 AT SR 1711(NORTH OAK FOREST ROAD) IN GOLDSBORO. CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | 2026-02-12 | HIGHWAY - STI (PRIORITIZATION) | 2025-07-18 | Division Design Raleigh Let (DDRL) | 2027-08-17 | Delivery | 1300000 | 2024-03-28 | 280000 | 2024-03-06 | 13600000 | 2026-02-12
U-6111 | 4 | Upper Coastal Plain RPO | WILSON | NC 58 (NASH STREET) AT SR 1330 (AIRPORT RD)/ SR 1332 (LAKE WILSON RD) IN WILSON. CONSTRUCT INTERSECTION IMPROVEMENTS. | Yes | 2026-06-04 | HIGHWAY - STI (PRIORITIZATION) | 2027-10-14 | Division Design Raleigh Let (DDRL) | 2030-09-17 | Delivery | 2900000 | 2026-05-13 | 790000 | 2026-06-03 | 9500000 | 2026-06-04
U-6114 | 7 | Burlington-Graham MPO | ALAMANCE | NC 62 (ALAMANCE ROAD) ALAMANCE COUNTY AT SR 1155 (HATCHERY ROAD)/ BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNALS AND ADD TURN LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-06-16 | Division Design Raleigh Let (DDRL) | 2031-06-17 | Delivery | 770000 | 2024-12-20 | 270000 | 2024-12-10 | 1800000 | 2024-11-21
U-6117 | 5 | Capital Area MPO | WAKE | APEX TOWNWIDE SIGNAL SYSTEM | Not Yet | 2026-02-11 | HIGHWAY - STI (PRIORITIZATION) | 2027-04-19 | Raleigh Letting (LET) | 2027-10-19 | Delivery | 10000 | 2026-06-23 | 350000 | 2026-06-23 | 8500000 | 2026-06-23
U-6119 | 5 | Capital Area MPO | WAKE | RALEIGH CITYWIDE SIGNAL SYSTEM | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2030-01-15 | Delivery |  |  |  |  | 5400000 | 2026-02-11
U-6120B | 5 | Triangle West TPO | DURHAM | NC 98 (HOLLOWAY STREET), SR 1919 (LYNN ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES, SAFETY IMPROVEMENTS, AND PEDESTRIAN ACCOMMODATIONS. | Yes | 2025-08-05 | HIGHWAY - STI (PRIORITIZATION) | 2028-09-15 | Division POC Let (DPOC) | 2030-09-25 | Delivery | 700000 | 2025-08-08 |  |  | 8100000 | 2025-08-05
U-6128 | 3 | Wilmington Urban Area MPO | NEW HANOVER | US 76 (OLEANDER DRIVE) AT GREENVILLE LOOP ROAD / GREENVILLEAVENUE IN WILMINGTON. CONSTRUCT INTERSECTION IMPROVEMENTS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-06-17 | Division POC Let (DPOC) | 2030-06-20 | Delivery | 2600000 | 2026-04-01 | 1100000 | 2026-05-07 | 6700000 | 2026-05-14
U-6131 | 7 | Burlington-Graham MPO | ALAMANCE | NC 54 (WEST HARDEN STREET)AT NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-01-13 | Division POC Let (DPOC) | 2030-01-17 | Delivery | 11700000 | 2024-11-08 | 1100000 | 2024-12-10 | 7400000 | 2024-10-24
U-6134 | 12 | Gaston-Cleveland-Lincoln MPO | LINCOLN | NC 16 BYPASS AT SR 1380 (OPTIMIST CLUB ROAD)INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE | Yes | 2024-07-26 | HIGHWAY - STI (PRIORITIZATION) | 2024-08-26 | Division Design Raleigh Let (DDRL) | 2031-01-21 | Delivery | 500000 | 2023-10-04 | 100000 | 2023-10-04 | 46800000 | 2024-07-26
U-6146 | 12 | Gaston-Cleveland-Lincoln MPO | GASTON | US 29/US 74 (WILKINSON BOULEVARD)FROM MARKET STREET TO SR 2015 (ALBERTA AVENUE). (COMB W/B-5857). | Yes | 2026-07-06 | HIGHWAY - STI (PRIORITIZATION) | 2021-07-14 | Division Design Raleigh Let (DDRL) | 2026-11-17 | Delivery | 7800000 | 2021-06-14 | 5500000 | 2021-08-02 | 32000000 | 2026-07-06
U-6157 | 11 | Greater Hickory MPO | CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) FROM SR 1001 (CONNELLY SPRINGS ROAD) TO US 321 ALTERNATE IN SAWMILLS. MODERNIZE ROADWAY. | Yes | 2024-10-29 | HIGHWAY - STI (PRIORITIZATION) | 2025-02-11 | Division Design Raleigh Let (DDRL) | 2028-10-17 | Delivery | 13000000 | 2024-05-15 | 10200000 | 2023-10-03 | 45100000 | 2024-10-29
U-6161 | 11 | Greater Hickory MPO | CALDWELL | US 321 FROM SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-03-01 | Division Design Raleigh Let (DDRL) | 2028-03-21 | Delivery | 2000000 | 2025-04-03 | 270000 | 2024-10-16 | 6300000 | 2024-08-22
U-6163 | 13 | French Broad River MPO | BUNCOMBE | SR 3116 (MILLS GAP ROAD) AT SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT | Yes | 2023-10-04 | HIGHWAY - STI (PRIORITIZATION) |  | Division POC Let (DPOC) | 2027-04-01 | Delivery |  |  |  |  | 2400000 | 2023-10-04
U-6188 | 9 | Winston-Salem Area TPO | FORSYTH | SR 1969 (PINEY GROVE ROAD)FROM NORTH OF NELSON STREET TO SR2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO THREE LANES WITH BICYCLE/PEDESTRIAN ACCOMMODATIONS | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-11-20 | Division Design Raleigh Let (DDRL) | 2030-02-19 | Delivery | 2200000 | 2024-02-05 | 500000 | 2024-02-26 | 6800000 | 2024-02-27
U-6189 | 9 | Winston-Salem Area TPO | FORSYTH | SR 1156 (LEWISVILLE- CLEMMONS ROAD) FROM SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDENTO 3 LANES BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-07-31 | Division Design Raleigh Let (DDRL) | 2033-01-18 | Delivery | 14600000 | 2024-09-10 | 3300000 | 2024-09-30 | 27000000 | 2024-10-03
U-6190 | 9 | Winston-Salem Area TPO | FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) FROM SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-08-31 | Division Design Raleigh Let (DDRL) | 2030-03-19 | Delivery | 2900000 | 2024-02-07 | 900000 | 2024-03-15 | 3800000 | 2024-03-15
U-6191 | 8 | High Point Urban Area MPO | RANDOLPH | NC 62 FROM SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-06-01 | Division Design Raleigh Let (DDRL) | 2034-04-18 | Delivery | 21400000 | 2024-11-05 | 12400000 | 2024-10-10 | 30000000 | 2024-10-11
U-6194 | 5 | Capital Area MPO | WAKE | VARIOUS, GARNER CITYWIDE SIGNAL SYSTEM | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) |  | Raleigh Letting (LET) | 2031-01-21 | Delivery |  |  | 480000 | 2026-02-11 | 9300000 | 2026-02-11
U-6197 | 2 | Greenville Urban Area MPO | PITT | SR 1711 (WORTHINGTON ROAD) AT SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-02-15 | Division POC Let (DPOC) | 2029-06-13 | Delivery | 1300000 | 2024-11-18 | 730000 | 2024-11-01 | 3100000 | 2024-11-04
U-6199 | 3 | Wilmington Urban Area MPO | NEW HANOVER | VARIOUS, WILMINGTON CITYWIDE SIGNAL SYSTEM | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2027-07-16 | Division Design Raleigh Let (DDRL) | 2030-01-15 | Delivery | 100000 | 2026-05-22 | 1200000 | 2026-05-22 | 18700000 | 2026-05-22
U-6203 | 4 | Capital Area MPO | JOHNSTON | NC 210 FROM NC 50 TO SR 1330 (RALEIGH ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | Yes | 2024-07-24 | HIGHWAY - STI (PRIORITIZATION) | 2026-10-19 | Division Design Raleigh Let (DDRL) | 2029-10-16 | Delivery | 12800000 | 2024-09-25 | 4000000 | 2024-07-24 | 71600000 | 2024-07-24
U-6204 | 4 | Goldsboro Urban Area MPO | WAYNE | SR SR 1556 (WAYNE MEMORIAL DRIVE) FROM SR 1569 (COUNTRY DAY ROAD) TO SR 1003 (NEW HOPE ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | Yes | 2026-08-06 | HIGHWAY - STI (PRIORITIZATION) | 2026-08-10 | Division Design Raleigh Let (DDRL) | 2028-07-18 | Delivery | 4100000 | 2024-10-03 | 2000000 | 2026-01-28 | 25100000 | 2024-10-25
U-6205 | 4 | Goldsboro Urban Area MPO | WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) FROM US 70 BYPASS TO SR 1547(STONEY CREEK ROAD). WIDEN ROADWAY. | Yes | 2024-05-15 | HIGHWAY - STI (PRIORITIZATION) | 2027-01-04 | Division Design Raleigh Let (DDRL) | 2029-03-20 | Delivery | 70000 | 2025-12-31 | 420000 | 2026-02-19 | 2500000 | 2025-12-18
U-6206 | 4 | Goldsboro Urban Area MPO | WAYNE | SR 1713 (MILLER'S CHAPEL ROAD) WAYNE COUNTY FROM US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | Yes | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2028-10-16 | Division Design Raleigh Let (DDRL) | 2030-09-17 | Delivery | 9200000 | 2024-08-21 | 2500000 | 2024-11-06 | 10900000 | 2024-10-10
U-6208 | 4 | Capital Area MPO | JOHNSTON | NEW ROUTE FROM SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCTROADWAY ON NEW LOCATION. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-15 | Raleigh Letting (LET) | 2033-09-20 | Delivery | 19500000 | 2024-08-26 | 3900000 | 2024-08-26 | 33100000 | 2024-08-26
U-6216 | 4 | Capital Area MPO | JOHNSTON | SR 1010 (CLEVELAND ROAD) FROM NORTH OF SR 2231 (SOUTHFORT DRIVE) TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | Not Yet | Not Yet | HIGHWAY - STI (PRIORITIZATION) | 2029-10-15 | Division Design Raleigh Let (DDRL) | 2035-09-18 | Delivery | 36600000 | 2024-10-08 | 6300000 | 2024-11-20 | 100900000 | 2024-10-21