## Project Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | MPO | IDNUM | PROJ_ID | DESCRIPTION | AGENDA_COMMENT | FUNDING_COMMENT | FEDERAL_AMENDMENT | CATEGORY
2024-11-07 | FINAL | ADDITION | RALEIGH | HB-0072 | HB-0072 | SR 1629 (FLAT ROCK ROAD), REPLACE BRIDGE 380199 OVER FORK CREEK. | ADD PROJECT AT THE REQUEST OF THE STRUCTURES MANAGEMENT UNIT. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. |  | Y | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | EB-6016 | EB-6016 | EAST CLAYTON CONNECTOR GREENWAY, SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | ADD UTILITY PHASE IN FY 27 NOT PREVIOUSLY PROGRAMMED. |  | N | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HL-0008J | HL-0008 | NC 50, NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 24 TO FY 25 AND DELAY UTILITIES AND CONSTRUCTION FROM FY 25 TO FY 26. |  | N | EX
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405AI | HS-2405 | SR 3008 (EDENTON STREET), HARRINGTON STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO RALEIGH SIGNAL SYSTEM. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405AJ | HS-2405 | SR 1152 (HOLLY SPRINGS ROAD), SR 4089 (WINDING OAK WAY)/YMCA DRIVEWAY. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMODATIONS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405AK | HS-2405 | SR 1004 (GARNER ROAD), SR 2684 (TRYON ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL, AND INSTALL PEDESTRIAN SIGNALS, CURB RAMPS, AND CROSSWALKS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405AL | HS-2405 | NC 96 (EAST MAIN STREET), CROSS STREET INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405AN | HS-2405 | SR 3009 (EDWARDS MILL ROAD), SR 1728 (WADE AVENUE) RAMPS. UPGRADE TRAFFIC SIGNAL, INSTALL PEDESTRIAN SIGNALS, AND INSTALL RECTANGULAR RAPID FLASHING BEACONS AT SLIP RAMPS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405AQ | HS-2405 | SR 1835 (PINECREST ROAD), GROVE BARTON ROAD/TOSCANA DRIVE INTERSECTION. INSTALL TRAFFIC SIGNAL AND INTERSECTION PEDESTRIAN IMPROVEMENTS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405C | HS-2405 | VARIOUS, US 401 IN FRANKLIN COUNTY. NC 42 IN WAKE COUNTY. NC 56 IN FRANKLIN AND GRANVILLE COUNTY. NC 96 IN WAKE AND GRANVILLE COUNTY. SR 1006 IN WAKE COUNTY AND NC 50 IN WAKE AND GRANVILLE COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 24 TO FY 25. |  | N | REG
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405D | HS-2405 | SR 1656 (TRINITY ROAD), SR 1656 (TRINITY ROAD) AT SR 3009 (EDWARDS MILL ROAD). UPGRADE TRAFFIC SIGNAL TO PROVIDE PEDESTRIAN ACCOMMODATIONS AND CROSSWALKS. | ADD UTILITIES PHASE IN FY 25 NOT PREVIOUSLY PROGRAMMED. |  | Y | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405G | HS-2405 | SR 1349 (DILLARD DRIVE), SR 1349 (DILLARD DRIVE) AT DILLARD DRVIE MIDDLE SCHOOL / ORABELLE COURT. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY AND CONSTRUCTION FROM FY 24 TO FY 25. |  | N | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | HS-2405L | HS-2405 | VARIOUS, ALL FREEWAY RAMP LOCATIONS IN DIVISION 5. BRING WRONG WAY DRIVER DETERRENCE MARKINGS UP TO STANDARD. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 24 TO FY 25. |  | N | SW
2024-11-07 | FINAL | MODIFICATION | RALEIGH | R-5705A | R-5705 | NC 55, JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | PROJECT TO UTILIZE BUILD NC BONDS FOR CONSTRUCTION. |  | N | DIV
2024-11-07 | FINAL | MODIFICATION | RALEIGH | U-5826 | U-5826 | SR 2000 (FALLS OF NEUSE ROAD), I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | PROJECT TO UTILIZE BUILD NC BONDS FOR CONSTRUCTION. |  | N | DIV
2024-12-05 | FINAL | ADDITION | RALEIGH | HO-0019 | HO-0019 | VARIOUS, INSTALL EV CHARGERS AT MULTIPLE COMMUNITY COLLEGES: BLUE RIDGE COMMUNITY COLLEGE CENTRAL CAROLINA COMMUNITY COLLEGE EDGECOMBE COMMUNITY COLLEGE FAYETTEVILLE COMMUNITY COLLEGE GASTON COLLEGE MARTIN COMMUNITY COLLEGE NASH COMMUNITY COLLEGE RANDOLPH | ADD PROJECT DUE TO AWARD OF FEDERAL GRANT. DP FUNDS REPRESENT FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. |  | Y | EX
2024-12-05 | FINAL | ADDITION | RALEIGH | TG-0027 | TG-0027 | CONSTRUCT 11 BUS STOPS. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | N | PT
2024-12-05 | FINAL | DELETION | RALEIGH | C-4924 | C-4924 | TRIANGLE J COUNCIL OF GOVERNMENTS, TRIANGLE J COUNCIL OF GOVERNMENTS (COG). TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN TRIANGLE OZONE NON-ATTAINMENT AREA. | REMOVE PROJECT AT THE REQUEST OF THE MPO. PROJECT NOW FUNDED UNDER HN-0026. |  | Y | EX
2024-12-05 | FINAL | DELETION | RALEIGH | C-4924A | C-4924 | TRIANGLE J COUNCIL OF GOVERNMENTS, TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) | REMOVE PROJECT AT THE REQUEST OF THE MPO. PROJECT NOW FUNDED UNDER HN-0026A. |  | Y | EX
2024-12-05 | FINAL | DELETION | RALEIGH | C-4924B | C-4924 | TRIANGLE J COUNCIL OF GOVERNMENTS, TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) | REMOVE PROJECT AT THE REQUEST OF THE MPO. PROJECT NOW FUNDED UNDER HN-0026B. |  | Y | EX
2024-12-05 | FINAL | MODIFICATION | RALEIGH | HN-0026A | HN-0026 | CENTRAL PINES REGIONAL COUNCIL, TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) | ADD ADDITIONAL IMPLEMENTATION FUNDING IN FY 25, FY 26, AND FY 27 NOT PREVIOUSLY PROGRAMMED AT THE REQUEST OF THE MPO. |  | Y | EX
2024-12-05 | FINAL | MODIFICATION | RALEIGH | HS-2405AR | HS-2405 | VARIOUS, DOWNTOWN RALEIGH PEDESTRIAN STUDY PHASE II. PEDESTRIAN IMPROVEMENTS AT MULTIPLE EXISTING CROSSWALKS INCLUDING PEDESTRIAN CURB EXTENSIONS, RAISED CROSSWALKS, AND MEDIAN REFUGE ISLANDS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION |  | Y | DIV
2024-12-05 | FINAL | MODIFICATION | RALEIGH | HS-2405AS | HS-2405 | US 1 (CAPITAL BOULEVARD), CALVARY DRIVE INTERSECTION. CONSTRUCT SIGNAL AND CROSSWALK UPGRADES AND INSTALL MEDIAN FENCE. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION |  | Y | SW
2024-12-05 | FINAL | MODIFICATION | STATEWIDE | TO-0004 | TO-0004 | STATEWIDE, SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. | MODIFY FUNDS AT THE REQUEST OF THE INTEGRATED MOBILITY DIVISION. |  | N | PT

## MPORPO
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | IDNUM | MPO_PERCENT | OFFICIAL_NAME
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | ADDITION | HB-0072 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HL-0008J | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405AI | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405AJ | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405AK | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405AL | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405AN | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405AQ | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405C | 70 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405C | 30 | KERR TAR RURAL PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405D | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405G | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405L | 50 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405L | 40 | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | HS-2405L | 10 | KERR TAR RURAL PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | R-5705A | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-11-07 | FINAL | MODIFICATION | U-5826 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | DELETION | C-4924 | 50 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | DELETION | C-4924 | 50 | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | DELETION | C-4924A | 50 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | DELETION | C-4924A | 50 | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | DELETION | C-4924B | 50 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | DELETION | C-4924B | 50 | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | MODIFICATION | HN-0026A | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 10 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | CENTRAL PINES RURAL PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | FAYETTEVILLE URBANIZED AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | GASTON CLEVELAND LINCOLN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | LAND OF SKY RURAL PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | MID-CAROLINA RURAL PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | PEANUT BELT RURAL PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | PIEDMONT TRIAD RURAL PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | ROCKY MOUNT METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | HO-0019 | 9 | UPPER COASTAL PLAIN RURAL PLANNING ORGANIZATION
2024-12-05 | FINAL | MODIFICATION | HS-2405AR | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | MODIFICATION | HS-2405AS | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | ADDITION | TG-0027 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2024-12-05 | FINAL | MODIFICATION | TO-0004 | 100 | STATEWIDE PROJECT

## Funding Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | PROJ | SORT_SEQUENCE | Activity | Year | FUND_SOURT_SEQ | FUND | AMNT
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 1 | ENGINEERING | FY 2026 - | 28 | (TAANY) | 206000
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 1 | ENGINEERING | FY 2026 - | 36 | (L(M)) | 52000
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 7 | RIGHT-OF-WAY | FY 2027 - | 28 | (TAANY) | 640000
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 7 | RIGHT-OF-WAY | FY 2027 - | 36 | (L(M)) | 160000
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 8 | UTILITIES | FY 2027 - | 28 | (TAANY) | 2280000
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 8 | UTILITIES | FY 2027 - | 36 | (L(M)) | 570000
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 13 | CONSTRUCTION | FY 2028 - | 28 | (TAANY) | 3640000
2024-11-07 | FINAL | MODIFICATION | EB-6016 | 13 | CONSTRUCTION | FY 2028 - | 36 | (L(M)) | 910000
2024-11-07 | FINAL | ADDITION | HB-0072 | 13 | CONSTRUCTION | FY 2026 - | 7 | (HP) | 770000
2024-11-07 | FINAL | ADDITION | HB-0072 | 13 | CONSTRUCTION | FY 2026 - | 26 | (BGOFF) | 1238000
2024-11-07 | FINAL | ADDITION | HB-0072 | 13 | CONSTRUCTION | FY 2026 - | 56 | (T(M)) | 193000
2024-11-07 | FINAL | MODIFICATION | HL-0008J | 7 | RIGHT-OF-WAY | FY 2025 - | 16 | (BGBA) | 1000000
2024-11-07 | FINAL | MODIFICATION | HL-0008J | 8 | UTILITIES | FY 2026 - | 16 | (BGBA) | 600000
2024-11-07 | FINAL | MODIFICATION | HL-0008J | 13 | CONSTRUCTION | FY 2028 - | 16 | (BGBA) | 3942000
2024-11-07 | FINAL | MODIFICATION | HL-0008J | 13 | CONSTRUCTION | FY 2026 - | 16 | (BGBA) | 3838000
2024-11-07 | FINAL | MODIFICATION | HL-0008J | 13 | CONSTRUCTION | FY 2027 - | 16 | (BGBA) | 6521000
2024-11-07 | FINAL | MODIFICATION | HS-2405AI | 7 | RIGHT-OF-WAY | FY 2025 - | 10 | (HSIP) | 20000
2024-11-07 | FINAL | MODIFICATION | HS-2405AI | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 20000
2024-11-07 | FINAL | MODIFICATION | HS-2405AI | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 300000
2024-11-07 | FINAL | MODIFICATION | HS-2405AJ | 7 | RIGHT-OF-WAY | FY 2025 - | 10 | (HSIP) | 12000
2024-11-07 | FINAL | MODIFICATION | HS-2405AJ | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 6000
2024-11-07 | FINAL | MODIFICATION | HS-2405AJ | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 248000
2024-11-07 | FINAL | MODIFICATION | HS-2405AK | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 8000
2024-11-07 | FINAL | MODIFICATION | HS-2405AK | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 145000
2024-11-07 | FINAL | MODIFICATION | HS-2405AL | 7 | RIGHT-OF-WAY | FY 2026 - | 10 | (HSIP) | 10000
2024-11-07 | FINAL | MODIFICATION | HS-2405AL | 8 | UTILITIES | FY 2026 - | 10 | (HSIP) | 10000
2024-11-07 | FINAL | MODIFICATION | HS-2405AL | 13 | CONSTRUCTION | FY 2027 - | 10 | (HSIP) | 165000
2024-11-07 | FINAL | MODIFICATION | HS-2405AN | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 185000
2024-11-07 | FINAL | MODIFICATION | HS-2405AQ | 7 | RIGHT-OF-WAY | FY 2025 - | 10 | (HSIP) | 30000
2024-11-07 | FINAL | MODIFICATION | HS-2405AQ | 8 | UTILITIES | FY 2026 - | 10 | (HSIP) | 5000
2024-11-07 | FINAL | MODIFICATION | HS-2405AQ | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 340000
2024-11-07 | FINAL | MODIFICATION | HS-2405C | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 14000
2024-11-07 | FINAL | MODIFICATION | HS-2405C | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 1301000
2024-11-07 | FINAL | MODIFICATION | HS-2405D | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 16000
2024-11-07 | FINAL | MODIFICATION | HS-2405D | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 125000
2024-11-07 | FINAL | MODIFICATION | HS-2405G | 7 | RIGHT-OF-WAY | FY 2025 - | 10 | (HSIP) | 8000
2024-11-07 | FINAL | MODIFICATION | HS-2405G | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 30000
2024-11-07 | FINAL | MODIFICATION | HS-2405G | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 297000
2024-11-07 | FINAL | MODIFICATION | HS-2405L | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 950000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 7 | RIGHT-OF-WAY | FY 2025 - | 28 | (T) | 4000000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (T) | 4000000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2031 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2033 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2025 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2032 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2026 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2027 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2028 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2029 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 10 | BUILD NC CON | FY 2030 - | 28 | (T) | 2033000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 13 | CONSTRUCTION | FY 2026 - | 28 | (T) | 12294000
2024-11-07 | FINAL | MODIFICATION | R-5705A | 13 | CONSTRUCTION | FY 2027 - | 28 | (T) | 5275000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2025 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2026 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2028 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2029 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2030 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2031 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2032 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2033 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | AFTER FY 2033 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 10 | BUILD NC CON | FY 2027 - | 28 | (T) | 540000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 13 | CONSTRUCTION | FY 2023 - | 28 | (T) | 4114000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 13 | CONSTRUCTION | FY 2024 - | 28 | (T) | 18116000
2024-11-07 | FINAL | MODIFICATION | U-5826 | 13 | CONSTRUCTION | FY 2025 - | 28 | (T) | 1456000
2024-12-05 | FINAL | DELETION | C-4924B | 17 | IMPLEMENTATION | FY 2025 - | 6 | (CMAQ) | 586000
2024-12-05 | FINAL | DELETION | C-4924B | 17 | IMPLEMENTATION | FY 2026 - | 6 | (CMAQ) | 622000
2024-12-05 | FINAL | DELETION | C-4924B | 17 | IMPLEMENTATION | FY 2027 - | 6 | (CMAQ) | 641000
2024-12-05 | FINAL | DELETION | C-4924B | 17 | IMPLEMENTATION | FY 2025 - | 36 | (L(M)) | 147000
2024-12-05 | FINAL | DELETION | C-4924B | 17 | IMPLEMENTATION | FY 2026 - | 36 | (L(M)) | 155000
2024-12-05 | FINAL | DELETION | C-4924B | 17 | IMPLEMENTATION | FY 2027 - | 36 | (L(M)) | 160000
2024-12-05 | FINAL | MODIFICATION | HN-0026A | 17 | IMPLEMENTATION | FY 2025 - | 6 | (CMAQ) | 619000
2024-12-05 | FINAL | MODIFICATION | HN-0026A | 17 | IMPLEMENTATION | FY 2027 - | 6 | (CMAQ) | 658000
2024-12-05 | FINAL | MODIFICATION | HN-0026A | 17 | IMPLEMENTATION | FY 2026 - | 6 | (CMAQ) | 639000
2024-12-05 | FINAL | MODIFICATION | HN-0026A | 17 | IMPLEMENTATION | FY 2025 - | 36 | (L(M)) | 155000
2024-12-05 | FINAL | MODIFICATION | HN-0026A | 17 | IMPLEMENTATION | FY 2026 - | 36 | (L(M)) | 160000
2024-12-05 | FINAL | MODIFICATION | HN-0026A | 17 | IMPLEMENTATION | FY 2027 - | 36 | (L(M)) | 164000
2024-12-05 | FINAL | ADDITION | HO-0019 | 13 | CONSTRUCTION | FY 2025 - | 7 | (DP) | 1007000
2024-12-05 | FINAL | ADDITION | HO-0019 | 13 | CONSTRUCTION | FY 2025 - | 61 | (HF(M)) | 252000
2024-12-05 | FINAL | MODIFICATION | HS-2405AR | 7 | RIGHT-OF-WAY | FY 2026 - | 10 | (HSIP) | 5000
2024-12-05 | FINAL | MODIFICATION | HS-2405AR | 8 | UTILITIES | FY 2026 - | 10 | (HSIP) | 5000
2024-12-05 | FINAL | MODIFICATION | HS-2405AR | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 1020000
2024-12-05 | FINAL | MODIFICATION | HS-2405AS | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 395000
2024-12-05 | FINAL | ADDITION | TG-0027 | 1 | ENGINEERING | FY 2025 - | 29 | (CPF) | 900000
2024-12-05 | FINAL | ADDITION | TG-0027 | 1 | ENGINEERING | FY 2025 - | 36 | (L) | 236000
2024-12-05 | FINAL | MODIFICATION | TO-0004 | 13 | CONSTRUCTION | FY 2026 - | 22 | (S) | 500000
2024-12-05 | FINAL | MODIFICATION | TO-0004 | 13 | CONSTRUCTION | FY 2025 - | 22 | (S) | 500000
2024-12-05 | FINAL | MODIFICATION | TO-0004 | 13 | CONSTRUCTION | FY 2026 - | 79 | (SSO) | 1000000
2024-12-05 | FINAL | MODIFICATION | TO-0004 | 13 | CONSTRUCTION | FY 2025 - | 79 | (SSO) | 1810000

## County Division
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | PERCENT | COUNTY | DIVISION
2024-11-07 | FINAL | MODIFICATION | 100 | FRANKLIN | 5
2024-11-07 | FINAL | ADDITION | 100 | GRANVILLE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | HARNETT | 6
2024-11-07 | FINAL | MODIFICATION | 100 | JOHNSTON | 4
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 53 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 27 | FRANKLIN | 5
2024-11-07 | FINAL | MODIFICATION | 20 | GRANVILLE | 5
2024-11-07 | FINAL | MODIFICATION | 15 | DURHAM | 5
2024-11-07 | FINAL | MODIFICATION | 15 | WAKE | 5
2024-11-07 | FINAL | MODIFICATION | 14 | FRANKLIN | 5
2024-11-07 | FINAL | MODIFICATION | 14 | GRANVILLE | 5
2024-11-07 | FINAL | MODIFICATION | 14 | PERSON | 5
2024-11-07 | FINAL | MODIFICATION | 14 | VANCE | 5
2024-11-07 | FINAL | MODIFICATION | 14 | WARREN | 5
2024-12-05 | FINAL | MODIFICATION | 100 | STATEWIDE | 99
2024-12-05 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-12-05 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-12-05 | FINAL | MODIFICATION | 100 | WAKE | 5
2024-12-05 | FINAL | ADDITION | 100 | WAKE | 5
2024-12-05 | FINAL | DELETION | 50 | WAKE | 5
2024-12-05 | FINAL | DELETION | 50 | WAKE | 5
2024-12-05 | FINAL | DELETION | 50 | WAKE | 5
2024-12-05 | FINAL | DELETION | 25 | DURHAM | 5
2024-12-05 | FINAL | DELETION | 25 | DURHAM | 5
2024-12-05 | FINAL | DELETION | 25 | DURHAM | 5
2024-12-05 | FINAL | DELETION | 25 | ORANGE | 7
2024-12-05 | FINAL | DELETION | 25 | ORANGE | 7
2024-12-05 | FINAL | DELETION | 25 | ORANGE | 7
2024-12-05 | FINAL | ADDITION | 7 | CHATHAM | 8
2024-12-05 | FINAL | ADDITION | 7 | CUMBERLAND | 6
2024-12-05 | FINAL | ADDITION | 7 | EDGECOMBE | 4
2024-12-05 | FINAL | ADDITION | 7 | GASTON | 12
2024-12-05 | FINAL | ADDITION | 7 | HARNETT | 6
2024-12-05 | FINAL | ADDITION | 7 | HENDERSON | 14
2024-12-05 | FINAL | ADDITION | 7 | LEE | 8
2024-12-05 | FINAL | ADDITION | 7 | LINCOLN | 12
2024-12-05 | FINAL | ADDITION | 7 | MARTIN | 1
2024-12-05 | FINAL | ADDITION | 7 | TRANSYLVANIA | 14
2024-12-05 | FINAL | ADDITION | 6 | BERTIE | 1
2024-12-05 | FINAL | ADDITION | 6 | HERTFORD | 1
2024-12-05 | FINAL | ADDITION | 6 | NASH | 4
2024-12-05 | FINAL | ADDITION | 6 | RANDOLPH | 8
2024-12-05 | FINAL | ADDITION | 6 | WAKE | 5