## Project Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | MPO | IDNUM | PROJ_ID | DESCRIPTION | AGENDA_COMMENT | FUNDING_COMMENT | FEDERAL_AMENDMENT | CATEGORY
2025-01-08 | FINAL | MODIFICATION | RALEIGH | BL-0091 | BL-0091 | HIGGINS GREENWAY, SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 24 TO FY 25. |  | N | EX
2025-01-08 | FINAL | MODIFICATION | RALEIGH | HM-0003 | HM-0003 | CHESWICK DRIVE, REPLACE BRIDGE 910627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 24 TO FY 25. |  | N | DIV
2025-01-08 | FINAL | MODIFICATION | STATEWIDE | R-5753 | R-5753 | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. | COST INCREASE EXCEEDING $2 MILLION AND 25% THRESHOLDS. |  | Y | EX

## MPORPO
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | IDNUM | MPO_PERCENT | OFFICIAL_NAME
2025-01-08 | FINAL | MODIFICATION | BL-0091 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-01-08 | FINAL | MODIFICATION | HM-0003 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-01-08 | FINAL | MODIFICATION | R-5753 | 100 | STATEWIDE PROJECT

## Funding Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | PROJ | SORT_SEQUENCE | Activity | Year | FUND_SOURT_SEQ | FUND | AMNT
2025-01-08 | FINAL | MODIFICATION | BL-0091 | 13 | CONSTRUCTION | FY 2025 - | 6 | (CMAQ) | 1960000
2025-01-08 | FINAL | MODIFICATION | BL-0091 | 13 | CONSTRUCTION | FY 2025 - | 36 | (L) | 490000
2025-01-08 | FINAL | MODIFICATION | HM-0003 | 7 | RIGHT-OF-WAY | FY 2025 - | 16 | (BFPOFF) | 250000
2025-01-08 | FINAL | MODIFICATION | HM-0003 | 8 | UTILITIES | FY 2025 - | 16 | (BFPOFF) | 250000
2025-01-08 | FINAL | MODIFICATION | HM-0003 | 13 | CONSTRUCTION | FY 2026 - | 16 | (BFPOFF) | 328000
2025-01-08 | FINAL | MODIFICATION | HM-0003 | 13 | CONSTRUCTION | FY 2025 - | 16 | (BFPOFF) | 922000
2025-01-08 | FINAL | MODIFICATION | R-5753 | 13 | CONSTRUCTION | FY 2026 - | 9 | (FLTP) | 12791000
2025-01-08 | FINAL | MODIFICATION | R-5753 | 13 | CONSTRUCTION | FY 2025 - | 9 | (ERFO) | 677000
2025-01-08 | FINAL | MODIFICATION | R-5753 | 13 | CONSTRUCTION | FY 2028 - | 9 | (FLTP) | 6500000
2025-01-08 | FINAL | MODIFICATION | R-5753 | 13 | CONSTRUCTION | FY 2027 - | 9 | (FLTP) | 21059000
2025-01-08 | FINAL | MODIFICATION | R-5753 | 13 | CONSTRUCTION | FY 2027 - | 9 | (ERFO) | 5992000
2025-01-08 | FINAL | MODIFICATION | R-5753 | 13 | CONSTRUCTION | FY 2025 - | 9 | (FLTP) | 11500000

## County Division
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | IDNUM | PERCENT | COUNTY | DIVISION
2025-01-08 | FINAL | MODIFICATION | BL-0091 | 100 | WAKE | 5
2025-01-08 | FINAL | MODIFICATION | HM-0003 | 100 | WAKE | 5
2025-01-08 | FINAL | MODIFICATION | R-5753 | 100 | STATEWIDE | 99