## Project Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | MPOsRPOs | IDNUM | PROJ_ID | ROUTES | DESCRIPTION | AGENDA_COMMENT | FUNDING_COMMENT | FEDERAL_AMENDMENT | CATEGORY
2025-07-09 | HANDOUT | MODIFICATION | Land-of-Sky RPO | BF-0002 | BF-0002 | ECUSTA TRAIL | ECUSTA TRAIL, TRANSYLVANIA COUNTY LINE TO LAMB CREEK NEAR BREVARD. CONSTRUCT GREENWAY. | ADD CONSTRUCTION PHASE IN FY 25 NOT PREVIOUSLY PROGRAMMED. THIS ACTION ADDS THE PROJECT TO THE FEDERALLY APPROVED STIP. DP REPRESENTS RAISE GRANT OF $23.559M AND NSFLTP GRANT OF $733K. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | BL-0078 | BL-0078 | ECUSTA TRAIL | ECUSTA TRAIL, US 64 TO TRANSYLVANIA COUNTY LINE NEAR ETOWAH. CONSTRUCT GREENWAY. | TO REFLECT LATEST DELIVERY SCHEDULE, ACCELERATE CONSTRUCTION FROM FY 27 TO FY 25. COST INCREASE EXCEEDING $2 MILLION AND 25% THRESHOLDS. DP REPRESENTS RAISE GRANT OF $1.0M AND NSFLTP GRANT OF $14.974M. |  | Y | DIV
2025-07-09 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | BL-0087 | BL-0087 | VARIOUS | VARIOUS, ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. | MODIFY SCOPE AT THE REQUEST OF THE DIVISION. |  | Y | DIV
2025-07-09 | HANDOUT | ADDITION | New Bern Area MPO | BL-0167 | BL-0167 | SR 1309 (GLENBURNIE ROAD) | SR 1309 (GLENBURNIE ROAD), COLLEGE COURT TO GREENBRIAR PARKWAY IN NEW BERN. CONSTRUCT SIDEWALK. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION | High Country RPO | BN-0016 | BN-0016 | SR 1193 (LEDGER SCHOOL ROAD) | SR 1193 (LEDGER SCHOOL ROAD), NC 226 TO MITCHELL HIGH SCHOOL NEAR BAKERSVILLE. CONSTRUCT SIDEWALK. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26 AND CONSTRUCTION FROM FY 26 TO FY 28. |  | Y | EX
2025-07-09 | HANDOUT | ADDITION | Peanut Belt RPO | BR-0153 | BR-0153 | NC 11 | NC 11, BRIDGE 070024 OVER CASHIE RIVER. REPLACE BRIDGE. | ADD PROJECT AT THE REQUEST OF THE STRUCTURES MANAGEMENT UNIT. |  | Y | REG
2025-07-09 | HANDOUT | DELETION | Goldsboro Urban Area MPO | EB-5850 | EB-5850 | BERKELEY BOULEVARD | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | REMOVE PROJECT AT THE REQUEST OF THE MPO. |  | Y | DIV
2025-07-09 | HANDOUT | MODIFICATION | Greensboro Urban Area MPO | EB-5900 | EB-5900 | SUMMERFIELD SOUTH GREENWAY | SUMMERFIELD SOUTH GREENWAY, US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | ADD UTILITIES NOT PREVIOUSLY PROGRAMMED. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Cape Fear RPO, Wilmington Urban Area MPO | F-5707 | F-5707 | SOUTH PORT TO FORT FISHER FERRY | SOUTHPORT TO FORT FISHER FERRY, SOUTH PORT FERRY TERMINAL. CONSTRUCT MOORING FACILITIES. | REMOVE CONSTRUCTION AT THE REQUEST OF FERRY DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | HE-0001B | HE-0001 | NEW ROUTE | NEW ROUTE, FREDERICK LAW OLMSTEAD WAY EAST TO I-26. CONSTRUCT TWO LANE ROAD WITH SIDEWALK. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. THIS IS AN ECONOMIC DEVELOPMENT PROJECT. |  | N | EX
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | HE-0007A | HE-0007 | SR 1004 (OLD OXFORD ROAD) | SR 1004 (OLD OXFORD ROAD), FIRST AVENUE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 24 TO FY 26. THIS IS AN ECONOMIC DEVELOPMENT PROJECT. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | HL-0049 | HL-0049 | BRENNER AVENUE | BRENNER AVENUE, US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN AND CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | COST INCREASE EXCEEDING $2 MILLION AND 25% THRESHOLDS. |  | Y | DIV
2025-07-09 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | HL-0062 | HL-0062 | NC 49 | NC 49, SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY AND UTILITIES FROM FY 25 TO FY 26 AND CONSTRUCTION FROM FY 26 TO FY 27. |  | N | SW
2025-07-09 | HANDOUT | DELETION |  | HN-0021 |  |  | NC 71, SR 1001 (SHANNON ROAD) INTERSECTION IN SHANNON. CONSTRUCT ROUNDABOUT. | REMOVE PROJECT AT THE REQUEST OF THE DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | ADDITION |  | HN-0042 | HN-0042 | US 74 | US 74, ANSON HIGH SCHOOL ROAD INTERSECTION IN WADESBORO. CONSTRUCT INTERSECTION IMPROVEMENTS. | ADD PROJECT AT THE REQUEST OF THE DIVISION. |  | Y | SW
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | HO-0001AB | HO-0001 | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY, -. INSTALL FIBER OPTIC CABLE. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | EX
2025-07-09 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2003AD | HS-2003 | US 117 / NC 132 (COLLEGE ROAD) | US 117 / NC 132 (COLLEGE ROAD), CREWS DRIVE INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL SIGNALIZED PEDESTRIAN CROSSINGS. | MODIFY SCOPE AT THE REQUEST OF THE DIVISION. |  | N | SW
2025-07-09 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2003AI | HS-2003 | US 117/NC 132 (COLLEGE ROAD) | US 117/NC 132 (COLLEGE ROAD), SR 2160 (LONG RIDGE ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | Eastern Carolina RPO | HS-2003I | HS-2003 | NC 403 | NC 403, SR 1306 (BEAUTANCUS ROAD) INTERSECTION. CONSTRUCT SAFETY IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | Albemarle RPO, Peanut Belt RPO | HS-2401Q | HS-2401 | US 64; US 158; NC 32 | US 64; US 158; NC 32, VARIOUS LOCATIONS. INSTALL RUMBLE STRIPES AND SNOW PLOWABLE PAVEMENT MARKERS. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | Greenville Urban Area MPO, Mid-East RPO | HS-2402G | HS-2402 | US 13 / US 264 | US 13 / US 264, SR 1124 (SPEIGHT SPEED FARM ROAD) / SR 1207 (NASH JOYNER ROAD) INTERSECTION IN GREENVILLE. CONSTRUCT REDUCED CONFLICT INTERSECTION WITH RIGHT TURN LANES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY AND UTILITIES FROM FY 25 TO FY 26 AND CONSTRUCTION FROM FY 26 TO FY 27. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | Greenville Urban Area MPO | HS-2402O | HS-2402 | NC 43 | NC 43, US 264 INTERCHANGE RAMPS. CONSTRUCT ROUNDABOUTS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | Eastern Carolina RPO | HS-2403L | HS-2403 | US 117 | US 117, SR 1150 (LODGE/HIGH SCHOOL ROAD) INTERSECTION IN TEACHEY. INSTALL TRAFFIC SIGNAL. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Cape Fear RPO | HS-2403M | HS-2403 | NC 50 (ROLAND AVENUE) | NC 50 (ROLAND AVENUE), NC 210 / SR 1534 (BELT ROAD) INTERSECTION IN SURF CITY. UPGRADE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2403N | HS-2403 | US 117 / NC 132 | US 117 / NC 132, SR 2206 (WEST NORTHCHASE PARKWAY) / SR 2257 (SOUTHEAST NORTHCHASE PARKWAY) INTERSECTION NORTH OF WILMINGTON. UPGRADE TRAFFIC SIGNAL. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2403O | HS-2403 | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET), 10TH STREET INTERSECTION IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2403P | HS-2403 | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET), 5TH AVENUE INTERSECTION IN WILMINGTON. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2403Q | HS-2403 | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET), LULLWATER DRIVE INTERSECTION IN WILMINGTON. UPGRADE SIGNING AND TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO, Kerr-Tar RPO | HS-2405BA | HS-2405 | VARIOUS | VARIOUS, ROUTES IN WAKE AND FRANKLIN COUNTIES. INSTALL EXPERIMENTAL PAVEMENT MARKINGS TO EVALUATE WET RETROREFLECTIVITY. | ADD PROJECT BREAK AT THE REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | HS-2405J | HS-2405 | US 70 / US 401 (SOUTH SAUNDERS STREET) | US 70 / US 401 (SOUTH SAUNDERS STREET), I-40 / I-440 RAMP TERMINALS. UPRADE RAMP TRAFFIC SIGNALS. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | HS-2405O | HS-2405 | SR 2754 (KENNEBEC ROAD) | SR 2754 (KENNEBEC ROAD), SR 2763 (MAUDE STEWART ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | HS-2410A | HS-2410 | SR 1790 (WINECOFF SCHOOL ROAD) | SR 1790 (WINECOFF SCHOOL ROAD), WINECOFF ELEMENTARY SCHOOL IN CONCORD. INSTALL PEDESTRIAN ACCOMMODATIONS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | HS-2410L | HS-2410 | VARIOUS | VARIOUS LOCATIONS. INSTALL SIGNAL AT VARIOUS LOCATION ON SECONDARY ROUTES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-07-09 | HANDOUT | DELETION | Gaston-Cleveland-Lincoln MPO | I-5719E | I-5719 | I-85 | I-85, VARIOUS LOCATIONS. INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR. | REMOVE PROJECT. WORK NO LONGER INCLUDED IN FEDERAL INFRA GRANT. |  | Y | SW
2025-07-09 | HANDOUT | ADDITION |  | M-0570 |  |  | VARIOUS. FUNDING FOR MULTI-MODAL PLANNING. | ADD PROJECT AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570L |  |  | VARIOUS LOCATIONS IN WINTERVILLE, FUNDING FOR BICYCLE AND PEDESTRIAN PLANNING. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570M |  |  | VARIOUS LOCATIONS IN KINSTON. FUNDING FOR MULTI-MODAL PLANNING. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570N |  |  | VARIOUS LOCATIONS IN VANDEMERE. FUNDING FOR BICYCLE AND PEDESTRIAN PROJECT ACCELERATION PLAN. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570P |  |  | VARIOUS LOCATIONS IN SURF CITY. FUNDING FOR BICYCLE AND PEDESTRIAN PLANNING. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570Q |  |  | VARIOUS LOCATIONS IN BURGAW. FUNDING FOR BICYCLE AND PEDESTRIAN PROJECT ACCELERATION PLAN. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570R |  |  | VARIOUS LOCATIONS AT NC STATE UNIVERSITY. FUNDING FOR MULTI-MODAL PLANNING. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570S |  |  | VARIOUS LOCATIONS AT UNC WILMINGTON. FUNDING FOR MULTI-MODAL PLANNING. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570T |  |  | VARIOUS LOCATIONS AT UNC CHAPEL HILL. FUNDING FOR MULTI-MODAL PLANNING. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | M-0570U |  |  | VARIOUS LOCATIONS IN MATTHEWS. FUNDING FOR BICYCLE AND PEDESTRIAN PLANNING. | ADD PROJECT BREAK AT THE REQUEST OF THE OFFICE OF STRATEGIC INITIATIVES AND PROGRAM SUPPORT. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION |  | R-5020AA |  |  | US 701 BUISINESS, SOUTH OF SR 1920 (MILL POND ROAD), REPLACE CULVERT. | ADD PROJECT BREAK AT THE REQUEST OF THE DIVISION. |  | Y | REG
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | R-5711 | R-5711 | US 21 | US 21, SR 2375 (HOUSTON ROAD) / SR 1312 (FLOWER HOUSE ROAD) INTERSECTION IN TROUTMAN. REALIGN AND SIGNALIZE INTERSECTION. | ADD UTILITIES PHASE IN FY 25 NOT PREVIOUSLY PROGRAMMED. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | High Country RPO | R-5830 | R-5830 | SR 1522 (DEERFIELD ROAD) | SR 1522 (DEERFIELD ROAD), STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD) IN BOONE. UPGRADE ROADWAY. | MODIFY FUNDING FROM STATE TO FEDERAL. |  | Y | DIV
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | RL-0001 | RL-0001 | SR 2395 (MAZEPPA ROAD) | SR 2395 (MAZEPPA ROAD), NC 115 INTERSECTION IN MOORESVILLE. CONSTRUCT GRADE SEPARATION OVER NORFOLK SOUTHERN RAILROAD AND NC 115. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26 AND CONSTRUCTION FROM FY 26 TO FY 28. DP REPRESENTS RAISE GRANT OF $4.090M. |  | N | EX
2025-07-09 | HANDOUT | MODIFICATION | Mid-Carolina RPO | RX-2006A | RX-2006 | SR 1714 (CHURCH STREET) | SR 1714 (CHURCH STREET), CSX CROSSING 629869Y IN WADE. INSTALL ACTIVE WARNING DEVICES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TA-4818A | TA-4818A | GOTRIANGLE | GOTRIANGLE, SYSTEMWIDE. PURCHASE BUS FOR SERVICE EXPANSION. | ADD FUNDS IN FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | TA-4818B | TA-4818B | GOTRIANGLE | GOTRIANGLE, SYSTEMWIDE. PURCHASE REPLACEMENT BUS. | MODIFY FUNDS AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Fayetteville Area MPO | TA-4948A | TA-4948A | FAYETTEVILLE AREA SYSTEM OF TRANSIT (FAST) | FAYETTEVILLE AREA SYSTEM OF TRANSIT (FAST), SYSTEMWIDE. REPLACE BUS. | ADD FUNDS IN FY 25, FY 26, FY 27, AND FY 28 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TA-5140 | TA-5140 | GORALEIGH | GORALEIGH, SYSTEMWIDE. PURCHASE REPLACEMENT BUS. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TA-5229 | TA-5229 | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT, SYSTEMWIDE. PURCHASE REPLACEMENT TRANSIT VEHICLE. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TA-6703 | TA-6703 | CITY OF ASHEVILLE TRANSIT | CITY OF ASHEVILLE TRANSIT, SYSTEMWIDE. PURCHASE LO-NO TRANSIT VEHICLE. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | TA-6724 | TA-6724 | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | CHARLOTTE AREA TRANSIT SYSTEM (CATS), I-77 AND HAMBRIGHT ROAD PARK. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | MODIFY THE FUNDS AT THE REQUEST OF THE MPO. |  | Y | DIV
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | TC-0042 | TC-0042 | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT, SYSTEMWIDE. FUND MOBILTY MANAGEMENT UNDER 5310 GRANT. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | TC-0043 | TC-0043 | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT, SYSTEMWIDE. FUND EX RIDER SENIOR SHUTTLE 5310 GRANT. | ADD FUNDS TO FY 25 AT THE REQUES OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION |  | TC-0044 |  |  | GORALEIGH. ROUTINE CAPITAL – SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE/SUPPORT VEHICLES, COMPUTER HARDWARE/SOFTWARE, RADIO | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION |  | TC-0045 |  |  | CAPITAL INVESTMENTS FOR THE DEMOLITION, PURCHASE, AND INSTALLATION OF BUS SHELTERS THROUGHOUT NEW HANOVER COUNTY. | ADD FUNDS IN FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TD-5305 | TD-5305 | CARY TRANSIT | CARY TRANSIT, SYSTEMWIDE. FUNDING FOR DOWNTOWN CARY MULTI MODAL FACILITY. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TD-5308 | TD-5308 | GORALEIGH | GORALEIGH, VARIOUS LOCATIONS. CONSTRUCT COORDINATED ADA FACILITY. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. DP FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TG-0011 | TG-0011 | CITY OF ASHEVILLE TRANSIT | CITY OF ASHEVILLE TRANSIT, VARIOUS LOCATIONS. FUNDING FOR BUS STOP IMPROVEMENT PROGRAM. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TG-0013 | TG-0013 | GORALEIGH | GORALEIGH, VARIOUS LOCATIONS. FUNDING FOR PREVENTATIVE MAINTENANCE. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TG-0015 | TG-0015 | GORALEIGH | GORALEIGH, VARIOUS LOCATIONS. FUNDING FOR CAPITAL PROJECTS. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Greensboro Urban Area MPO | TG-0019 | TG-0019 | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY, VARIOUS LOCATIONS. FUNDING FOR ROUTINE CAPITAL INCLUDING FAREBOXES, CAMERA SYSTEMS, APCS AND DELIVERY FOR ASSET TRANSFER OF USED BUSES, DEPOT TICKET MACHINE, REALTIME SHELTER SIGNAGE, AND BUS SHELTERS. | MODIFY THE FUNDS AND DESCRIPTION AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION |  | TG-0031 |  |  | GODURHAM TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. | MODIFY THE DESCRIPTION AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Goldsboro Urban Area MPO | TG-4752B | TG-4752B | TRANSPORTATION AUTHORITY OF GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY OF GOLDSBORO-WAYNE, SYSTEMWIDE. FUNDING FOR PREVENTATIVE MAINTENANCE. | ADD FUNDS IN FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Goldsboro Urban Area MPO | TG-4752C | TG-4752C | TRANSPORTATION AUTHORITY OF GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY OF GOLDSBORO-WAYNE, SYSTEMWIDE. FUNDING FOR ADA PARATRANSIT SERVICE. | ADD FUNDS IN FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TG-4792B | TG-4792B | GORALEIGH | GORALEIGH, SYSTEMWIDE. FUNDING FOR ADA PARATRANSIT SERVICE. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO, Triangle West TPO | TG-4821B | TG-4821B | GOTRIANGLE | GOTRIANGLE, SYSTEMWIDE. FUNDING FOR ROUTINE CAPITAL INCLUDING BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES ETC. | ADD FUNDS IN FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TG-4935A | TG-4935A | CARY TRANSIT | CARY TRANSIT, SYSTEMWIDE. FUNDING FOR CONTRACTING COSTS. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Greensboro Urban Area MPO | TG-5105 | TG-5105 | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY, SYSTEMWIDE. FUNDING FOR ROUTINE CAPITAL. | MODIFY THE FUNDS AND DESCRIPTION AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Fayetteville Area MPO | TG-5224C | TG-5224C | FAYETTEVILLE AREA SYSTEM OF TRANSIT (FAST) | FAYETTEVILLE AREA SYSTEM OF TRANSIT (FAST), VARIOUS LOCATIONS. FUNDING FOR ROUTINE CAPITAL. | ADD FUNDS IN FY 26, FY 27, AND FY 28 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TG-6143 | TG-6143 | CITY OF ASHEVILLE TRANSIT | CITY OF ASHEVILLE TRANSIT, SYSTEMWIDE. FUNDING FOR BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, AND SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. | ADD FUNDS TO FY 25 AT THE RQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TG-6181 | TG-6181 | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT, SYSTEMWIDE. FUNDING FOR CONTRACTS. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TG-6183B | TG-6183B | CITY OF ASHEVILLE TRANSIT | CITY OF ASHEVILLE TRANSIT, SYSTEMWIDE. FUNDING FOR PREVENTATIVE MAINTENANCE. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | TL-0035 | TL-0035 | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT, SOUTHERN VILLAGE PARK AND RIDE LOT TO EUBANKS ROAD PARK AND RIDE LOT. . CONSTRUCT NORTH-SOUTH BUS RAPID TRANSIT (NSBRT) SYSTEM. | ADD FUNDS TO FY27 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | TL-0062 | TL-0062 | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT, VARIOUS LOCATIONS. IMPROVE ALL BUS STOPS. | ADD FUNDS TO FY 26 AT THE REQUEST OF THE MPO. |  | N | DIV
2025-07-09 | HANDOUT | ADDITION | Triangle West TPO | TL-0065 | TL-0065 | GODURHAM | GODURHAM, SYSTEMWIDE. PURCHASE BATTERY ELECTRIC BUSES. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | N | EX
2025-07-09 | HANDOUT | MODIFICATION | Greensboro Urban Area MPO | TL-0068 | TL-0068 | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY, SYSTEMWIDE. FUND STUDY AND DESIGN OF CROSSMAX PURPLE CORRIDOR. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. DP FUNDS REPRESENT FEDERAL RAISE GRANT AWARD. |  | N | EX
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | TM-0040 | TM-0040 | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | CHARLOTTE AREA TRANSIT SYSTEM (CATS), SYSTEMWIDE. PLAN NEW AND REPLACEMENT CIRCULATOR ROUTES WITH NEW ON-DEMAND STRATEGY OF MICRO-TRANSIT ZONES TO REDUCE TRAVEL TIMES AND IMPROVE CONNECTIVITY TO HIGH-FREQUENCY ROUTES AT MOBILITY HUBS. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Gaston-Cleveland-Lincoln MPO | TM-0058 | TM-0058 | GASTONIA TRANSIT AUTHORITY | GASTONIA TRANSIT AUTHORITY, GASTONIA. PURCHASE AN ELECTRIC ADA VAN. | MODIFY THE FUNDS AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | TM-0066 | TM-0066 | ORANGE COUNTY PUBLIC TRANSIT | ORANGE COUNTY PUBLIC TRANSIT, SYSTEMWIDE. OPERATING ASSISTANCE AND PURCHASE OF BUS SHELTERS. | ADD FUNDS AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TN-6116 | TN-6116 | WAKE COORDINATED TRANSPORTATION SERVICE | WAKE COORDINATED TRANSPORTATION SERVICE, VARIOUS LOCATIONS. FUNDING FOR TRANSIT SERVICE OPERATING ASSISTANCE. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | ADDITION |  | TN-6136 |  |  | ROCKY MOUNT, SYSTEMWIDE. EXPANSION OF COMMUTER BUS SERVICES BETWEEN RALEIGH AND ROCKY MOUNT. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | Y | EX
2025-07-09 | HANDOUT | MODIFICATION | Goldsboro Urban Area MPO | TO-4719 | TO-4719 | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY, VARIOUS LOCATIONS. FUNDING FOR OPERATING ASSISTANCE. | ADD FUNDS IN FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TO-6106 | TO-6106 | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT, SYSTEMWIDE. FUNDING FOR OPERATING ASSISTANCE. | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Greensboro Urban Area MPO | TO-6139 | TO-6139 | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY, SYSTEMWIDE. FUNDING FOR OPERATING ASSISTANCE. | MODIFY THE FUNDS AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TP-5100B | TP-5100B | GORALEIGH | GORALEIGH, VARIOUS LOCATIONS. FUNDING FOR PLANNING ASSISTANCE -5307 | ADD FUNDS TO FY 25 AND FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Greater Hickory MPO | TP-5106 | TP-5106 | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS, SYSTEMWIDE. FUNDING FOR PLANNING ASSISTANCE. | ADD FUNDING TO FY 26, FY 27, AND FY 28 AT THE REQUEST OF THE MPO |  | N | PT
2025-07-09 | HANDOUT | DELETION |  | TP-5112 |  |  | PLANNING ASSISTANCE | REMOVE PROJECT AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Greensboro Urban Area MPO | TQ-6783 | TQ-6783 | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY, VARIOUS LOCATIONS. FUNDING FOR SECTION 5310 FOR CAPITAL PROJECT. | MODIFY THE FUNDS AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Capital Area MPO | TQ-9037 | TQ-9037 | GORALEIGH | GORALEIGH, SYSTEMWIDE. 5310 ADMINISTRATION AND CAPITAL. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION |  | TU-0010 |  |  | PROGRAM SUPPORT. | ADD FUNDS TO FY 26 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | TU-0013 | TU-0013 | GODURHAM | GODURHAM, DURHAM STATION. IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, INCREASE CONNECTION TO EMPLOYMENT, HEALTH CARE AND EDUCATIONAL OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES AND PLA | ADD FUNDING TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | French Broad River MPO | TU-0020 | TU-0020 | CITY OF ASHEVILLE TRANSIT | CITY OF ASHEVILLE TRANSIT, VARIOUS. FY 2021 AOPP - AREAS OF CONSISTENT POVERTY PLANNING SURVEY AND ENGAGEMENT. | ADD FUNDS TO FY 25 AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Greensboro Urban Area MPO | TU-0021 | TU-0021 | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY, SYSTEMWIDE. TRANSIT PLANNING | MODIFY THE FUNDS AT THE REQUEST OF THE MPO. |  | N | PT
2025-07-09 | HANDOUT | MODIFICATION | Greater Hickory MPO | U-4700CC | U-4700 | US 321 | US 321, SR 1108 (MISSION ROAD) INTERSECTION IN SAWMILLS. CONSTRUCT REDUCED CONFLICT INTERSECTION WITHIN THE LIMITS OF U-4700C. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | SW
2025-07-09 | HANDOUT | MODIFICATION | Triangle West TPO | U-4726HO | U-4726 | CARPENTER FLETCHER ROAD | CARPENTER FLETCHER ROAD, WOODCROFT PARKWAY TO SR 1945 (ALSTON AVENUE). CONSTRUCT BICYCLE LANES AND SIDEWALKS. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY RIGHT-OF-WAY AND CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | U-5769A | U-5769 | NC 16 (PROVIDENCE ROAD SOUTH) | NC 16 (PROVIDENCE ROAD SOUTH), SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH ROAD) IN WAXHAW. WIDEN TO MULTI-LANES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | U-5769B | U-5769 | NC 16 (PROVIDENCE ROAD SOUTH) | NC 16 (PROVIDENCE ROAD SOUTH), SR 1307 (BONDS GROVE CHURCH ROAD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | REG
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | U-5803 | U-5803 | SR 2940 (EASTWAY DRIVE) | SR 2940 (EASTWAY DRIVE), SHAMROCK DRIVE INTERSECTION IN CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. "O" FUNDS REPRESENT CITY OF CHARLOTTE FUNDS. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Charlotte Regional TPO | U-5906 | U-5906 | SR 2195 (TORRENCE CHAPEL ROAD) | SR 2195 (TORRENCE CHAPEL ROAD), SR 5544 (WEST CATAWBA AVENUE) INTERSECTION IN CORNELIUS. CONSTRUCT INTERSECTION IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR UTILITY RELOCATION, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Kerr-Tar RPO | W-5705G | W-5705 | SR 1001 (WARRENTON ROAD) | SR 1001 (WARRENTON ROAD), SR 1507 (BROOKSTON ROAD) INTERSECTION. . CONSTRUCT INTERSECTION IMPROVEMENTS. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-07-09 | HANDOUT | MODIFICATION | Kerr-Tar RPO | W-5805G | W-5805 | US 1 | US 1, SR 1113 (LAKE LODGE ROAD) INTERSECTION. . CONSTRUCT UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | SW

## MPORPO
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | IDNUM | MPO_PERCENT | OFFICIAL_NAME
2025-07-09 | HANDOUT | MODIFICATION | BF-0002 | 100 | LAND OF SKY RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | BL-0078 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | BL-0087 | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | ADDITION | BL-0167 | 100 | NEW BERN METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 100 | HIGH COUNTRY RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | ADDITION | BR-0153 | 100 | PEANUT BELT RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | DELETION | EB-5850 | 100 | GOLDSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 100 | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | F-5707 | 50 | CAPE FEAR RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | F-5707 | 50 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HE-0001B | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HE-0007A | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | DELETION | HN-0021 | 100 | LUMBER RIVER RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 100 | ROCKY RIVER RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HO-0001AB | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2003AD | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2003AI | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2003I | 100 | EASTERN CAROLINA RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2401Q | 64 | ALBEMARLE RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2401Q | 36 | PEANUT BELT RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2402G | 50 | GREENVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2402G | 50 | MID-EAST RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2402O | 100 | GREENVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2403L | 100 | EASTERN CAROLINA RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2403M | 100 | CAPE FEAR RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2403N | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2403O | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2403P | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2403Q | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2405BA | 90 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2405BA | 10 | KERR TAR RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2405J | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2405O | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2410A | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | HS-2410L | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | DELETION | I-5719E | 100 | GASTON CLEVELAND LINCOLN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | ADDITION | M-0570 | 100 | STATEWIDE PROJECT
2025-07-09 | HANDOUT | MODIFICATION | M-0570L | 100 | GREENVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570M | 100 | EASTERN CAROLINA RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570N | 100 | DOWN EAST RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570P | 100 | CAPE FEAR RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570Q | 100 | CAPE FEAR RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570R | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570S | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570T | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | M-0570U | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | R-5020AA | 100 | CAPE FEAR RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | R-5711 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 100 | HIGH COUNTRY RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | RX-2006A | 100 | MID-CAROLINA RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TA-4818A | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 100 | FAYETTEVILLE URBANIZED AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TA-5140 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TA-5229 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TA-6703 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TC-0042 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TC-0043 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TC-0044 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TC-0045 | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TD-5305 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TD-5308 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-0011 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-0013 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-0015 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 100 | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-0031 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-4752B | 100 | GOLDSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-4752C | 100 | GOLDSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-4792B | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B | 50 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B | 50 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-4935A | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 100 | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 100 | FAYETTEVILLE URBANIZED AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-6143 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-6181 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TG-6183B | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TL-0035 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TL-0062 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | ADDITION | TL-0065 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TL-0068 | 100 | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TM-0040 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TM-0058 | 100 | GASTON CLEVELAND LINCOLN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TN-6116 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 100 | ROCKY MOUNT METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TO-4719 | 100 | GOLDSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TO-6106 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 100 | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TP-5100B | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 100 | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | DELETION | TP-5112 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 100 | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TU-0010 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TU-0013 | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TU-0020 | 100 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | TU-0021 | 100 | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | U-4700CC | 100 | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | U-4726HO | 100 | TRIANGLE WEST TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | W-5705G | 100 | KERR TAR RURAL PLANNING ORGANIZATION
2025-07-09 | HANDOUT | MODIFICATION | W-5805G | 100 | KERR TAR RURAL PLANNING ORGANIZATION

## Funding Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | PROJ | SORT_SEQUENCE | Activity | Year | FUND_SOURT_SEQ | FUND | AMNT
2025-07-09 | HANDOUT | MODIFICATION | BF-0002 | 13 | CONSTRUCTION | FY 2025 - | 7 | (DP) | 733000
2025-07-09 | HANDOUT | MODIFICATION | BF-0002 | 13 | CONSTRUCTION | FY 2025 - | 7 | (DP) | 23559000
2025-07-09 | HANDOUT | MODIFICATION | BF-0002 | 13 | CONSTRUCTION | FY 2025 - | 36 | (L(M)) | 81000
2025-07-09 | HANDOUT | MODIFICATION | BL-0078 | 13 | CONSTRUCTION | FY 2025 - | 7 | (DP) | 14974000
2025-07-09 | HANDOUT | MODIFICATION | BL-0078 | 13 | CONSTRUCTION | FY 2025 - | 7 | (DP) | 1000000
2025-07-09 | HANDOUT | MODIFICATION | BL-0078 | 13 | CONSTRUCTION | FY 2025 - | 27 | (BGDA) | 883000
2025-07-09 | HANDOUT | MODIFICATION | BL-0078 | 13 | CONSTRUCTION | FY 2025 - | 36 | (L(M)) | 1664000
2025-07-09 | HANDOUT | MODIFICATION | BL-0078 | 13 | CONSTRUCTION | FY 2025 - | 36 | (L(M)) | 221000
2025-07-09 | HANDOUT | MODIFICATION | BL-0087 | 13 | CONSTRUCTION | FY 2026 - | 28 | (TADA) | 1292000
2025-07-09 | HANDOUT | MODIFICATION | BL-0087 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 323000
2025-07-09 | HANDOUT | ADDITION | BL-0167 | 1 | ENGINEERING | FY 2026 - | 27 | (CRPDA) | 4000
2025-07-09 | HANDOUT | ADDITION | BL-0167 | 1 | ENGINEERING | FY 2026 - | 36 | (L(M)) | 1000
2025-07-09 | HANDOUT | ADDITION | BL-0167 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CRPDA) | 78000
2025-07-09 | HANDOUT | ADDITION | BL-0167 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 19000
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 1 | ENGINEERING | FY 2025 - | 27 | (CRPLT5) | 252000
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 1 | ENGINEERING | FY 2025 - | 61 | (HF(M)) | 63000
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 7 | RIGHT-OF-WAY | FY 2026 - | 27 | (CRPLT5) | 8000
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 7 | RIGHT-OF-WAY | FY 2026 - | 61 | (HF(M)) | 2000
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 13 | CONSTRUCTION | FY 2028 - | 27 | (CRPLT5) | 1472000
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 13 | CONSTRUCTION | FY 2028 - | 61 | (HF(M)) | 368000
2025-07-09 | HANDOUT | ADDITION | BR-0153 | 13 | CONSTRUCTION | FY 2025 - | 16 | (BFP) | 6100000
2025-07-09 | HANDOUT | DELETION | EB-5850 | 1 | ENGINEERING | FY 2025 - | 28 | (TA50200) | 15000
2025-07-09 | HANDOUT | DELETION | EB-5850 | 1 | ENGINEERING | FY 2025 - | 36 | (L) | 4000
2025-07-09 | HANDOUT | DELETION | EB-5850 | 8 | UTILITIES | FY 2026 - | 28 | (TA50200) | 160000
2025-07-09 | HANDOUT | DELETION | EB-5850 | 8 | UTILITIES | FY 2026 - | 36 | (L) | 40000
2025-07-09 | HANDOUT | DELETION | EB-5850 | 13 | CONSTRUCTION | FY 2026 - | 28 | (TA50200) | 10000
2025-07-09 | HANDOUT | DELETION | EB-5850 | 13 | CONSTRUCTION | FY 2027 - | 28 | (TA50200) | 950000
2025-07-09 | HANDOUT | DELETION | EB-5850 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L) | 240000
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 7 | UTILITIES | FY 2025 - | 28 | (TAANY) | 140000
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 7 | RIGHT-OF-WAY | FY 2025 - | 28 | (TAANY) | 312000
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 7 | UTILITIES | FY 2025 - | 36 | (L) | 35000
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 7 | RIGHT-OF-WAY | FY 2025 - | 36 | (L) | 78000
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 13 | CONSTRUCTION | FY 2026 - | 28 | (TAANY) | 2291000
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L) | 573000
2025-07-09 | HANDOUT | MODIFICATION | HE-0001B | 13 | CONSTRUCTION | FY 2026 - | 1 | (ADHSL) | 2500000
2025-07-09 | HANDOUT | MODIFICATION | HE-0001B | 13 | CONSTRUCTION | FY 2026 - | 61 | (HF) | 8082000
2025-07-09 | HANDOUT | MODIFICATION | HE-0007A | 13 | CONSTRUCTION | FY 2026 - | 28 | (T) | 165000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 7 | RIGHT-OF-WAY | FY 2025 - | 27 | (BGDA) | 11000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 7 | RIGHT-OF-WAY | FY 2025 - | 36 | (L(M)) | 3000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 8 | UTILITIES | FY 2025 - | 27 | (BGDA) | 160000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 8 | UTILITIES | FY 2025 - | 36 | (L(M)) | 40000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 13 | CONSTRUCTION | FY 2026 - | 27 | (BGDA) | 473000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 13 | CONSTRUCTION | FY 2026 - | 28 | (L(M)) | 118000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 13 | CONSTRUCTION | FY 2026 - | 29 | (TADA) | 1601000
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 400000
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 7 | RIGHT-OF-WAY | FY 2026 - | 26 | (BGANY) | 579000
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 7 | RIGHT-OF-WAY | FY 2026 - | 27 | (BGDA) | 185000
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L) | 191000
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 8 | UTILITIES | FY 2026 - | 26 | (BGANY) | 306000
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 8 | UTILITIES | FY 2026 - | 36 | (L) | 76000
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 13 | CONSTRUCTION | FY 2027 - | 26 | (BGANY) | 5156000
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L) | 1289000
2025-07-09 | HANDOUT | DELETION | HN-0021 | 7 | RIGHT-OF-WAY | FY 2025 - | 27 | (CRPLT5) | 120000
2025-07-09 | HANDOUT | DELETION | HN-0021 | 7 | RIGHT-OF-WAY | FY 2025 - | 28 | (T(M)) | 30000
2025-07-09 | HANDOUT | DELETION | HN-0021 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CRPLT5) | 1444000
2025-07-09 | HANDOUT | DELETION | HN-0021 | 13 | CONSTRUCTION | FY 2027 - | 27 | (CRPLT5) | 830000
2025-07-09 | HANDOUT | DELETION | HN-0021 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T(M)) | 207000
2025-07-09 | HANDOUT | DELETION | HN-0021 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T(M)) | 361000
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 1 | ENGINEERING | FY 2026 - | 27 | (CRPLT5) | 384000
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 1 | ENGINEERING | FY 2026 - | 28 | (T(M)) | 96000
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 7 | RIGHT-OF-WAY | FY 2026 - | 27 | (CRPLT5) | 155000
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (T(M)) | 39000
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CRPLT5) | 2102000
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T(M)) | 525000
2025-07-09 | HANDOUT | MODIFICATION | HO-0001AB | 13 | CONSTRUCTION | FY 2026 - | 7 | (DP) | 84000
2025-07-09 | HANDOUT | MODIFICATION | HO-0001AB | 13 | CONSTRUCTION | FY 2027 - | 61 | (HF(M)) | 29000
2025-07-09 | HANDOUT | MODIFICATION | HO-0001AB | 13 | CONSTRUCTION | FY 2026 - | 61 | (HF(M)) | 55000
2025-07-09 | HANDOUT | MODIFICATION | HS-2003AD | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 95000
2025-07-09 | HANDOUT | MODIFICATION | HS-2003AI | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 575000
2025-07-09 | HANDOUT | MODIFICATION | HS-2003I | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 70000
2025-07-09 | HANDOUT | MODIFICATION | HS-2401Q | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 1950000
2025-07-09 | HANDOUT | MODIFICATION | HS-2402G | 7 | RIGHT-OF-WAY | FY 2026 - | 10 | (HSIP) | 150000
2025-07-09 | HANDOUT | MODIFICATION | HS-2402G | 8 | UTILITIES | FY 2026 - | 10 | (HSIP) | 300000
2025-07-09 | HANDOUT | MODIFICATION | HS-2402G | 13 | CONSTRUCTION | FY 2027 - | 10 | (HSIP) | 950000
2025-07-09 | HANDOUT | MODIFICATION | HS-2402O | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 200000
2025-07-09 | HANDOUT | MODIFICATION | HS-2402O | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 388000
2025-07-09 | HANDOUT | MODIFICATION | HS-2403L | 13 | CONSTRUCTION | FY 2025 - | 10 | (HSIP) | 132000
2025-07-09 | HANDOUT | MODIFICATION | HS-2403M | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 40000
2025-07-09 | HANDOUT | MODIFICATION | HS-2403N | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 113000
2025-07-09 | HANDOUT | MODIFICATION | HS-2403O | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 82000
2025-07-09 | HANDOUT | MODIFICATION | HS-2403P | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 47000
2025-07-09 | HANDOUT | MODIFICATION | HS-2403Q | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 51000
2025-07-09 | HANDOUT | MODIFICATION | HS-2405BA | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 2925000
2025-07-09 | HANDOUT | MODIFICATION | HS-2405J | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 360000
2025-07-09 | HANDOUT | MODIFICATION | HS-2405O | 7 | RIGHT-OF-WAY | FY 2025 - | 10 | (HSIP) | 50000
2025-07-09 | HANDOUT | MODIFICATION | HS-2405O | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 50000
2025-07-09 | HANDOUT | MODIFICATION | HS-2405O | 13 | CONSTRUCTION | FY 2027 - | 10 | (HSIP) | 554000
2025-07-09 | HANDOUT | MODIFICATION | HS-2405O | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 6000
2025-07-09 | HANDOUT | MODIFICATION | HS-2410A | 7 | RIGHT-OF-WAY | FY 2026 - | 10 | (HSIP) | 10000
2025-07-09 | HANDOUT | MODIFICATION | HS-2410A | 13 | CONSTRUCTION | FY 2028 - | 10 | (HSIP) | 97000
2025-07-09 | HANDOUT | MODIFICATION | HS-2410L | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 1153000
2025-07-09 | HANDOUT | DELETION | I-5719E | 1 | ENGINEERING | FY 2025 - | 7 | (DP) | 112000
2025-07-09 | HANDOUT | DELETION | I-5719E | 1 | ENGINEERING | FY 2025 - | 28 | (T(M)) | 28000
2025-07-09 | HANDOUT | DELETION | I-5719E | 13 | CONSTRUCTION | FY 2025 - | 7 | (DP) | 448000
2025-07-09 | HANDOUT | DELETION | I-5719E | 13 | CONSTRUCTION | FY 2025 - | 28 | (T(M)) | 112000
2025-07-09 | HANDOUT | MODIFICATION | M-0570L | 1 | PLANNING | FY 2025 - | 27 | (CRPANY) | 44000
2025-07-09 | HANDOUT | MODIFICATION | M-0570L | 1 | PLANNING | FY 2025 - | 36 | (L) | 13000
2025-07-09 | HANDOUT | MODIFICATION | M-0570L | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 11000
2025-07-09 | HANDOUT | MODIFICATION | M-0570M | 1 | PLANNING | FY 2025 - | 27 | (CRPANY) | 44000
2025-07-09 | HANDOUT | MODIFICATION | M-0570M | 1 | PLANNING | FY 2025 - | 36 | (L) | 13000
2025-07-09 | HANDOUT | MODIFICATION | M-0570M | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 11000
2025-07-09 | HANDOUT | MODIFICATION | M-0570N | 1 | PLANNING | FY 2025 - | 27 | (CRPLT5) | 34000
2025-07-09 | HANDOUT | MODIFICATION | M-0570N | 1 | PLANNING | FY 2025 - | 36 | (L) | 5000
2025-07-09 | HANDOUT | MODIFICATION | M-0570N | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 9000
2025-07-09 | HANDOUT | MODIFICATION | M-0570P | 1 | PLANNING | FY 2025 - | 27 | (CRPANY) | 46000
2025-07-09 | HANDOUT | MODIFICATION | M-0570P | 1 | PLANNING | FY 2025 - | 36 | (L) | 6000
2025-07-09 | HANDOUT | MODIFICATION | M-0570P | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 12000
2025-07-09 | HANDOUT | MODIFICATION | M-0570Q | 1 | PLANNING | FY 2025 - | 27 | (CRPLT5) | 34000
2025-07-09 | HANDOUT | MODIFICATION | M-0570Q | 1 | PLANNING | FY 2025 - | 36 | (L) | 5000
2025-07-09 | HANDOUT | MODIFICATION | M-0570Q | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 9000
2025-07-09 | HANDOUT | MODIFICATION | M-0570R | 1 | PLANNING | FY 2025 - | 27 | (CRPANY) | 48000
2025-07-09 | HANDOUT | MODIFICATION | M-0570R | 1 | PLANNING | FY 2025 - | 36 | (L) | 14000
2025-07-09 | HANDOUT | MODIFICATION | M-0570R | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 12000
2025-07-09 | HANDOUT | MODIFICATION | M-0570S | 1 | PLANNING | FY 2025 - | 27 | (CRPANY) | 44000
2025-07-09 | HANDOUT | MODIFICATION | M-0570S | 1 | PLANNING | FY 2025 - | 36 | (L) | 13000
2025-07-09 | HANDOUT | MODIFICATION | M-0570S | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 11000
2025-07-09 | HANDOUT | MODIFICATION | M-0570T | 1 | PLANNING | FY 2025 - | 27 | (CRPANY) | 68000
2025-07-09 | HANDOUT | MODIFICATION | M-0570T | 1 | PLANNING | FY 2025 - | 36 | (L) | 20000
2025-07-09 | HANDOUT | MODIFICATION | M-0570T | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 17000
2025-07-09 | HANDOUT | MODIFICATION | M-0570U | 1 | PLANNING | FY 2025 - | 27 | (CRPANY) | 42000
2025-07-09 | HANDOUT | MODIFICATION | M-0570U | 1 | PLANNING | FY 2025 - | 36 | (L) | 21000
2025-07-09 | HANDOUT | MODIFICATION | M-0570U | 1 | PLANNING | FY 2025 - | 61 | (HF(M)) | 11000
2025-07-09 | HANDOUT | MODIFICATION | R-5020AA | 13 | CONSTRUCTION | FY 2027 - | 26 | (BG5T50) | 2000000
2025-07-09 | HANDOUT | MODIFICATION | R-5711 | 8 | UTILITIES | FY 2025 - | 28 | (T) | 600000
2025-07-09 | HANDOUT | MODIFICATION | R-5711 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T) | 2216000
2025-07-09 | HANDOUT | MODIFICATION | R-5711 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T) | 734000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 7 | RIGHT-OF-WAY | FY 2026 - | 26 | (BG5T50) | 112000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 7 | RIGHT-OF-WAY | FY 2029 - | 26 | (BG5T50) | 334000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 7 | RIGHT-OF-WAY | FY 2028 - | 26 | (BG5T50) | 1337000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 7 | RIGHT-OF-WAY | FY 2027 - | 26 | (BG5T50) | 1337000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 7 | RIGHT-OF-WAY | FY 2030 - | 26 | (BG5T50) | 780000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 8 | UTILITIES | FY 2026 - | 26 | (BG5T50) | 560000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 13 | CONSTRUCTION | FY 2032 - | 26 | (BG5T50) | 3248000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 13 | CONSTRUCTION | FY 2031 - | 26 | (BG5T50) | 5104000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 13 | CONSTRUCTION | FY 2028 - | 26 | (BG5T50) | 232000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 13 | CONSTRUCTION | FY 2030 - | 26 | (BG5T50) | 6960000
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 13 | CONSTRUCTION | FY 2029 - | 26 | (BG5T50) | 7656000
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 7 | RIGHT-OF-WAY | FY 2026 - | 7 | (DP) | 160000
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L) | 160000
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 13 | CONSTRUCTION | FY 2028 - | 7 | (DP) | 3930000
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 13 | CONSTRUCTION | FY 2028 - | 27 | (BGDA) | 3818000
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 13 | CONSTRUCTION | FY 2028 - | 36 | (L) | 3930000
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 13 | CONSTRUCTION | FY 2028 - | 36 | (L) | 955000
2025-07-09 | HANDOUT | MODIFICATION | RX-2006A | 13 | CONSTRUCTION | FY 2026 - | 21 | (RR) | 800000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818A | 21 | CAPITAL | FY 2025 - | 36 | (L) | 1108000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818A | 21 | CAPITAL | FY 2025 - | 79 | (5339) | 433000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818A | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 4000000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 21 | CAPITAL | FY 2025 - | 36 | (L) | 1000000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 21 | CAPITAL | FY 2025 - | 36 | (L) | 114000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 21 | CAPITAL | FY 2025 - | 79 | (5309) | 226000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 21 | CAPITAL | FY 2025 - | 79 | (5339) | 227000
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 4000000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2026 - | 36 | (L) | 1120000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2028 - | 36 | (L) | 840000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2025 - | 36 | (L) | 1120000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2027 - | 36 | (L) | 840000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2028 - | 79 | (5307) | 2520000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2028 - | 79 | (5339) | 840000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2027 - | 79 | (5339) | 840000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2026 - | 79 | (5339) | 1120000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 3360000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 3360000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2025 - | 79 | (5339) | 1120000
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 21 | CAPITAL | FY 2027 - | 79 | (5307) | 2520000
2025-07-09 | HANDOUT | MODIFICATION | TA-5140 | 21 | CAPITAL | FY 2025 - | 22 | (L) | 5000
2025-07-09 | HANDOUT | MODIFICATION | TA-5140 | 21 | CAPITAL | FY 2025 - | 79 | (CPF) | 2000000
2025-07-09 | HANDOUT | MODIFICATION | TA-5229 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 180000
2025-07-09 | HANDOUT | MODIFICATION | TA-5229 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 37000
2025-07-09 | HANDOUT | MODIFICATION | TA-5229 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 9000
2025-07-09 | HANDOUT | MODIFICATION | TA-5229 | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 543000
2025-07-09 | HANDOUT | MODIFICATION | TA-6703 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 644000
2025-07-09 | HANDOUT | MODIFICATION | TA-6703 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 4292000
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 1 | ENGINEERING | FY 2025 - | 27 | (BGDA) | 1008900
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 1 | ENGINEERING | FY 2026 - | 27 | (BGDA) | 112100
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 1 | ENGINEERING | FY 2025 - | 28 | (T(M)) | 214200
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 1 | ENGINEERING | FY 2026 - | 28 | (T(M)) | 23800
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 1 | ENGINEERING | FY 2025 - | 36 | (L(M)) | 135900
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 1 | ENGINEERING | FY 2026 - | 36 | (L(M)) | 15100
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2025 - | 6 | (CMAQ) | 275500
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2026 - | 6 | (CMAQ) | 14500
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2026 - | 27 | (BGDA) | 33150
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2025 - | 27 | (BGDA) | 629850
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (T(M)) | 8850
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2025 - | 28 | (T(M)) | 168150
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2025 - | 36 | (L(M)) | 120650
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 6350
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 13 | CONSTRUCTION | FY 2025 - | 6 | (CMAQ) | 3677000
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 3677000
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 13 | CONSTRUCTION | FY 2025 - | 28 | (T(M)) | 780000
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T(M)) | 780000
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 13 | CONSTRUCTION | FY 2025 - | 36 | (L(M)) | 495500
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 495500
2025-07-09 | HANDOUT | MODIFICATION | TC-0042 | 21 | CAPITAL | FY 2025 - | 22 | (S) | 15000
2025-07-09 | HANDOUT | MODIFICATION | TC-0042 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 60000
2025-07-09 | HANDOUT | MODIFICATION | TC-0043 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 274000
2025-07-09 | HANDOUT | MODIFICATION | TC-0043 | 21 | CAPITAL | FY 2025 - | 79 | (5310) | 274000
2025-07-09 | HANDOUT | MODIFICATION | TC-0044 |  | CAPITAL | FY 2026 - |  | (FED) | 250000
2025-07-09 | HANDOUT | MODIFICATION | TC-0044 |  | CAPITAL | FY 2025 - |  | (L) | 63000
2025-07-09 | HANDOUT | MODIFICATION | TC-0044 |  | CAPITAL | FY 2025 - |  | (FED) | 250000
2025-07-09 | HANDOUT | MODIFICATION | TC-0044 |  | CAPITAL | FY 2026 - |  | (L) | 63000
2025-07-09 | HANDOUT | MODIFICATION | TC-0045 |  | CAPITAL | FY 2025 - |  | (L) | 153000
2025-07-09 | HANDOUT | MODIFICATION | TC-0045 |  | CAPITAL | FY 2025 - |  | (5307) | 612000
2025-07-09 | HANDOUT | MODIFICATION | TD-5305 | 13 | CONSTRUCTION | FY 2025 - | 36 | (L) | 65000000
2025-07-09 | HANDOUT | MODIFICATION | TD-5308 | 13 | CONSTRUCTION | FY 2025 - | 7 | (DP) | 9966000
2025-07-09 | HANDOUT | MODIFICATION | TD-5308 | 13 | CONSTRUCTION | FY 2025 - | 36 | (L) | 42315000
2025-07-09 | HANDOUT | MODIFICATION | TD-5308 | 13 | CONSTRUCTION | FY 2025 - | 79 | (5339) | 3888000
2025-07-09 | HANDOUT | MODIFICATION | TG-0011 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 202000
2025-07-09 | HANDOUT | MODIFICATION | TG-0011 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 1012000
2025-07-09 | HANDOUT | MODIFICATION | TG-0013 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 1710000
2025-07-09 | HANDOUT | MODIFICATION | TG-0013 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 1710000
2025-07-09 | HANDOUT | MODIFICATION | TG-0013 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 6840000
2025-07-09 | HANDOUT | MODIFICATION | TG-0013 | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 6840000
2025-07-09 | HANDOUT | MODIFICATION | TG-0015 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 232000
2025-07-09 | HANDOUT | MODIFICATION | TG-0015 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 927000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 257000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 134000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2027 - | 36 | (L) | 134000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2028 - | 36 | (L) | 134000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2025 - | 79 | (5339) | 1028000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2026 - | 79 | (5339) | 536000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2027 - | 79 | (5339) | 536000
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 21 | CAPITAL | FY 2028 - | 79 | (5339) | 536000
2025-07-09 | HANDOUT | MODIFICATION | TG-0031 |  | CONSTRUCTION | FY 2026 - |  | (T) | 159000
2025-07-09 | HANDOUT | MODIFICATION | TG-0031 |  | CONSTRUCTION | FY 2026 - |  | (5307) | 1272000
2025-07-09 | HANDOUT | MODIFICATION | TG-0031 |  | CONSTRUCTION | FY 2026 - |  | (L) | 159000
2025-07-09 | HANDOUT | MODIFICATION | TG-4752B | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 201000
2025-07-09 | HANDOUT | MODIFICATION | TG-4752B | 20 | OPERATIONS | FY 2025 - | 79 | (5307) | 803000
2025-07-09 | HANDOUT | MODIFICATION | TG-4752C | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 140000
2025-07-09 | HANDOUT | MODIFICATION | TG-4752C | 20 | OPERATIONS | FY 2025 - | 79 | (5307) | 560000
2025-07-09 | HANDOUT | MODIFICATION | TG-4792B | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 6900000
2025-07-09 | HANDOUT | MODIFICATION | TG-4792B | 20 | OPERATIONS | FY 2026 - | 36 | (L) | 6900000
2025-07-09 | HANDOUT | MODIFICATION | TG-4792B | 20 | OPERATIONS | FY 2025 - | 79 | (5307) | 6900000
2025-07-09 | HANDOUT | MODIFICATION | TG-4792B | 20 | OPERATIONS | FY 2026 - | 79 | (5307) | 6900000
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B |  | OPERATIONS | FY 2025 - |  | (L) | 1111000
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B |  | OPERATIONS | FY 2025 - |  | (5339) | 4444000
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B | 21 | CAPITAL | FY 2025 - | 36 | (L) | 2550000
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 10199000
2025-07-09 | HANDOUT | MODIFICATION | TG-4935A | 21 | CAPITAL | FY 2025 - | 36 | (L) | 3620000
2025-07-09 | HANDOUT | MODIFICATION | TG-4935A | 21 | CAPITAL | FY 2025 - | 79 | (5309) | 200000
2025-07-09 | HANDOUT | MODIFICATION | TG-4935A | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 2300000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2028 - | 36 | (L) | 14000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2027 - | 36 | (L) | 14000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 14000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 39000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2028 - | 79 | (5339) | 56000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2027 - | 79 | (5339) | 56000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2026 - | 79 | (5339) | 56000
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 21 | CAPITAL | FY 2025 - | 79 | (5339) | 156000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2027 - | 36 | (L) | 42000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2028 - | 36 | (L) | 42000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2026 - | 36 | (L) | 42000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2028 - | 79 | (5339) | 42000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2027 - | 79 | (5307) | 126000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2027 - | 79 | (5339) | 42000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 126000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2026 - | 79 | (5339) | 42000
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 21 | CAPITAL | FY 2028 - | 79 | (5307) | 126000
2025-07-09 | HANDOUT | MODIFICATION | TG-6143 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 164000
2025-07-09 | HANDOUT | MODIFICATION | TG-6143 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 655000
2025-07-09 | HANDOUT | MODIFICATION | TG-6181 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 557000
2025-07-09 | HANDOUT | MODIFICATION | TG-6181 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 49000
2025-07-09 | HANDOUT | MODIFICATION | TG-6181 | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 262000
2025-07-09 | HANDOUT | MODIFICATION | TG-6181 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 197000
2025-07-09 | HANDOUT | MODIFICATION | TG-6183B | 21 | CAPITAL | FY 2025 - | 29 | (5312) | 2110000
2025-07-09 | HANDOUT | MODIFICATION | TG-6183B | 21 | CAPITAL | FY 2026 - | 29 | (5312) | 1750000
2025-07-09 | HANDOUT | MODIFICATION | TG-6183B | 21 | CAPITAL | FY 2025 - | 36 | (L) | 507000
2025-07-09 | HANDOUT | MODIFICATION | TG-6183B | 21 | CAPITAL | FY 2026 - | 36 | (L) | 392000
2025-07-09 | HANDOUT | MODIFICATION | TL-0035 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L) | 38744000
2025-07-09 | HANDOUT | MODIFICATION | TL-0035 | 13 | CONSTRUCTION | FY 2027 - | 79 | (5307) | 162804000
2025-07-09 | HANDOUT | MODIFICATION | TL-0062 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CPF) | 680000
2025-07-09 | HANDOUT | MODIFICATION | TL-0062 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 170000
2025-07-09 | HANDOUT | ADDITION | TL-0065 | 21 | CAPITAL | FY 2026 - | 29 | (CRPDA) | 863000
2025-07-09 | HANDOUT | ADDITION | TL-0065 | 21 | CAPITAL | FY 2025 - | 29 | (CRPDA) | 863000
2025-07-09 | HANDOUT | ADDITION | TL-0065 | 21 | CAPITAL | FY 2026 - | 36 | (L(M)) | 319000
2025-07-09 | HANDOUT | ADDITION | TL-0065 | 21 | CAPITAL | FY 2025 - | 36 | (L(M)) | 319000
2025-07-09 | HANDOUT | MODIFICATION | TL-0068 | 1 | ENGINEERING | FY 2025 - | 7 | (DP) | 2000000
2025-07-09 | HANDOUT | MODIFICATION | TL-0068 | 1 | ENGINEERING | FY 2025 - | 36 | (L(M)) | 500000
2025-07-09 | HANDOUT | MODIFICATION | TM-0040 | 1 | PLANNING | FY 2025 - | 79 | (ARP) | 600000
2025-07-09 | HANDOUT | MODIFICATION | TM-0040 | 1 | PLANNING | FY 2026 - | 79 | (ARP) | 150000
2025-07-09 | HANDOUT | MODIFICATION | TM-0058 | 13 | OPERATIONS | FY 2025 - | 36 | (L) | 53000
2025-07-09 | HANDOUT | MODIFICATION | TM-0058 | 13 | OPERATIONS | FY 2025 - | 79 | (5307) | 213000
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 429000
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 10000
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 429000
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 429000
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 21 | CAPITAL | FY 2025 - | 79 | (5339) | 42000
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 21 | CAPITAL | FY 2025 - | 79 | (5307) | 429000
2025-07-09 | HANDOUT | MODIFICATION | TN-6116 | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 1400000
2025-07-09 | HANDOUT | MODIFICATION | TN-6116 | 20 | OPERATIONS | FY 2026 - | 36 | (L) | 1400000
2025-07-09 | HANDOUT | MODIFICATION | TN-6116 | 20 | OPERATIONS | FY 2025 - | 79 | (5307) | 1400000
2025-07-09 | HANDOUT | MODIFICATION | TN-6116 | 20 | OPERATIONS | FY 2026 - | 79 | (5307) | 1400000
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 20 | OPERATIONS | FY 2026 - | 6 | (CMAQ) | 800000
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 20 | OPERATIONS | FY 2028 - | 6 | (CMAQ) | 800000
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 20 | OPERATIONS | FY 2027 - | 6 | (CMAQ) | 800000
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 20 | OPERATIONS | FY 2026 - | 36 | (L(M)) | 200000
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 20 | OPERATIONS | FY 2027 - | 36 | (L(M)) | 200000
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 20 | OPERATIONS | FY 2028 - | 63 | (L(M)) | 200000
2025-07-09 | HANDOUT | MODIFICATION | TO-4719 | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 1680000
2025-07-09 | HANDOUT | MODIFICATION | TO-4719 | 20 | OPERATIONS | FY 2025 - | 79 | (5307) | 1680000
2025-07-09 | HANDOUT | MODIFICATION | TO-6106 | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 190000
2025-07-09 | HANDOUT | MODIFICATION | TO-6106 | 20 | OPERATIONS | FY 2026 - | 36 | (L) | 278000
2025-07-09 | HANDOUT | MODIFICATION | TO-6106 | 20 | OPERATIONS | FY 2025 - | 79 | (5307) | 190000
2025-07-09 | HANDOUT | MODIFICATION | TO-6106 | 20 | OPERATIONS | FY 2026 - | 79 | (5307) | 278000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2028 - | 36 | (L) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2026 - | 36 | (L) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2029 - | 36 | (L) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 85000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2030 - | 36 | (L) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2027 - | 36 | (L) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2030 - | 79 | (5310) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2029 - | 79 | (5310) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2027 - | 79 | (5310) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2026 - | 79 | (5310) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2025 - | 79 | (5310) | 85000
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 20 | OPERATIONS | FY 2028 - | 79 | (5310) | 35000
2025-07-09 | HANDOUT | MODIFICATION | TP-5100B | 1 | PLANNING | FY 2026 - | 36 | (L) | 750000
2025-07-09 | HANDOUT | MODIFICATION | TP-5100B | 1 | PLANNING | FY 2025 - | 36 | (L) | 750000
2025-07-09 | HANDOUT | MODIFICATION | TP-5100B | 1 | PLANNING | FY 2026 - | 79 | (5307) | 3000000
2025-07-09 | HANDOUT | MODIFICATION | TP-5100B | 1 | PLANNING | FY 2025 - | 79 | (5307) | 3000000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2025 - | 22 | (S) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2026 - | 22 | (S) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2027 - | 22 | (S) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2028 - | 22 | (S) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2026 - | 36 | (L(M)) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2028 - | 36 | (L(M)) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2027 - | 36 | (L(M)) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2025 - | 36 | (L(M)) | 8000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2027 - | 79 | (5303) | 57000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2028 - | 79 | (5303) | 57000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2025 - | 79 | (5303) | 57000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 1 | PLANNING | FY 2026 - | 79 | (5303) | 57000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 31 | ADMINISTRATIVE | FY 2025 - | 36 | (L(M)) | 9000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 31 | ADMINISTRATIVE | FY 2025 - | 61 | (HF) | 9000
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 31 | ADMINISTRATIVE | FY 2025 - | 79 | (5303) | 67000
2025-07-09 | HANDOUT | DELETION | TP-5112 |  | PLANNING | FY 2025 - |  | (L) | 56000
2025-07-09 | HANDOUT | DELETION | TP-5112 |  | PLANNING | FY 2025 - |  | (5307) | 280000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 164000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 84000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2027 - | 36 | (L) | 84000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2030 - | 36 | (L) | 84000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2028 - | 36 | (L) | 84000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2029 - | 36 | (L) | 84000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2029 - | 79 | (5310) | 335000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2027 - | 79 | (5310) | 335000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2026 - | 79 | (5310) | 335000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2030 - | 79 | (5310) | 335000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2025 - | 79 | (5310) | 656000
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 21 | CAPITAL | FY 2028 - | 79 | (5310) | 335000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 20 | OPERATIONS | FY 2025 - | 36 | (L) | 625000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 20 | OPERATIONS | FY 2026 - | 36 | (L) | 625000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 20 | OPERATIONS | FY 2026 - | 79 | (5310) | 2500000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 20 | OPERATIONS | FY 2025 - | 79 | (5310) | 2500000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 21 | CAPITAL | FY 2026 - | 36 | (L) | 625000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 21 | CAPITAL | FY 2025 - | 36 | (L) | 625000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 21 | CAPITAL | FY 2026 - | 79 | (5310) | 2500000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 21 | CAPITAL | FY 2025 - | 79 | (5310) | 2500000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 31 | ADMINISTRATIVE | FY 2026 - | 36 | (L) | 390000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 31 | ADMINISTRATIVE | FY 2025 - | 36 | (L) | 390000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 31 | ADMINISTRATIVE | FY 2025 - | 79 | (5310) | 1560000
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 31 | ADMINISTRATIVE | FY 2026 - | 79 | (5310) | 1560000
2025-07-09 | HANDOUT | MODIFICATION | TU-0010 |  | CAPITAL | FY 2025 - |  | (L) | 50000
2025-07-09 | HANDOUT | MODIFICATION | TU-0010 |  | CAPITAL | FY 2026 - |  | (L) | 50000
2025-07-09 | HANDOUT | MODIFICATION | TU-0010 |  | CAPITAL | FY 2026 - |  | (5307) | 200000
2025-07-09 | HANDOUT | MODIFICATION | TU-0013 | 1 | CAPITAL | FY 2025 - | 36 | (L) | 9963000
2025-07-09 | HANDOUT | MODIFICATION | TU-0013 | 1 | CAPITAL | FY 2025 - | 79 | (5339(b)) | 10732000
2025-07-09 | HANDOUT | MODIFICATION | TU-0020 | 1 | PLANNING | FY 2025 - | 7 | (DP) | 268000
2025-07-09 | HANDOUT | MODIFICATION | TU-0020 | 1 | PLANNING | FY 2025 - | 36 | (L) | 67000
2025-07-09 | HANDOUT | MODIFICATION | TU-0021 | 1 | PLANNING | FY 2025 - | 22 | (S) | 30000
2025-07-09 | HANDOUT | MODIFICATION | TU-0021 | 1 | PLANNING | FY 2025 - | 36 | (L) | 30000
2025-07-09 | HANDOUT | MODIFICATION | TU-0021 | 1 | PLANNING | FY 2025 - | 79 | (5303) | 242000
2025-07-09 | HANDOUT | MODIFICATION | U-4700CC | 13 | CONSTRUCTION | FY 2026 - | 16 | (NHP) | 83000
2025-07-09 | HANDOUT | MODIFICATION | U-4700CC | 13 | CONSTRUCTION | FY 2028 - | 16 | (NHP) | 3217000
2025-07-09 | HANDOUT | MODIFICATION | U-4700CC | 13 | CONSTRUCTION | FY 2029 - | 16 | (NHP) | 950000
2025-07-09 | HANDOUT | MODIFICATION | U-4700CC | 13 | CONSTRUCTION | FY 2027 - | 16 | (NHP) | 4050000
2025-07-09 | HANDOUT | MODIFICATION | U-4726HO | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (TADA) | 22000
2025-07-09 | HANDOUT | MODIFICATION | U-4726HO | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L) | 5000
2025-07-09 | HANDOUT | MODIFICATION | U-4726HO | 13 | CONSTRUCTION | FY 2026 - | 26 | (BGANY) | 6305000
2025-07-09 | HANDOUT | MODIFICATION | U-4726HO | 13 | CONSTRUCTION | FY 2026 - | 36 | (L) | 1576000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 7 | RIGHT-OF-WAY | FY 2027 - | 28 | (T) | 5722000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 7 | RIGHT-OF-WAY | FY 2030 - | 28 | (T) | 11680000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 7 | RIGHT-OF-WAY | FY 2028 - | 28 | (T) | 5722000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 7 | RIGHT-OF-WAY | FY 2029 - | 28 | (T) | 5722000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (T) | 954000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 8 | UTILITIES | FY 2026 - | 28 | (T) | 10000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 13 | CONSTRUCTION | FY 2033 - | 28 | (T) | 12070000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 13 | CONSTRUCTION | FY 2032 - | 28 | (T) | 16330000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 13 | CONSTRUCTION | FY 2031 - | 28 | (T) | 20590000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 13 | CONSTRUCTION | FY 2030 - | 28 | (T) | 21300000
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 13 | CONSTRUCTION | FY 2029 - | 28 | (T) | 710000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 7 | RIGHT-OF-WAY | FY 2028 - | 28 | (T) | 3495000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (T) | 582000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 7 | RIGHT-OF-WAY | FY 2027 - | 28 | (T) | 3495000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 7 | RIGHT-OF-WAY | FY 2029 - | 28 | (T) | 3495000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 7 | RIGHT-OF-WAY | FY 2030 - | 28 | (T) | 7133000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 8 | UTILITIES | FY 2026 - | 28 | (T) | 10000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 13 | CONSTRUCTION | FY 2033 - | 28 | (T) | 14562000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 13 | CONSTRUCTION | FY 2029 - | 28 | (T) | 809000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 13 | CONSTRUCTION | FY 2030 - | 28 | (T) | 22652000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 13 | CONSTRUCTION | FY 2031 - | 28 | (T) | 23461000
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 13 | CONSTRUCTION | FY 2032 - | 28 | (T) | 19416000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 7 | RIGHT-OF-WAY | FY 2026 - | 26 | (BGANY) | 2700000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 7 | RIGHT-OF-WAY | FY 2027 - | 26 | (BGANY) | 2700000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 600000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2028 - | 26 | (BGANY) | 1920000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2029 - | 26 | (BGANY) | 2268000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2030 - | 26 | (BGANY) | 1798000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2030 - | 26 | (BGANY) | 1472000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2031 - | 26 | (BGANY) | 1088000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2031 - | 26 | (BGANY) | 1329000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2029 - | 26 | (BGANY) | 1856000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2028 - | 26 | (BGANY) | 2346000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2027 - | 26 | (BGANY) | 78000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2027 - | 26 | (BGANY) | 64000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2027 - | 31 | (O) | 359000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2029 - | 31 | (O) | 10406000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2028 - | 31 | (O) | 10764000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2031 - | 31 | (O) | 6100000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2030 - | 31 | (O) | 8252000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 78000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2030 - | 36 | (L(M)) | 1798000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 16000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2031 - | 36 | (L(M)) | 272000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2030 - | 36 | (L(M)) | 368000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2028 - | 36 | (L(M)) | 2346000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2028 - | 36 | (L(M)) | 480000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2029 - | 36 | (L(M)) | 464000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2029 - | 36 | (L(M)) | 2268000
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 13 | CONSTRUCTION | FY 2031 - | 36 | (L(M)) | 1329000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 27 | (BGDA) | 7773000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T) | 651000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2029 - | 28 | (T(DA)) | 397000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2029 - | 28 | (T) | 240000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2028 - | 28 | (T(DA)) | 775000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T(DA)) | 1080000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T(DA)) | 23000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T) | 14000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2028 - | 28 | (T) | 467000
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L) | 7773000
2025-07-09 | HANDOUT | MODIFICATION | W-5705G | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 790000
2025-07-09 | HANDOUT | MODIFICATION | W-5805G | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 1380000
2025-07-09 | HANDOUT | MODIFICATION | W-5805G | 13 | CONSTRUCTION | FY 2027 - | 10 | (HSIP) | 435000

## County Division
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | IDNUM | PERCENT | COUNTY | DIVISION
2025-07-09 | HANDOUT | MODIFICATION | BF-0002 | 100 | TRANSYLVANIA | 14
2025-07-09 | HANDOUT | MODIFICATION | BL-0078 | 100 | HENDERSON | 14
2025-07-09 | HANDOUT | MODIFICATION | BL-0087 | 100 | CABARRUS | 10
2025-07-09 | HANDOUT | ADDITION | BL-0167 | 100 | CRAVEN | 2
2025-07-09 | HANDOUT | MODIFICATION | BN-0016 | 100 | MITCHELL | 13
2025-07-09 | HANDOUT | ADDITION | BR-0153 | 100 | BERTIE | 1
2025-07-09 | HANDOUT | DELETION | EB-5850 | 100 | WAYNE | 4
2025-07-09 | HANDOUT | MODIFICATION | EB-5900 | 100 | GUILFORD | 7
2025-07-09 | HANDOUT | MODIFICATION | F-5707 | 50 | BRUNSWICK | 3
2025-07-09 | HANDOUT | MODIFICATION | F-5707 | 50 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | HE-0001B | 100 | BUNCOMBE | 13
2025-07-09 | HANDOUT | MODIFICATION | HE-0007A | 100 | DURHAM | 5
2025-07-09 | HANDOUT | MODIFICATION | HL-0049 | 100 | ROWAN | 9
2025-07-09 | HANDOUT | MODIFICATION | HL-0062 | 100 | CABARRUS | 10
2025-07-09 | HANDOUT | DELETION | HN-0021 | 100 | ROBESON | 6
2025-07-09 | HANDOUT | ADDITION | HN-0042 | 100 | ANSON | 10
2025-07-09 | HANDOUT | MODIFICATION | HO-0001AB | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | HS-2003AD | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2003AI | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2003I | 100 | DUPLIN | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2401Q | 36 | NORTHAMPTON | 1
2025-07-09 | HANDOUT | MODIFICATION | HS-2401Q | 30 | CHOWAN | 1
2025-07-09 | HANDOUT | MODIFICATION | HS-2401Q | 26 | GATES | 1
2025-07-09 | HANDOUT | MODIFICATION | HS-2401Q | 8 | TYRRELL | 1
2025-07-09 | HANDOUT | MODIFICATION | HS-2402G | 100 | PITT | 2
2025-07-09 | HANDOUT | MODIFICATION | HS-2402O | 100 | PITT | 2
2025-07-09 | HANDOUT | MODIFICATION | HS-2403L | 100 | DUPLIN | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2403M | 100 | PENDER | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2403N | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2403O | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2403P | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2403Q | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | HS-2405BA | 80 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | HS-2405BA | 20 | FRANKLIN | 5
2025-07-09 | HANDOUT | MODIFICATION | HS-2405J | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | HS-2405O | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | HS-2410A | 100 | CABARRUS | 10
2025-07-09 | HANDOUT | MODIFICATION | HS-2410L | 100 | MECKLENBURG | 10
2025-07-09 | HANDOUT | DELETION | I-5719E | 70 | GASTON | 12
2025-07-09 | HANDOUT | DELETION | I-5719E | 30 | CLEVELAND | 12
2025-07-09 | HANDOUT | ADDITION | M-0570 | 100 | STATEWIDE | 99
2025-07-09 | HANDOUT | MODIFICATION | M-0570L | 100 | PITT | 2
2025-07-09 | HANDOUT | MODIFICATION | M-0570M | 100 | LENOIR | 2
2025-07-09 | HANDOUT | MODIFICATION | M-0570N | 100 | PAMLICO | 2
2025-07-09 | HANDOUT | MODIFICATION | M-0570P | 95 | PENDER | 3
2025-07-09 | HANDOUT | MODIFICATION | M-0570P | 5 | ONSLOW | 3
2025-07-09 | HANDOUT | MODIFICATION | M-0570Q | 100 | PENDER | 3
2025-07-09 | HANDOUT | MODIFICATION | M-0570R | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | M-0570S | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | M-0570T | 100 | ORANGE | 7
2025-07-09 | HANDOUT | MODIFICATION | M-0570U | 100 | MECKLENBURG | 10
2025-07-09 | HANDOUT | MODIFICATION | R-5020AA | 100 | COLUMBUS | 6
2025-07-09 | HANDOUT | MODIFICATION | R-5711 | 100 | IREDELL | 12
2025-07-09 | HANDOUT | MODIFICATION | R-5830 | 100 | WATAUGA | 11
2025-07-09 | HANDOUT | MODIFICATION | RL-0001 | 100 | IREDELL | 12
2025-07-09 | HANDOUT | MODIFICATION | RX-2006A | 100 | CUMBERLAND | 6
2025-07-09 | HANDOUT | MODIFICATION | TA-4818A | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 50 | DURHAM | 5
2025-07-09 | HANDOUT | MODIFICATION | TA-4818B | 50 | ORANGE | 7
2025-07-09 | HANDOUT | MODIFICATION | TA-4948A | 100 | CUMBERLAND | 6
2025-07-09 | HANDOUT | MODIFICATION | TA-5140 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TA-5229 | 100 | HENDERSON | 14
2025-07-09 | HANDOUT | MODIFICATION | TA-6703 | 100 | BUNCOMBE | 13
2025-07-09 | HANDOUT | MODIFICATION | TA-6724 | 100 | MECKLENBURG | 10
2025-07-09 | HANDOUT | MODIFICATION | TC-0042 | 100 | ORANGE | 7
2025-07-09 | HANDOUT | MODIFICATION | TC-0043 | 100 | ORANGE | 7
2025-07-09 | HANDOUT | MODIFICATION | TC-0044 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TC-0045 | 100 | NEW HANOVER | 3
2025-07-09 | HANDOUT | MODIFICATION | TD-5305 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TD-5308 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-0011 | 100 | BUNCOMBE | 13
2025-07-09 | HANDOUT | MODIFICATION | TG-0013 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-0015 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-0019 | 100 | GUILFORD | 7
2025-07-09 | HANDOUT | MODIFICATION | TG-0031 | 100 | DURHAM | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-4752B | 100 | WAYNE | 4
2025-07-09 | HANDOUT | MODIFICATION | TG-4752C | 100 | WAYNE | 4
2025-07-09 | HANDOUT | MODIFICATION | TG-4792B | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B | 50 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B | 30 | DURHAM | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-4821B | 20 | ORANGE | 7
2025-07-09 | HANDOUT | MODIFICATION | TG-4935A | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TG-5105 | 100 | GUILFORD | 7
2025-07-09 | HANDOUT | MODIFICATION | TG-5224C | 100 | CUMBERLAND | 6
2025-07-09 | HANDOUT | MODIFICATION | TG-6143 | 100 | HENDERSON | 14
2025-07-09 | HANDOUT | MODIFICATION | TG-6181 | 100 | HENDERSON | 14
2025-07-09 | HANDOUT | MODIFICATION | TG-6183B | 100 | BUNCOMBE | 13
2025-07-09 | HANDOUT | MODIFICATION | TL-0035 | 100 | ORANGE | 7
2025-07-09 | HANDOUT | MODIFICATION | TL-0062 | 100 | ORANGE | 7
2025-07-09 | HANDOUT | ADDITION | TL-0065 | 100 | DURHAM | 5
2025-07-09 | HANDOUT | MODIFICATION | TL-0068 | 100 | GUILFORD | 7
2025-07-09 | HANDOUT | MODIFICATION | TM-0040 | 100 | MECKLENBURG | 10
2025-07-09 | HANDOUT | MODIFICATION | TM-0058 | 100 | GASTON | 12
2025-07-09 | HANDOUT | MODIFICATION | TM-0066 | 100 | ORANGE | 7
2025-07-09 | HANDOUT | MODIFICATION | TN-6116 | 100 | WAKE | 5
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 50 | EDGECOMBE | 4
2025-07-09 | HANDOUT | ADDITION | TN-6136 | 50 | NASH | 4
2025-07-09 | HANDOUT | MODIFICATION | TO-4719 | 100 | WAYNE | 4
2025-07-09 | HANDOUT | MODIFICATION | TO-6106 | 100 | HENDERSON | 14
2025-07-09 | HANDOUT | MODIFICATION | TO-6139 | 100 | GUILFORD | 7
2025-07-09 | HANDOUT | MODIFICATION | TP-5100B | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 25 | ALEXANDER | 12
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 25 | BURKE | 13
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 25 | CALDWELL | 11
2025-07-09 | HANDOUT | MODIFICATION | TP-5106 | 25 | CATAWBA | 12
2025-07-09 | HANDOUT | DELETION | TP-5112 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TQ-6783 | 100 | GUILFORD | 7
2025-07-09 | HANDOUT | MODIFICATION | TQ-9037 | 100 | WAKE | 5
2025-07-09 | HANDOUT | MODIFICATION | TU-0010 | 100 | HENDERSON | 14
2025-07-09 | HANDOUT | MODIFICATION | TU-0013 | 100 | DURHAM | 5
2025-07-09 | HANDOUT | MODIFICATION | TU-0020 | 100 | BUNCOMBE | 13
2025-07-09 | HANDOUT | MODIFICATION | TU-0021 | 100 | GUILFORD | 7
2025-07-09 | HANDOUT | MODIFICATION | U-4700CC | 100 | CALDWELL | 11
2025-07-09 | HANDOUT | MODIFICATION | U-4726HO | 100 | DURHAM | 5
2025-07-09 | HANDOUT | MODIFICATION | U-5769A | 100 | UNION | 10
2025-07-09 | HANDOUT | MODIFICATION | U-5769B | 100 | UNION | 10
2025-07-09 | HANDOUT | MODIFICATION | U-5803 | 100 | MECKLENBURG | 10
2025-07-09 | HANDOUT | MODIFICATION | U-5906 | 100 | MECKLENBURG | 10
2025-07-09 | HANDOUT | MODIFICATION | W-5705G | 100 | VANCE | 5
2025-07-09 | HANDOUT | MODIFICATION | W-5805G | 100 | VANCE | 5