## Project Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | MPOsRPOs | IDNUM | PROJ_ID | ROUTES | DESCRIPTION | AGENDA_COMMENT | FUNDING_COMMENT | FEDERAL_AMENDMENT | CATEGORY
2025-09-04 | HANDOUT | MODIFICATION | Southwestern RPO | B-6029 | B-6029 | SR 1001 (ELLIJAY ROAD) | SR 1001 (ELLIJAY ROAD), BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. REPLACE BRIDGE. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Southwestern RPO | B-6034 | B-6034 | SR 1300 (PUMPKINTOWN ROAD) | SR 1300 (PUMPKINTOWN ROAD), BRIDGE 490065 OVER SAVANNAH CREEK. REPLACE BRIDGE. | TO REFLECT THE LATEST DELIVERY SCHEDULE, ACCELERATE CONSTRUCTION FROM FY 27 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Upper Coastal Plain RPO | B-6050 | B-6050 | SR 2137 (PITTMAN ROAD); SR 2130 (EAST MAIN STREET); SR 2339 (BAGLEY ROAD) | SR 2137 (PITTMAN ROAD); SR 2130 (EAST MAIN STREET); SR 2339 (BAGLEY ROAD), BRIDGES 500109, 500110, 500112 OVER I-95. REPLACE BRIDGES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY & UTILITIES FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | BL-0009 | BL-0009 | NC 152 (NORTH MAIN STREET) | NC 152 (NORTH MAIN STREET), PINE STREET TO NORTH MAIN PARK IN HENDERSONVILLE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | TO REFLECT THE LATEST DELIVERY SCHEDULE, DELAY PRELIMINARY ENGINEERING FROM FY 24 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Rocky Mount Urban Area MPO | BL-0032 | BL-0032 | SR 1164 (COKEY ROAD); REX STREET | SR 1164 (COKEY ROAD); REX STREET, CSX RAILROAD TO WINTERGREEN COURT; OLD WILSON ROAD TO SR 1164 (COKEY ROAD). CONSTRUCT SIDEWALK. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | MODIFICATION | Capital Area MPO | BL-0050 | BL-0050 | SR 1004 (EAST MAIN STREET) | SR 1004 (EAST MAIN STREET), SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | TO REFLECT THE LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | ADDITION |  | BL-0176 | BL-0176 | ABERDEEN | ABERDEEN. POPLAR STREET FROM PEACH AVENUE TO PROVIDENCE PLACE/JOHNSON STREET. CONSTRUCT SIDEWALK. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | Y | EX
2025-09-04 | HANDOUT | MODIFICATION | Eastern Carolina RPO | BN-0008 | BN-0008 | KINSTON RIVERWALK | KINSTON RIVERWALK, CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | MODIFICATION | Rocky Mount Urban Area MPO | BO-2417 | BO-2417 | US 64 BUSINESS (THOMAS STREET) | US 64 BUSINESS (THOMAS STREET), MAIN STREET INTERSECTION IN ROCKY MOUNT. CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26 AND CONSTRUCTION FROM FY 26 TO FY 27. |  | N | EX
2025-09-04 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | C-5603F | C-5603 | SR 1643 (BETHPAGE ROAD) | SR 1643 (BETHPAGE ROAD), SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE, AND WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALK. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | C-5603I | C-5603 | US 601 | US 601, SR 1132 (FLOWES STORE ROAD) TO SR 1153 (ZION CHURCH ROAD), AND SR 1132 (FLOWES STORE ROAD) INTERSECTION IN CONCORD. CONSTRUCT SIDEWALKS AND INTERSECTION IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | C-5613J | C-5613 | NC 115 | NC 115, HICKORY STREET INTERSECTION IN CORNELIUS. CONSTRUCT INTERSECTION IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | EB-5600 | EB-5600 | SR 1219 (SOUTH 17TH STREET) | SR 1219 (SOUTH 17TH STREET), HARBOUR DRIVE TO SHIPYARD BOULEVARD IN WILMINGTON. CONSTRUCT MULTI-USE PATH. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | EB-5723 | EB-5723 | US 74 | US 74, SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD); SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE IN INDIAN TRAIL. CONSTRUCT MULTI-USE PATH. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY RIGHT-OF-WAY FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | EB-5783 | EB-5783 | SR 3168 (SAM NEWELL ROAD) | SR 3168 (SAM NEWELL ROAD), NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL IN MATTHEWS. CONSTRUCT GREENWAY. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | High Country RPO | EB-5924 | EB-5924 | NEW ROUTE | NEW ROUTE, MIDDLE FORK GREENWAY IN BLOWING ROCK. CONSTRUCT GREENWAY. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY CONSTRUCTION FROM FY 24 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | EB-5931 | EB-5931 | NORTH INDIAN TRAIL ROAD | NORTH INDIAN TRAIL ROAD, SR 1371 (SOUTHFORK ROAD) TO LIBERTY LANE IN INDIAN TRAIL. CONSTRUCT COMPLETE STREET. CONSTRUCT INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD). | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | EB-5933 | EB-5933 | KINCAID MULTI-USE PATH | KINCAID MULTI-USE PATH, EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY IN DAVIDSON. CONSTRUCT MULTI-USE PATH. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | DELETION | Charlotte Regional TPO | EB-5971 | EB-5971 | SR 2151 (JETTON STREET) | SR 2151 (JETTON STREET), GRIFFITH STREET TO SR 6037 (POTTS STREET) IN DAVIDSON. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | REMOVE PROJECT AT THE REQUEST OF THE MPO. |  | Y | DIV
2025-09-04 | HANDOUT | MODIFICATION | Peanut Belt RPO | HB-0070 | HB-0070 | US 13 / US 17 (FUTURE I-87) | US 13 / US 17 (FUTURE I-87), BRIDGES 070155, 070156, 070158, AND 070159 OVER ROANOKE RIVER OVERFLOW. REPAIR BRIDGES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | SW
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | HL-0023 | HL-0023 | REA ROAD | REA ROAD, I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Capital Area MPO | HL-0043 | HL-0043 | SR 1005 (SIX FORKS ROAD) | SR 1005 (SIX FORKS ROAD), SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | ADD UTILITIES IN FY 26 NOT PREVIOUSLY PROGRAMMED. |  | Y | EX
2025-09-04 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | HL-0123 | HL-0123 | VARIOUS | VARIOUS, LOCATIONS IN CONCORD. UPGRADE SOFTWARE FOR CONCORD CITYWIDE SIGNAL SYSTEM. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | EX
2025-09-04 | HANDOUT | ADDITION | Charlotte Regional TPO | HL-0163 | HL-0163 | NC 27 (FREEDOM DRIVE); EASTWAY DRIVE | NC 27 (FREEDOM DRIVE); EASTWAY DRIVE, VALERIE C. WOODARD CENTER AND ELLA B. SCARBOROUGH COMMUNITY RESOURCE CENTER. INSTALL ELECTRIC VEHICLE FAST CHARGING STATIONS. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | Y | EX
2025-09-04 | HANDOUT | ADDITION |  | HL-0175 | HL-0175 | AIRPORT ROAD | AIRPORT ROAD. THORNE ROAD TO KNOLL ROAD IN ABERDEEN. IMPROVE ROADWAY. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | Y | EX
2025-09-04 | HANDOUT | MODIFICATION | Foothills RPO | HN-0019 | HN-0019 | US 64 / US 74A | US 64 / US 74A, NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. CONSTRUCT ROUNDABOUT. | TO REFLECT THE LATEST DELIVERY SCHEDULE, ACCELERATE CONSTRUCTION FROM FY 27 TO FY 26. |  | N | REG
2025-09-04 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2003AK | HS-2003 | SR 1301 (PRINCESS PLACE DRIVE) | SR 1301 (PRINCESS PLACE DRIVE), NORTH 30TH STREET INTERSECTION IN WILMINGTON. CONSTRUCT SAFETY IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR RIGHT-OF-WAY ACQUISITION, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | MODIFICATION | Wilmington Urban Area MPO | HS-2003L | HS-2003 | US 17 / US 76 (OLEANDER DRIVE) | US 17 / US 76 (OLEANDER DRIVE), SR 1421 (GREENVILLE LOOP ROAD / GREENVILLE AVENUE) INTERSECTION IN WILMINGTON. REVISE TRAFFIC SIGNAL. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-09-04 | HANDOUT | MODIFICATION | Northwest Piedmont RPO | HS-2011G | HS-2011 | NC 89 (PINE STREET) | NC 89 (PINE STREET), SR 1345 (BEULAH ROAD / BEULAH CHURCH ROAD) INTERSECTION NEAR LOWGAP. CONSTRUCT ROUNDABOUT. | TO REFLECT LATEST DELIVERY SCHEDULE, DELAY RIGHT-OF-WAY AND UTILITIES FROM FY 25 TO FY 26 AND DELAY CONSTRUCTION FROM FY 26 TO FY 27. |  | N | REG
2025-09-04 | HANDOUT | MODIFICATION | Southwestern RPO | HS-2014W | HS-2014 | US 64 (MURPHY ROAD) | US 64 (MURPHY ROAD), SR 1146 (PATTON ROAD) AND SR 1442 (OLD MURPHY ROAD) INTERSECTIONS NEAR FRANKLIN. CONSTRUCT DIRECTIONAL LEFTOVER WITH U-TURN BULB-OUTS. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-09-04 | HANDOUT | MODIFICATION | Greenville Urban Area MPO | HS-2402Q | HS-2402 | NC 11 / NC 43 / NC 903 (MEMORIAL DRIVE) | NC 11 / NC 43 / NC 903 (MEMORIAL DRIVE), ARLINGTON BOULEVARD INTERSECTION IN GREENVILLE. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND SIDEWALK. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-09-04 | HANDOUT | MODIFICATION | Jacksonville Urban Area MPO | HS-2403AA | HS-2403 | NC 53 (WESTERN BOULEVARD) | NC 53 (WESTERN BOULEVARD), SR 1308 (GUM BRANCH ROAD) INTERSECTION IN JACKSONVILLE. UPGRADE TRAFFIC SIGNAL. | TO ALLOW ADDITIONAL TIME FOR PLANNING AND DESIGN, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | REG
2025-09-04 | HANDOUT | ADDITION |  | HS-2403AW | HS-2403 | NC 133 | NC 133, SR 1518 (DAWS CREEK ROAD) TO SR 1551 (BLACKWELL ROAD). INSTALL RUMBLE STRIPS. | ADD PROJECT AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-09-04 | HANDOUT | ADDITION |  | HS-2403AX | HS-2403 | NC 41 | NC 41, NORTH OF NC 50 TO BEULAVILLE CITY LIMITS. WIDEN ROADWAY AND INSTALL RUMBLE STRIPS. | ADD PROJECT AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-09-04 | HANDOUT | MODIFICATION | Jacksonville Urban Area MPO | HS-2403T | HS-2403 | US 258 / NC 24 | US 258 / NC 24, SR 1320 (WELLS ROAD) TO SR 1238 (KOONCE FORK ROAD) SOUTH OF RICHLANDS. INSTALL RUMBLE STRIPES. | PROJECT COMBINED WITH ONSLOW RESURFACING CONTRACT, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | SW
2025-09-04 | HANDOUT | ADDITION | Charlotte Regional TPO | HS-2410K | HS-2410 | SR 3448 (PLEASANT PLAINS ROAD) | SR 3448 (PLEASANT PLAINS ROAD), SQUIRREL LAKE PARK ENTRANCE INTERSECTION IN MATTHEWS. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. | ADD PROJECT BREAK AT THE REQUEST OF THE TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | HS-2410N | HS-2410 | SR 3468 (WEDDINGTON ROAD) | SR 3468 (WEDDINGTON ROAD), VICINITY OF SOCRATES ACADEMY. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | TO REFLECT LATEST DELIVERY SCHEDULE, ACCELERATE CONSTRUCTION FROM FY 27 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | ADDITION | Greater Hickory MPO | HS-2411D | HS-2411 | US 321 | US 321, SR 1370 (KIRBY MOUNTAIN ROAD) TO GREEN HILL ROAD. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | ADD PROJECT BREAK AT THE REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | SW
2025-09-04 | HANDOUT | ADDITION |  | HS-2412B | HS-2412 | NC 150 | NC 150, NORTH OF SR 2068 (TROY ROAD) TO SR 1651 (DELVIEW ROAD). INSTALL RUMBLE STRIPS WITH SIX INCH LONG LIFE PAVEMENT MARKINGS. | ADD PROJECT BREAK AT THE REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-09-04 | HANDOUT | ADDITION |  | HS-2413Q | HS-2413 | SR 1786 (MILLER BRIDGE ROAD) | SR 1786 (MILLER BRIDGE ROAD), NC 18 AND SR 1761 (OLD NC HIGHWAY 10). INSTALL RUMBLE STRIPS WITH 6-INCH LONG LIFE PAVEMENT MARKINGS. | ADD PROJECT BREAK AT THE REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | DIV
2025-09-04 | HANDOUT | ADDITION |  | HS-2413R | HS-2413 | VARIOUS | VARIOUS, VARIOUS LOCATIONS IN DIVISION 13. INSTALL HORIZONTAL ALIGNMENT WARNING SIGNS. | ADD PROJECT BREAK AT THE REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. |  | Y | REG
2025-09-04 | HANDOUT | MODIFICATION | Statewide Project | HV-0001 | HV-0001 | VARIOUS | VARIOUS, LOCATIONS STATEWIDE. CONSTRUCTION OF ELECTRIC VEHICLE SUPPLY EQUIPMENT ALONG NORTH CAROLINA'S ALTERNATIVE CORRIDORS AND NEVI PLANNING. | ADD PRELIMINARY ENGINEERING AND CONSTRUCTION IN FY 26. THIS ACTION ADDS THESE PHASES TO THE 2026-2035 STIP. |  | Y | DIV
2025-09-04 | HANDOUT | ADDITION |  | NOTE |  |  | STIP AMENDMENTS APPROVED BY THE BOARD OF TRANSPORTATION IN JULY AND AUGUST 2025 (ITEM N FINAL) WILL BE AMENDED TO THE 2026-2035 STIP UPON FEDERAL APPROVAL (ANTICIPATED LATE 2025). THESE AMENDMENTS WERE PREVIOUSLY APPROVED ONLY FOR THE 2024-2035 STIP. |  |  | Y
2025-09-04 | HANDOUT | MODIFICATION | Northwest Piedmont RPO | R-5831 | R-5831 | US 601 (CAROLINA AVENUE) | US 601 (CAROLINA AVENUE), NC 67 (MAIN STREET) INTERSECTION IN BOONVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS. | TO ALLOW ADDITIONAL TIME FOR UTILITY RELOCATION, DELAY CONSTRUCTION FROM FY 25 TO FY 26. |  | N | DIV
2025-09-04 | HANDOUT | ADDITION | Rocky Mount Urban Area MPO | TC-0039 | TC-0039 | TAR RIVER TRANSIT | TAR RIVER TRANSIT, SYSTEMWIDE. PURCHASE 4 REPLACEMENT 30- FOOT VEHICLES. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | N | PT
2025-09-04 | HANDOUT | ADDITION | Rocky Mount Urban Area MPO | TC-0040 | TC-0040 | TAR RIVER TRANSIT | TAR RIVER TRANSIT, SYSTEMWIDE. PURCHASE ONE EXPANSION 25-FOOT VEHICLE. | ADD PROJECT AT THE REQUEST OF THE MPO. |  | N | PT
2025-09-04 | HANDOUT | MODIFICATION | Cabarrus-Rowan MPO | U-5761 | U-5761 | NC 3 (DALE EARNHARDT BOULEVARD) | NC 3 (DALE EARNHARDT BOULEVARD), US 29 / US 601 (CANNON BOULEVARD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | ADD UTILITIES IN FY 26 NOT PREVIOUSLY PROGRAMMED. |  | N | REG
2025-09-04 | HANDOUT | MODIFICATION | Charlotte Regional TPO | U-5906 | U-5906 | SR 2195 (TORRENCE CHAPEL ROAD) | SR 2195 (TORRENCE CHAPEL ROAD), SR 5544 (WEST CATAWBA AVENUE) INTERSECTION IN CORNELIUS.. CONSTRUCT INTERSECTION IMPROVEMENTS. | MODIFY SCOPE AT THE REQUEST OF THE DIVISION. |  | Y | DIV

## MPORPO
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | IDNUM | MPO_PERCENT | OFFICIAL_NAME
2025-09-04 | HANDOUT | MODIFICATION | B-6029 | 100 | SOUTHWESTERN RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | B-6034 | 100 | SOUTHWESTERN RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 100 | UPPER COASTAL PLAIN RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 100 | ROCKY MOUNT METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | BL-0050 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | BL-0176 | 100 | SANDHILLS METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | BN-0008 | 100 | EASTERN CAROLINA RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 100 | ROCKY MOUNT METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | C-5603F | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | C-5603I | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | C-5613J | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | EB-5600 | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | EB-5783 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 100 | HIGH COUNTRY RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | EB-5931 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | EB-5933 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | DELETION | EB-5971 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HB-0070 | 100 | PEANUT BELT RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HL-0023 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 100 | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HL-0123 | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HL-0163 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HL-0175 | 100 | SANDHILLS METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 100 | FOOTHILLS RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2003AK | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2003L | 100 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 100 | NORTHWEST PIEDMONT RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2014W | 100 | SOUTHWESTERN RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2402Q | 100 | GREENVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2403AA | 100 | JACKSONVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2403AW | 90 | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2403AW | 10 | CAPE FEAR RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2403AX | 100 | EASTERN CAROLINA RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2403T | 100 | JACKSONVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2410K | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HS-2410N | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2411D | 100 | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2412B |  | GASTON CLEVELAND LINCOLN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2413Q | 100 | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 34 | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 34 | LAND OF SKY RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 18 | HIGH COUNTRY RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 14 | FOOTHILLS RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | HV-0001 | 100 | STATEWIDE PROJECT
2025-09-04 | HANDOUT | MODIFICATION | R-5831 | 100 | NORTHWEST PIEDMONT RURAL PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | TC-0039 | 100 | ROCKY MOUNT METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | ADDITION | TC-0040 | 100 | ROCKY MOUNT METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | U-5761 | 100 | CABARRUS-ROWAN URBAN AREA METROPOLITAN PLANNING ORGANIZATION
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 100 | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION

## Funding Data
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | PROJ | SORT_SEQUENCE | Activity | Year | FUND_SOURT_SEQ | FUND | AMNT
2025-09-04 | HANDOUT | MODIFICATION | B-6029 | 13 | CONSTRUCTION | FY 2026 - | 26 | (BGOFF) | 1389000
2025-09-04 | HANDOUT | MODIFICATION | B-6029 | 13 | CONSTRUCTION | FY 2027 - | 26 | (BGOFF) | 611000
2025-09-04 | HANDOUT | MODIFICATION | B-6034 | 13 | CONSTRUCTION | FY 2026 - | 26 | (BGOFF) | 900000
2025-09-04 | HANDOUT | MODIFICATION | B-6034 | 13 | CONSTRUCTION | FY 2027 - | 26 | (BGOFF) | 600000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 7 | RIGHT-OF-WAY | FY 2026 - | 16 | (BFP) | 43000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 7 | RIGHT-OF-WAY | FY 2027 - | 16 | (BFP) | 517000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 7 | RIGHT-OF-WAY | FY 2028 - | 16 | (BFP) | 517000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 7 | RIGHT-OF-WAY | FY 2029 - | 16 | (BFP) | 517000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 7 | RIGHT-OF-WAY | FY 2030 - | 16 | (BFP) | 506000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 8 | UTILITIES | FY 2026 - | 16 | (BFP) | 3050000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 8 | UTILITIES | FY 2027 - | 16 | (BFP) | 3050000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 13 | CONSTRUCTION | FY 2030 - | 16 | (BFP) | 17404000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 13 | CONSTRUCTION | FY 2027 - | 16 | (BFP) | 18320000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 13 | CONSTRUCTION | FY 2029 - | 16 | (BFP) | 20152000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 13 | CONSTRUCTION | FY 2031 - | 16 | (BFP) | 13740000
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 13 | CONSTRUCTION | FY 2028 - | 16 | (BFP) | 21984000
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 1 | ENGINEERING | FY 2026 - | 27 | (BGDA) | 110000
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 1 | ENGINEERING | FY 2026 - | 36 | (L(M)) | 28000
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 7 | RIGHT-OF-WAY | FY 2026 - | 27 | (BGDA) | 493000
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 124000
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 13 | CONSTRUCTION | FY 2027 - | 27 | (BGDA) | 583000
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 146000
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 7 | RIGHT-OF-WAY | FY 2026 - | 6 | (CMAQ) | 8000
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 2000
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 3000
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 13 | CONSTRUCTION | FY 2027 - | 6 | (CMAQ) | 269000
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 1000
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 67000
2025-09-04 | HANDOUT | MODIFICATION | BL-0050 | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 307000
2025-09-04 | HANDOUT | MODIFICATION | BL-0050 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 133000
2025-09-04 | HANDOUT | ADDITION | BL-0176 | 1 | ENGINEERING | FY 2026 - | 27 | (CRPDA) | 60000
2025-09-04 | HANDOUT | ADDITION | BL-0176 | 1 | ENGINEERING | FY 2026 - | 36 | (L(M)) | 12000
2025-09-04 | HANDOUT | MODIFICATION | BN-0008 | 7 | RIGHT-OF-WAY | FY 2026 - | 27 | (CRP550) | 4000
2025-09-04 | HANDOUT | MODIFICATION | BN-0008 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 1000
2025-09-04 | HANDOUT | MODIFICATION | BN-0008 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CRP550) | 2432000
2025-09-04 | HANDOUT | MODIFICATION | BN-0008 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 608000
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 1 | ENGINEERING | FY 2025 - | 11 | (HP) | 998000
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 1 | ENGINEERING | FY 2025 - | 36 | (L(M)) | 250000
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 7 | RIGHT-OF-WAY | FY 2026 - | 11 | (HP) | 312000
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 78000
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 13 | CONSTRUCTION | FY 2027 - | 11 | (HP) | 1690000
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L) | 3690000
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 423000
2025-09-04 | HANDOUT | MODIFICATION | C-5603F | 7 | RIGHT-OF-WAY | FY 2026 - | 6 | (CMAQ) | 94000
2025-09-04 | HANDOUT | MODIFICATION | C-5603F | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 23000
2025-09-04 | HANDOUT | MODIFICATION | C-5603F | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 1892000
2025-09-04 | HANDOUT | MODIFICATION | C-5603F | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 473000
2025-09-04 | HANDOUT | MODIFICATION | C-5603I | 7 | RIGHT-OF-WAY | FY 2026 - | 6 | (CMAQ) | 200000
2025-09-04 | HANDOUT | MODIFICATION | C-5603I | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 50000
2025-09-04 | HANDOUT | MODIFICATION | C-5603I | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 3905000
2025-09-04 | HANDOUT | MODIFICATION | C-5603I | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 976000
2025-09-04 | HANDOUT | MODIFICATION | C-5613J | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 822000
2025-09-04 | HANDOUT | MODIFICATION | C-5613J | 13 | CONSTRUCTION | FY 2026 - | 27 | (BGDA) | 1121000
2025-09-04 | HANDOUT | MODIFICATION | C-5613J | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 405000
2025-09-04 | HANDOUT | MODIFICATION | C-5613J | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 1121000
2025-09-04 | HANDOUT | MODIFICATION | EB-5600 | 13 | CONSTRUCTION | FY 2026 - | 26 | (BGANY) | 440000
2025-09-04 | HANDOUT | MODIFICATION | EB-5600 | 13 | CONSTRUCTION | FY 2027 - | 27 | (BGDA) | 2400000
2025-09-04 | HANDOUT | MODIFICATION | EB-5600 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 600000
2025-09-04 | HANDOUT | MODIFICATION | EB-5600 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 128000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (TAANY) | 100000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 7 | RIGHT-OF-WAY | FY 2026 - | 36 | (L(M)) | 25000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2028 - | 6 | (CMAQ) | 286000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 20000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2027 - | 6 | (CMAQ) | 1736000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2028 - | 28 | (TAANY) | 122000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2027 - | 28 | (TAANY) | 738000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2026 - | 28 | (TAANY) | 9000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 10000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2028 - | 36 | (L(M)) | 143000
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 867000
2025-09-04 | HANDOUT | MODIFICATION | EB-5783 | 13 | CONSTRUCTION | FY 2026 - | 27 | (BGDA) | 1221000
2025-09-04 | HANDOUT | MODIFICATION | EB-5783 | 13 | CONSTRUCTION | FY 2026 - | 27 | (BGDA) | 398000
2025-09-04 | HANDOUT | MODIFICATION | EB-5783 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L) | 305000
2025-09-04 | HANDOUT | MODIFICATION | EB-5783 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 99000
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 1 | ENGINEERING | FY 2025 - | 9 | (FLAP) | 386000
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 1 | ENGINEERING | FY 2025 - | 36 | (L(M)) | 77000
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 7 | RIGHT-OF-WAY | FY 2025 - | 31 | (O) | 90000
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 13 | CONSTRUCTION | FY 2026 - | 9 | (FLAP) | 1310000
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 324000
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 13 | CONSTRUCTION | FY 2026 - | 61 | (HF(M)) | 394000
2025-09-04 | HANDOUT | MODIFICATION | EB-5931 | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 4013000
2025-09-04 | HANDOUT | MODIFICATION | EB-5931 | 13 | CONSTRUCTION | FY 2027 - | 27 | (BGDA) | 1322000
2025-09-04 | HANDOUT | MODIFICATION | EB-5931 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 1726000
2025-09-04 | HANDOUT | MODIFICATION | EB-5931 | 13 | CONSTRUCTION | FY 2027 - | 36 | (L(M)) | 330000
2025-09-04 | HANDOUT | MODIFICATION | EB-5933 | 13 | CONSTRUCTION | FY 2026 - | 28 | (TAANY) | 702000
2025-09-04 | HANDOUT | MODIFICATION | EB-5933 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 176000
2025-09-04 | HANDOUT | DELETION | EB-5971 | 1 | ENGINEERING | FY 2025 - | 28 | (TAANY) | 8000
2025-09-04 | HANDOUT | DELETION | EB-5971 | 1 | ENGINEERING | FY 2025 - | 36 | (L(M)) | 2000
2025-09-04 | HANDOUT | DELETION | EB-5971 | 13 | CONSTRUCTION | FY 2026 - | 28 | (TAANY) | 224000
2025-09-04 | HANDOUT | DELETION | EB-5971 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 56000
2025-09-04 | HANDOUT | MODIFICATION | HB-0070 | 13 | CONSTRUCTION | FY 2028 - | 16 | (BFP) | 1496000
2025-09-04 | HANDOUT | MODIFICATION | HB-0070 | 13 | CONSTRUCTION | FY 2027 - | 16 | (BFP) | 2860000
2025-09-04 | HANDOUT | MODIFICATION | HB-0070 | 13 | CONSTRUCTION | FY 2026 - | 16 | (BFP) | 44000
2025-09-04 | HANDOUT | MODIFICATION | HL-0023 | 1 | ENGINEERING | FY 2026 - | 28 | (T(DA)) | 64000
2025-09-04 | HANDOUT | MODIFICATION | HL-0023 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T(DA)) | 2265000
2025-09-04 | HANDOUT | MODIFICATION | HL-0023 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T(DA)) | 3542000
2025-09-04 | HANDOUT | MODIFICATION | HL-0023 | 13 | CONSTRUCTION | FY 2026 - | 31 | (O) | 10000
2025-09-04 | HANDOUT | MODIFICATION | HL-0023 | 13 | CONSTRUCTION | FY 2026 - | 61 | (HF) | 300000
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 8 | UTILITIES | FY 2026 - | 6 | (CMAQ) | 160000
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 8 | UTILITIES | FY 2026 - | 61 | (HF) | 40000
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 13 | CONSTRUCTION | FY 2027 - | 6 | (CMAQ) | 664000
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 8000
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 13 | CONSTRUCTION | FY 2026 - | 61 | (HF) | 2000
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 13 | CONSTRUCTION | FY 2027 - | 61 | (HF) | 166000
2025-09-04 | HANDOUT | MODIFICATION | HL-0123 | 1 | ENGINEERING | FY 2025 - | 27 | (CRPDA) | 800000
2025-09-04 | HANDOUT | MODIFICATION | HL-0123 | 1 | ENGINEERING | FY 2025 - | 36 | (L(M)) | 200000
2025-09-04 | HANDOUT | MODIFICATION | HL-0123 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CRPDA) | 400000
2025-09-04 | HANDOUT | MODIFICATION | HL-0123 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 100000
2025-09-04 | HANDOUT | ADDITION | HL-0163 | 1 | ENGINEERING | FY 2026 - | 27 | (CRPDA) | 40000
2025-09-04 | HANDOUT | ADDITION | HL-0163 | 1 | ENGINEERING | FY 2026 - | 36 | (L(M)) | 10000
2025-09-04 | HANDOUT | ADDITION | HL-0163 | 13 | CONSTRUCTION | FY 2026 - | 6 | (CMAQ) | 92000
2025-09-04 | HANDOUT | ADDITION | HL-0163 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CRPDA) | 535000
2025-09-04 | HANDOUT | ADDITION | HL-0163 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 157000
2025-09-04 | HANDOUT | ADDITION | HL-0175 | 1 | ENGINEERING | FY 2026 - | 27 | (CRPDA) | 151000
2025-09-04 | HANDOUT | ADDITION | HL-0175 | 1 | ENGINEERING | FY 2026 - | 36 | (L(M)) | 30000
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 7 | RIGHT-OF-WAY | FY 2026 - | 27 | (CRP550) | 2640000
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 7 | RIGHT-OF-WAY | FY 2026 - | 28 | (T(M)) | 660000
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 8 | UTILITIES | FY 2026 - | 27 | (CRP550) | 200000
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 8 | UTILITIES | FY 2026 - | 28 | (T(M)) | 50000
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 13 | CONSTRUCTION | FY 2026 - | 27 | (CRP550) | 2320000
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T(M)) | 580000
2025-09-04 | HANDOUT | MODIFICATION | HS-2003AK | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 151000
2025-09-04 | HANDOUT | MODIFICATION | HS-2003L | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 84000
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 7 | RIGHT-OF-WAY | FY 2026 - | 10 | (HSIP) | 300000
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 7 | RIGHT-OF-WAY | FY 2026 - | 61 | (HF) | 125000
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 8 | UTILITIES | FY 2026 - | 61 | (HF) | 25000
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 13 | CONSTRUCTION | FY 2027 - | 10 | (HSIP) | 389000
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 13 | CONSTRUCTION | FY 2028 - | 10 | (HSIP) | 120000
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 13 | CONSTRUCTION | FY 2029 - | 61 | (HF) | 584000
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 13 | CONSTRUCTION | FY 2030 - | 61 | (HF) | 181000
2025-09-04 | HANDOUT | MODIFICATION | HS-2014W | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 955000
2025-09-04 | HANDOUT | MODIFICATION | HS-2402Q | 7 | RIGHT-OF-WAY | FY 2025 - | 10 | (HSIP) | 6000
2025-09-04 | HANDOUT | MODIFICATION | HS-2402Q | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 142000
2025-09-04 | HANDOUT | MODIFICATION | HS-2403AA | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 13000
2025-09-04 | HANDOUT | ADDITION | HS-2403AW | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 245000
2025-09-04 | HANDOUT | ADDITION | HS-2403AX | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 628000
2025-09-04 | HANDOUT | MODIFICATION | HS-2403T | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 292000
2025-09-04 | HANDOUT | ADDITION | HS-2410K | 8 | UTILITIES | FY 2026 - | 10 | (HSIP) | 10000
2025-09-04 | HANDOUT | ADDITION | HS-2410K | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 101000
2025-09-04 | HANDOUT | MODIFICATION | HS-2410N | 7 | RIGHT-OF-WAY | FY 2025 - | 10 | (HSIP) | 10000
2025-09-04 | HANDOUT | MODIFICATION | HS-2410N | 8 | UTILITIES | FY 2025 - | 10 | (HSIP) | 5000
2025-09-04 | HANDOUT | MODIFICATION | HS-2410N | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 115000
2025-09-04 | HANDOUT | ADDITION | HS-2411D | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 625000
2025-09-04 | HANDOUT | ADDITION | HS-2412B | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 389000
2025-09-04 | HANDOUT | ADDITION | HS-2413Q | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 135000
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 13 | CONSTRUCTION | FY 2026 - | 10 | (HSIP) | 939000
2025-09-04 | HANDOUT | MODIFICATION | HV-0001 | 1 | ENGINEERING | FY 2026 - | 50 | (NEVI) | 9202000
2025-09-04 | HANDOUT | MODIFICATION | HV-0001 | 13 | CONSTRUCTION | FY 2026 - | 50 | (NEVI) | 91702000
2025-09-04 | HANDOUT | MODIFICATION | R-5831 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T) | 819000
2025-09-04 | HANDOUT | MODIFICATION | R-5831 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T) | 2418000
2025-09-04 | HANDOUT | MODIFICATION | R-5831 | 13 | CONSTRUCTION | FY 2028 - | 28 | (T) | 663000
2025-09-04 | HANDOUT | ADDITION | TC-0039 | 21 | CAPITAL | FY 2026 - | 36 | (L(M)) | 600000
2025-09-04 | HANDOUT | ADDITION | TC-0039 | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 2400000
2025-09-04 | HANDOUT | ADDITION | TC-0040 | 21 | CAPITAL | FY 2026 - | 36 | (L(M)) | 38000
2025-09-04 | HANDOUT | ADDITION | TC-0040 | 21 | CAPITAL | FY 2026 - | 79 | (5307) | 150000
2025-09-04 | HANDOUT | MODIFICATION | U-5761 | 8 | UTILITIES | FY 2027 - | 28 | (T) | 1790000
2025-09-04 | HANDOUT | MODIFICATION | U-5761 | 8 | UTILITIES | FY 2026 - | 28 | (T) | 10000
2025-09-04 | HANDOUT | MODIFICATION | U-5761 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T) | 1053000
2025-09-04 | HANDOUT | MODIFICATION | U-5761 | 13 | CONSTRUCTION | FY 2029 - | 28 | (T) | 2430000
2025-09-04 | HANDOUT | MODIFICATION | U-5761 | 13 | CONSTRUCTION | FY 2028 - | 28 | (T) | 4617000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 27 | (BGDA) | 7773000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T) | 14000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2029 - | 28 | (T) | 235000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2028 - | 28 | (T(DA)) | 775000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2028 - | 28 | (T) | 457000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T(DA)) | 1080000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2027 - | 28 | (T) | 638000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 28 | (T(DA)) | 23000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2029 - | 28 | (T(DA)) | 397000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 31 | (O) | 1257000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L) | 1078000
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 13 | CONSTRUCTION | FY 2026 - | 36 | (L(M)) | 7773000

## County Division
AGENDA_DATE | AGENDA_ITEM | AGENDA_ACTION | IDNUM | PERCENT | COUNTY | DIVISION
2025-09-04 | HANDOUT | MODIFICATION | B-6029 | 100 | MACON | 14
2025-09-04 | HANDOUT | MODIFICATION | B-6034 | 100 | JACKSON | 14
2025-09-04 | HANDOUT | MODIFICATION | B-6050 | 100 | JOHNSTON | 4
2025-09-04 | HANDOUT | MODIFICATION | BL-0009 | 100 | IREDELL | 12
2025-09-04 | HANDOUT | MODIFICATION | BL-0032 | 100 | EDGECOMBE | 4
2025-09-04 | HANDOUT | MODIFICATION | BL-0050 | 100 | JOHNSTON | 4
2025-09-04 | HANDOUT | ADDITION | BL-0176 | 100 | MOORE | 8
2025-09-04 | HANDOUT | MODIFICATION | BN-0008 | 100 | LENOIR | 2
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 50 | EDGECOMBE | 4
2025-09-04 | HANDOUT | MODIFICATION | BO-2417 | 50 | NASH | 4
2025-09-04 | HANDOUT | MODIFICATION | C-5603F | 100 | CABARRUS | 10
2025-09-04 | HANDOUT | MODIFICATION | C-5603I | 100 | CABARRUS | 10
2025-09-04 | HANDOUT | MODIFICATION | C-5613J | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | MODIFICATION | EB-5600 | 100 | NEW HANOVER | 3
2025-09-04 | HANDOUT | MODIFICATION | EB-5723 | 100 | UNION | 10
2025-09-04 | HANDOUT | MODIFICATION | EB-5783 | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | MODIFICATION | EB-5924 | 100 | WATAUGA | 11
2025-09-04 | HANDOUT | MODIFICATION | EB-5931 | 100 | UNION | 10
2025-09-04 | HANDOUT | MODIFICATION | EB-5933 | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | DELETION | EB-5971 | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | MODIFICATION | HB-0070 | 100 | BERTIE | 1
2025-09-04 | HANDOUT | MODIFICATION | HL-0023 | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | MODIFICATION | HL-0043 | 100 | WAKE | 5
2025-09-04 | HANDOUT | MODIFICATION | HL-0123 | 100 | CABARRUS | 10
2025-09-04 | HANDOUT | ADDITION | HL-0163 | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | ADDITION | HL-0175 | 100 | MOORE | 8
2025-09-04 | HANDOUT | MODIFICATION | HN-0019 | 100 | RUTHERFORD | 13
2025-09-04 | HANDOUT | MODIFICATION | HS-2003AK | 100 | NEW HANOVER | 3
2025-09-04 | HANDOUT | MODIFICATION | HS-2003L | 100 | NEW HANOVER | 3
2025-09-04 | HANDOUT | MODIFICATION | HS-2011G | 100 | SURRY | 11
2025-09-04 | HANDOUT | MODIFICATION | HS-2014W | 100 | MACON | 14
2025-09-04 | HANDOUT | MODIFICATION | HS-2402Q | 100 | PITT | 2
2025-09-04 | HANDOUT | MODIFICATION | HS-2403AA | 100 | ONSLOW | 3
2025-09-04 | HANDOUT | ADDITION | HS-2403AW | 100 | BRUNSWICK | 3
2025-09-04 | HANDOUT | ADDITION | HS-2403AX | 100 | DUPLIN | 3
2025-09-04 | HANDOUT | MODIFICATION | HS-2403T | 100 | ONSLOW | 3
2025-09-04 | HANDOUT | ADDITION | HS-2410K | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | MODIFICATION | HS-2410N | 100 | MECKLENBURG | 10
2025-09-04 | HANDOUT | ADDITION | HS-2411D | 100 | CALDWELL | 11
2025-09-04 | HANDOUT | ADDITION | HS-2412B | 80 | CLEVELAND | 12
2025-09-04 | HANDOUT | ADDITION | HS-2412B | 20 | GASTON | 12
2025-09-04 | HANDOUT | ADDITION | HS-2413Q | 100 | BURKE | 13
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 45 | BUNCOMBE | 13
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 23 | MADISON | 13
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 18 | YANCEY | 13
2025-09-04 | HANDOUT | ADDITION | HS-2413R | 14 | RUTHERFORD | 13
2025-09-04 | HANDOUT | MODIFICATION | HV-0001 | 100 | STATEWIDE | 99
2025-09-04 | HANDOUT | ADDITION | NOTE
2025-09-04 | HANDOUT | MODIFICATION | R-5831 | 100 | YADKIN | 11
2025-09-04 | HANDOUT | ADDITION | TC-0039 | 50 | EDGECOMBE | 4
2025-09-04 | HANDOUT | ADDITION | TC-0039 | 50 | NASH | 4
2025-09-04 | HANDOUT | ADDITION | TC-0040 | 50 | EDGECOMBE | 4
2025-09-04 | HANDOUT | ADDITION | TC-0040 | 50 | NASH | 4
2025-09-04 | HANDOUT | MODIFICATION | U-5761 | 100 | CABARRUS | 10
2025-09-04 | HANDOUT | MODIFICATION | U-5906 | 100 | MECKLENBURG | 10