## Data_Dictionary
Column Heading | Description
Primary Service Concept | A conceptual bundle of projects that would support 3 daily train roundtrips in the specified corridor.
Potential Project - Description | An individual capital project that could be funded on a standalone basis or as part of a Service Concept
ROM Estimate ($2024) [SCC 10-100 except 70] | A high-level cost estimate based on the GoTriangle 2024 commuter rail cost estimating methodology (Note: high-level nature of study requires additional guidance from NCDOT Rail Division to confirm cost estimates shown)
Start MP | Milepost where the project begins (point projects like a station or a grade separation are listed only in MP)
End MP | Milepost where the project ends
Service Concepts Supported | Identifies how many of the studied Service Concepts an individual Potential Project may support.
NCDOT Corridor ID Overlap | Indicates which of the USDOT Corridor ID grants received by NCDOT in Dec 2023 overlaps with this project
Local Decision Tree Category | Identifies the category of projects described in the Local Decision Tree to help stakeholders prioritize investments OUTSIDE of a Service Concept
Connects to National Passenger Rail Network | Existing Stations that provide one-seat ride Amtrak service to locations outside of the Triangle region and NC allow connections with other Amtrak trains
Positive Eligibility Triggers | Identification of project attributes that are likely to be able to be asserted as benefits under state or federal funding programs
Freight Rail Compatibiilty | Key attributes that indicate greater potential success for negotiations with freight railroads if either of them is "Yes"
Federal Eligibility | Which federal programs under current FRA policymaking the project is eligible to be funded
Attractiveness to Federal Critieria | How well an individual project is likely to match any criteria it is eligible for
Attractiveness to State Criteria | How well an individual project is likely to receive funding under the most recent SPOT guidelines in the REGIONAL IMPACT TIER. This rating is primarily generated from feedback from Alix Demers at NCDOT Rail and Alex Rickard at CAMPO, who are both top tier SPOT experts in NC. For example, one of the nuances that Alix Demers shared was: "Within the current Rail Mode scoring methodology (which can change every round of SPOT), if a rail corridor (or section thereof) that serves freight flows is currently congested and passenger operations are desired to be increased (or newly added), then submit-ting a project under SIT Code 1 (Freight rail corridor improvement or construction (main line track, sid-ings)) is wise because it would score at the Statewide Mobility level and not a lower level as it would if the project were submitted under SIT Code 5 (Passenger rail service). Notice the above text, “corridor … that serves freight flows is currently congested” – the section of track between Mebane and Raleigh is generally not highly congested from a freight standpoint. Therefore, add-ing additional infrastructure such as interlockings and sidings can be beneficial, but not necessarily need-ed for additional freight flows to operate in the corridor – and this is what partly drives the scor-ing. Hence, a project may rank better if it is under SIT Code 1than if under SIT Code 5 simply because it has a shot at the Statewide Mobility level, but how much better I could not tell you."
What This Means for How This Impacts the State Funding Rating In This Study: Generally speaking, any individual capital project that has a chance to be categorized as a freight project scores higher on Attractiveness to State Criteria because it may have access to funding in the Statewide Tier in addition to the Regional and Division Tiers of SPOT funding. Projects that are more likely to be in areas that see higher rail congestion (near the East Durham yard, in between Cary and Raleigh with its significant traffic and most Service Concepts using that stretch in the future)

## Glossary of Railroad Terms
Railroad Term | Definition
Control Point (CP) | A designated location on a railway line where signals and switches are remotely controlled by a train dispatcher.
Crossover | Trackwork hardware that allows trains to switch from one track to another
Interlocking | An arrangement of signal apparatus that prevents conflicting movements through an arrangement of tracks such as junctions or crossings.
Positive Train Control (PTC) | A processor-based/communication-based train control system designed to prevent train accidents. This is a requirement on lines that have regularly scheduled intercity/commuter rail passenger service.
Siding | A short section of track that branches off from the main line, allowing trains to be routed off the main track for various purposes. These purposes can include storing rolling stock, enabling trains to pass each other, or providing access to facilities like warehouses or industries.
Project Term | Definition
CP Modifications | Addition/relocation of crossovers to allow for more movements between tracks
Siding Conversion to Main | Connecting the gap between multiple sidings into one long stretch of main track. This allows for dedicated tracks to isolate freight and passenger train traffic.
Siding Extension | Extending sidings to accommodate expected freight train lengths. Some freight trains can go as long as 10,000 ft.
Signal Upgrade | Implementing Positive Train Control to an existing line that does not have the required signals
Track Upgrade | Consists fo upgrading the track infrastructure such as replacing and upgrading ties, installing more heavy-duty rail, etc.
Track Curve Realignment | Flattening the sharpness of an existing curve to allow for higher speeds
Yard Modifications | For this specific instance, the Raleigh to Wake Forest FSP design proposes to reroute the northern connection point to a more direct connection to the S-Line

## Projects
CAMPO Apex Rail Switching Operations Relocation Study
2026-06-11 |  |  |  |  | Service Concepts Supported | [5 empty] | NCDOT Corridor ID Overlap | [5 empty] | Positive Eligibility Triggers |  |  |  |  | Freight Rail Compatibility |  | Federal Eligibility | [5 empty] | Attractiveness to Fed Criteria
Primary Service Concept | Potential Project - Description | ROM Estimate | Start MP | End MP | Mebane to Clayton | Apex to Wake Forest | Sanford to Franklinton | Durham to Raleigh | Lillington to Raleigh | Carrboro to Durham | Winston-Salem to Raleigh | Raleigh to Wilmington | Raleigh to Fayetteville | Charlotte to Washington DC | J-Line | Local Decision Tree Category | Connects to National Passenger Rail Network | Benefits Existing Passenger Rail | Benefits Existing Freight Rail | Expands Passenger Rail Service/Capacity | Expands Freight Rail Service/Capacity | Existing Freight Rail Operating Agreement for Passenger Rail? | Freight Operator Interested in Passenger Rail? | MEGA | INFRA | CRISI | BUILD | FSP | RCE | MEGA | INFRA | CRISI | BUILD | FSP | RCE | Attractiveness to State Criteria
Durham Spur | Track upgrades to Durham Spur (Class 1 to Class 2) | $18 M | SDS 2.15 | SDS 20.7 | N | Y | Y | N | N | N | N | N | N | N | Y |  | Y | N | Y | N | Y | N | N | N | Y | Y | Y | N | Y | N | Low | Med to High | Low to Med | N | Med | Low to Medium
CSX Switching Ops Relocation | Relocating CSX's switching operations out of downtown Apex |  | TBD | TBD | N | Y | Y | N | N | N | N | N | N | N | Y |  | Y | N | Y | N | Y | Y | N/A | N | Y | Y | Y | N | N | N | Low | Med to High | Med | N | N | Low to Medium